## 2020-21 SSLEP Dashboard
Stoke on Trent & Staffordshire Local Enterprise Partnership Finance Dashboard - 1st Quarter Outturn 20-21
LEP CAPITAL FUNDING | [10 empty] | LEP REVENUE & CAPITAL INVESTMENT FUNDING |  |  | LEP REVENUE GRANT FUNDING
| The Local Growth Deal & The City Deal - Headline Numbers | [10 empty] | The Growing Places Fund (GPF) - Grants & Loans Facility
[5 empty] | Total Grant Allocation (£m) |  | Spend to Date (£m) | % Spend To Date | Funding Remaining (£m) |  |  | * Since 2013-14, 3 grants totalling £7.855m in value, plus 14 GPF loans totalling £6.543m have been awarded by SSLEP to local SMEs - a £14.398m total investment to date which has
|  |  | Local Growth Deal | # | 116.775 |  | 82.9299 | 71.02% | 33.8451 |  |  | leveraged in over £79.43m of Private Sector Investment in to the local economy over a 7 year period.
(Total Funding & Spend as @ 31st March 20)
* As at Q1 2020, after taking into account all outstanding contractual loan payments and repayments the GPF Loans Fund currently holds an available 'rolling' fund balance of £2.921m.
|  |  | 20-21 LGF Grant Allocation |  | 24.398 |  | 8.1692 | 33.48% | 16.2288
|  |  | (as @ Q1 20-21) | [8 empty] | * As at the 30th June 2020, the total value of GPF loans currently outstanding, i.e. in circulation, is £1.678m. Of this sum, £0.450m of loan is expected to be repaid back into the GPF
Loans Fund during 20-21.
|  |  | The City Deal |  | 24.75 |  | 17.97 | 72.61% | 6.78
(Total Funding & Spend as @ 31st March 20)
|  |  | 20-21 City Deal Grant Allocation |  | 4.13 |  | 1.048 | 25.38% | 3.082
(as @ Q1 20-21)
| # | Note - 20-21 Total LGD Funding has been increased by £18.5m following the approval of the Etruria Valley DfT Retained Scheme business case. Funding is due to be paid to the Accountable Body on the 10th July 20.
The Local Growth Deal (Local Growth Fund Grant)
* All LGD funding has to be spent by 31st March 21. The one exception to 'this rule' is the £18.5m Etruria Valley DfT Retained scheme which has been permitted to spend its LFG Grant funding beyond the set LGD deadline
following recent DfT approval of its final business case. The SSLEP's LGF Grant funding over the 6 year LGD programme has therefore increased to £116.775m in total.
* In early 20-21, due to the severe impact of the Covid pandemic, the Gov't has initiated a national review of funding resources available to stimulate economic recovery. Given this directive, BEIS has decided to initially pay 2/3rds of
the LGF Grant allocation to LEPS with the final 1/3rd to be paid following a review of the contractual status of all LGD projects & what the risk of slippage is. To date, £10.230m of the £15.345m total allocation has been paid.
* At the June 20 SPMG, approval was given to remove the remaining 20-21 LGD funding for the CCA scheme as the scheme is unable to spend any further LGF Grant funding this year. The SPMG approved that this remaining
£1.689m balance of funding be redirected to fund the i54 WE scheme. In addition, SPMG also identified and approved a reduction of £1.46m in LGF Grant funding for the CELR scheme which is unable to be spent within
| the BEIS deadline. This grant slippage funding is also to be redirected to the i54 WE scheme resulting in the total CELR LGF Grant funding being revised down to £7.009m for 20-21. Although 20-21 LGF Grant funding has | [13 empty] | The 2020-21 SSLEP Core Budget - £0.730m : £0.069m or 9.5% Spend to Date
either been withdrawn or reduced for these 2 key City of Stoke on Trent LGD schemes, this funding will be replaced, in future years, from future business rates secured from either the i54 EZ or th CVEZ or potentially funded
| from underspends on the future programme. | [13 empty] | * The annual Core Fund Grant is provided by the BEIS under Section 11 of the Industrial Development Act 1982 and is to be spent by 31st March 21. The 20-21
LEP Core budget of £0.730m was approved at the 27th February 2020 SSLEP Executive Board.
* The June SPMG also approved that the current unallocated balance of LGF Grant (£0.388m) be used to fund the i54 WE scheme taking total redirected LGF Grant funding up to £3.537m to date.
[16 empty] | Expenditure |  | £
| * At Q1 20-21, a total of £8.169m in LGF Grant funding (33.5%) has to date been spent against the remaining balance of LGF Grant funding of £24.398m. | [14 empty] | Staffing - SSLEP Secretariat |  | 385108
[16 empty] | LEP Operational Costs |  | 158250
| * As at 30th June 2020, the SSLEP has contractual committed 98.6% of the total £98.3m original LGD funding and has currently 2 LGD Grant Funding Agreements that are yet to be finalised with partners. | [10 empty] | * A new 'Open Call' (Round 14) was opened from December 19 to January 20 for new SME loan bids. Following the Call, 2 GPF loan bids for Dog & Bone Properties (£150,000) |  |  |  | Business Engagement & Support |  | 37500
|  |  |  | LGD Programme | LGF Funding (£m) | Current Status of Funding Agreement | [5 empty] | and Scott FM Ltd (£50,000) have now been initially Stage 1 approved by the GPF Panel and are currently subject to Stage 2 due diligence. |  |  |  | Strategic Planning - LIS Development # |  | 100000 | # NOTE - 20-21 LIS Implementation Plan is to be discussed at the July 20 SSLEP Executive Board.
|  | Blythe Park Development |  | OPEN CALL | 1.25 | LGF Funding Agreement drafted – Currently waiting for the GPF Agreement to be finalised for the match funding before both Agreements are signed. | [9 empty] | Project & Programme Development |  | 49500
|  | Stoke Power Upgrade |  | OPEN CALL | 0.1 | HoTs have been updated - Legal are currently drafting the contract. | [5 empty] | * There are currently 3 SME Stage 1 GPF loan approvals, totalling £1.6m, awaiting finalisation of Stage 2 due diligence procedures and respective Funding Agreements before GPF loan |  |  |  | Gross Expenditure |  | 730358
payments can be made. These are as follows:
| * During June, MHCLG announced a new funding call - Ideas for the Accelerating Existing Government Funded Capital Projects & Additional Shovel-Ready Capital Projects - to begin to stimulate the economy post Covid. | [14 empty] | Income
| SSLEP submitted an outline list of shovel-ready schemes and on the 1st July 20, the Gov't confirmed that the SLLEP will receive £23.7m of new grant funding which is to be spent over the following 18 months by 31st March 22. | [10 empty] | - Blythe Properties Ltd = £1.40m (Specified loan funding conditions now met by the Company & Stage 2 Due Diligence completed - FA shortly to be signed and 1st payment made.) |  |  |  | Core Fund Grant 2020-21 |  | 500000
[16 empty] | Core Fund Grant 2019-20 C/Fwd |  | 37474
AMBER |  |  | The LGD Programme continues to have an overall AMBER RAG rating due to delays in the completion of the 2 remaining LGD Scheme Funding arising Agreements. Any LGF Grant slippage | [6 empty] | CDGD 18 & CDGD 22 |  | - Dog & Bone Properties Ltd = £0.150m (Stage 2 Due Diligence completed - Currently stalled due to Covid-19 implications). |  |  |  | SSLEP Reserves - LGD Admin 'Top Slice' |  | 98337
|  |  | against the final year of the LGD Programme will be utilised to fund the i54 WE Scheme to ensure that the LGF Grant is fully spent in 20-21. | [12 empty] | SCC Direct Funding |  | 81547
[12 empty] | - Scott FM Ltd = £0.050m (Awaiting Stage 2 Due Diligence to be completed - currently stalled due to Covid-19 implication). |  |  |  | Chamber of Commerce Funding Contribution |  | 13000
| The City Deal | [14 empty] | Income |  | 730358
[11 empty] | GREEN |  | The 3 outstanding GPF loans are nearing Stage 2 completion and are expected to progress to Funding Agreements in the next quarter.
[13 empty] | After taking in to account all outstanding contractual loan payments and repayments, the available 'rolling' GPF Loan Fund balance is £2.921m. |  | * At Q1 20-21, only £0.069m of the LEP Core Budget has been spent to date. At this early stage of the year, it is anticipated that the LEP will fully spend its Core
Budget. If any over or underspend of the 20-21 LEP Core budget is to occur it will be transferred to the Reserves balances at the year end.
ESIF Funding - European Regional Development Fund (ERDF) & European Social Fund (ESF)
[14 empty] | GREEN |  | No issues arising. A 20-21 LIS Spend Plan is to be prepared, agreed and approved by the LEP Executive Board during Q2.
Annual Growth Hub Grant - £0.205m : £0.040m or 19.5% Spend to Date
* The 20-21 Growth Hub Grant allocation is £0.205m. An annual Grant Spending Plan has been submitted by the Growth Hub and approved by BEIS.
* This Grant is offered under Section 11 of the Industrial Development Act 1982 to support the further development of Growth Hubs to aligned to the Government's
commitment to ensure that businesses in every region have access to high quality advice and guidance via Growth Hubs and to further simplify access to support
for businesses.
* The 1st quarter claim for £39,925 covering the 1st quarter of 20-21 has recently been submitted - Currently, awaiting payment from BEIS.
[14 empty] | GREEN |  | No issues arising.
Supplementary 'One Off' Growth Hub Grant - £0.331m : £0.0m or 0% Spend to Date
* At the recent Budget, the Chancellor announced an additional £10 million nationally for LEPs for Growth Hubs for 20-21. Of the additional £10m Growth Hub funding,
the SSLEP's Growth Hub has been awarded £0.331m. This 'one off' funding will be provided under Section 11 of the Industrial Development Act, and will be payable
| * At Q1 20-21, a total of £1.048m or 25.4% of this year's City Deal's profiled spend has now been spent. | [13 empty] | quarterly in advance. This grant is to support further development of the Growth Hub to ensure businesses have access to high quality free and impartial advice and
guidance. In addition, the funding was awarded in recognition of immediate pressures faced by Growth Hubs in responding to the covid-19 pandemic.
| * The Keele SMART Energy Network Demonstrator scheme has a final planned City Deal spend of £0.630m profiled for the year and has, to date, spent 50.3% of this funding in Q1 20-21. | [9 empty] | No Spend update Available due to Covid-19 Pandemic - MHCLG claim payments are being maintained but the appraising of new ESIF projects has been suspended.
* A Supplementary Growth Hub Grant Spending Plan was submitted by the Growth Hub on 18th June 2020 and is currently awaiting approval by BEIS. The outline
| * The Stoke On Trent District Heat Network (DHN) has spent £0.731m (or 21%) of its planned £3.5m 20-21 City Deal profiled spend leaving a remaining balance of £2.65m of City Deal funding yet to be spent in 21-22. | [10 empty] | * As at Q1 20-21, £143.12m or 91.5% of the total ESIF Programme funding had, to date, been committed to projects with £107.43m or 75.1% of this committed funding sum claimed to |  |  | Spend Plan is as follows: |  |  |  | £.
[12 empty] | date. The ESIF Programme currently remains on target to commit its remaining theme allocations by the 31st March 21 & to have all grant claimed by 30th June 21. |  |  |  |  | Employees - Additional Advisor Capacity |  | 228000
GREEN |  |  | No immediate issues. Both the Keele SEND & SoT DHN schemes are expected to spend their respective 20-21 profiled spend this year. The DHN is expected to spend its remaining | [13 empty] | Economic Growth Planning |  | 72000
|  |  | £2.65m balance of City Deal funding post 20-21. | [8 empty] | MHCLG Recent Announcement - European Regional Development Fund (ERDF) Update and Response to COVID-19 |  |  |  |  | Growth Marketing Campaign |  | 20000
[12 empty] | The ERDF Programme is responding to two specific flexibilities provided by the European Commission in its Coronavirus Response Investment Initiative (CRII) and CRII+ regulations: |  |  |  |  | Growth Market Plans |  | 11500
| CVEZ Enterprise Zone Investment (18-19 to date) - NO Q1 20-21 UPDATE AVAILABLE | [10 empty] | * Greater flexibility to fund more of a project’s costs (the ‘intervention rate’). This is an emergency measure which enables us to fund up to 100% of a project’s costs for a limited period. |  |  |  |  | Total Supplementary Grant Funding |  | 331500
[6 empty] | * Key Risks include the pace of delivery; road infrastructure may not accommodate predicted CVEZ growth; Viability of sites | [5 empty] | * Businesses experiencing short-term financial difficulties may be classified as Undertakings in Difficulty (UiD). UiD were previously ineligible for ERDF support. EU regulations have
[6 empty] | may be underestimated & significantly the potential impact of delays to the delivery of the Etruria Valley Link Road. | [5 empty] | now been permanently changed to allow ERDF to support UiDs where this is allowed under State Aid rules. |  | GREEN |  | No issues arising.
|  |  |  | Value (£m) | [7 empty] | * MHCLG has announced that there will be no further Reserve Fund call and is currently reviewing plans for utilising remaining unallocated ERDF funding, including the mechanisms to
|  | Total Capital Expenditure |  | 7.656 |  | * Total SIP CVEZ Capital Investment is estimated at £13.2m - Prior year capital spend totalled £6.055m and as at 31st March 20 | [5 empty] | bring these to fruition. During June & July, Investment options are to be developed and they will be shortly providing further information on these plans as they develop
|  | Total Revenue Expenditure |  | 1.783 |  | CVEZ has spent a further £1.600m, taking total planned spend to date up to £7.656m. | [8 empty] | The Skills Advisory Panel Grant (£0.075m) : £0.020m or 26.7% Spend to Date
|  | Interest Paid on Borrowings |  | 0.25 | [7 empty] | ERDF & EAFRD - European Regional Development Fund & European Agricultural Fund for Regional Development
|  | Total Expenditure to Date |  | 9.689 |  | * Anticipated CVEZ business rates uplift per annum is currently estimated at £5.282m with £0.594m of rates delivered to date. | [5 empty] | * The ERDF & EAFRD Programme has to date committed £83.4m or 92% of its total funding with many projects & programmes now contracted and 'in delivery'. In comparison, |  |  | * In 19-20, the 1st year of the SAP Programme, the DfE provided a £0.075m grant to each local area establishing a Skills Advisory Panel (SAP) to enable it to
|  | Less, Total Business Rates Income |  | 1.11 | [7 empty] | the national average is c67% for ERDF & EAFRD commitments. The last ERDF Open Call yielded 27 new & extended bids seeking £22.5m in total. All but 3 of these applications are |  |  | increase its analytical capability sustainably and to support the development of the Local Industrial Strategy (LIS).
|  | Deficit Balance (as @ 31-03-2020) # |  | 8.579 |  | * Anticipated CVEZ Business Rates to be collected over 25 yrs is estimated at £118.69m - £81.95m for SoTCC & £36.74m in | [5 empty] | currently at the full application stage. Any remaining allocation was to feature in a National ERDF Reserve Call which was initially planned for Spring 20, but due to the COVID pandemic,
[6 empty] | total for SCC and NuLBC. SoTCC is expecting to produce a Business Rates surplus by 2025-26 & for SCC / Newcastle | [5 empty] | this has now been postponed indefinitely as government refocus EU financial resources to respond post Covid. |  |  | * In 20-21, the 2nd year of the Programme, the Government is keen that SAPs go even further in building Growth Hub analytical capability while at the same time
[6 empty] | under Lyme BC a surplus by 23-24 (Source - CVEZ SIP). | [8 empty] | increasing their local influence and their ability to address local skills challenges and grasp local skills opportunities. The Secretary of State for Education therefore
| Target 7,328 Jobs - At 31st March 20, 875 Jobs delivered to date | [10 empty] | * Total ERDF & EAFRD claimed to date by applicants now stands at £53.32m or 94.5% of the £83.4m total ERDF committed leaving £7.45m of funds yet to be committed in 20-21. |  |  | announced on 7th February 20, a further round of £0.075m funding for all local areas to enable them to continue to deliver the key objectives of the SAPs Programme.
# The current EZ Investment deficit has grown by a further £0.664m net since the reported 3rd Quarter of 19-20. For full details
[6 empty] | of the revenue & capital expenditure, plus business rates uplift please refer to Section 4 of the April 20 Annual CVEZ | [5 empty] | ESF - European Social Fund |  |  | * The SSLEP's SAP has now received its £0.075m SAP Grant from the DfE and was provided under Section 31 of the Local Government Act 2003 (‘a Section 31
| I54 Enterprise Zone & Western Extension |  |  |  |  | Quarterly Report. | [5 empty] | * Of the £59.72m of ESF committed to date, 91.2% of the £65.48m total ESF allocation. £54m of this sum is to be delivered through 3 national 'Opt In' Programmes by the DWP; The Skills |  |  | grant’) and is to be spent by 31 March 2021.
Funding Agency & the Big Lottery (Building Better Opportunities). In comparison, the national average is c70% for ESF commitments. Expressions of interest for a 2nd phase of
| * The initial borrowing to deliver the i54 Western Extension EZ development, which is currently 80% occupied, is expected to be fully repaid by April 24. Following this date, all business rates attained will be utilised to repay the | [10 empty] | the ESF 'Opt In' Prog has been submitted. DWP & Big Lottery 'Opt In' applications are currently being processed. Any returned funds will go to the Reserve Fund but due to the COVID |  |  | * To date, the SSLEP Executive Board has allocated £0.020m of the £0.075m grant. £0.005m has been approved towards the continued funding of the SAP Analyst
| £10m planned Investment that the LEP Exec Board has agreed to invest for the i54 Western Extension. | [10 empty] | pandemic, this has now been postponed indefinitely as gov't refocus their response post Covid. |  |  | & £0.015m towards the purchase of the EMSI data. The SAP Panel will be returning to Board for further approval when they have finalised their SAP Spend Plan.
GREEN |  |  | No issues arising for either Ceramic Valley or the i54 Western Extension Enerprise Zones | [7 empty] | GREEN |  | There is a 'high level of confidence' that the balance of ESIF funding remains 'on course' to meet the grant commitments deadline (31st March 21) & the grant | GREEN |  | No issues arising.
spend (30th June 21), subject to any Gov't national review of uncommitted ESIF Funding being undertaken to refocus financial resources on the pandemic.
Note on F38: Broad, John (F&R): Increase total LGF Grant to £117.775m now that EV DfT scheme (£18.5m) to be transferred to the AB following Business case approval? CHECK WITH SA