## SUMMARY
SSLEP Executive Board - Growth Deal Outputs Summary |  |  | at Q4 2019/20
JOBS created or safeguarded - actual vs forecast
These forecasts are based on scheme forecasts revised in April 2019. Forecasts will be revisited in Q1, 2020
Housing units constructed - actual vs forecast
These forecasts are based on scheme forecasts revised in April 2019. Forecasts will be revisited in Q1, 2020
Skills - Apprenticeships and Learners - ACTUALS
Target: 1,000

## CDGD TIMELINE
2020-04-01
GROWTH DEAL |  |  | SSLEP Confidential report GD Programme Delivery and Outputs Forecasting JOBS | [10 empty] | Outputs RAG - current position against forecast JOBS
Scheme title | Status | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | JOBS Delivered to date | % of 2019-20 target attained to date | JOBS Forecast by March 2020 | JOBS Forecast by March 2021 | JOBS Forecast 2021-22+ | ORIGINAL forecast (by 2025)
Apprenticeships - AME South Staffs College | Completed and closed, outputs delivered | [12 empty] | 107 | 100% | 107 | 107 | 107 | 107
Apprenticeships - AME NSCG | Completed and closed, outputs delivered | [12 empty] | 47 | 100% | 47 | 47 | 47 | 47
Apprenticeships - AME JCB | Completed and closed, outputs delivered | [12 empty] | 146 | 100% | 146 | 146 | 146 | 146
Lichfield Park | Completed - monitoring outputs | [12 empty] | 0 | 0% | 200 | 400 | 723 | 1100
Meaford | Completed - monitoring outputs | [12 empty] | 80 | 100% | 80 | 500 | 2200 | 2200
Bericote Four Ashes (Phases 1 and 2) | Completed - monitoring outputs | [12 empty] | 488 | 46% | 1060 | 1160 | 1360 | 1080
Branston Locks | Completed - monitoring outputs | [12 empty] | 0 | N/A | 0 | 460 | 3800 | 3844
Redhill (S) | Completed - monitoring outputs | [12 empty] | 89 | 100% | 89 | 220 | 220 | 125
Keele IC5 (S) | Completed - monitoring outputs | [12 empty] | 162 | 137% | 120 | 120 | 120 | 120
i54 (S) | Completed - monitoring outputs | [12 empty] | 80 | 62% | 130 | 190 | 190 | 190
Keele SIH | Completed - monitoring outputs | [12 empty] | 8 | N/A | 0 | 38 | 80 | 80
Skills Equipment Fund 1 | Completed - monitoring outputs | [12 empty] | 1067 | 171% | 626 | 626 | 626 | 626
Skills Equipment Fund 2 | Completed - monitoring outputs | [12 empty] | 0 | N/A | 0 | 285 | 285 | 285
SWAR | Live - in implementation | [12 empty] | 0 | 0% | 50 | 50 | 100 | 0
Tamworth Enterprise Quarter | Live - in implementation | [12 empty] | 80 | 167% | 48 | 98 | 98 | 98
Spode Church Street Phase 2 | Live - in implementation | [12 empty] | 0 | 0% | 20 | 20 | 20 | 20
Victoria Ground Phase 2 | Live - in implementation | [12 empty] | 0 | N/A | 0 | 44 | 44 | 44
Stoke Flood Alleviation | Live - in implementation | [12 empty] | 0 | N/A | 0 | 0 | 186 | 186
SME Expansion programme (GPF) | Live - in implementation | [12 empty] | 0 | N/A | 0 | 314 | 314 | 314
Etruria Valley | Approved - pending contract | [12 empty] | 0 | 0% | 500 | 1000 | 2200 | 2200
Stoke on Trent Railway Station Power Upgrade | Approved - pending contract | [12 empty] | 0 | N/A | 0 | 12 | 12 | 12
Blythe Park Extension Infrastructure project | Approved - pending contract | [12 empty] | 0 | N/A | 0 | 190 | 415 | 415
Cannock & Silverdale Enterprise Centres | Approved - pending contract | [12 empty] | 0 | N/A | 0 | 30 | 30 | 30
|  |  | Growth Deal - Jobs totals | [10 empty] | 2354 | 73.04% | 3223 | 6057 | 13323 | 13269
GROWTH DEAL |  |  | SSLEP GD Programme Delivery and Outputs Forecasting - HOUSING | [10 empty] | Outputs RAG - current position against forecast HOUSING
Scheme title |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | HOUSES Delivered to date | % of 2019-20 target attained to date | HOUSES Forecast by March 2020 | HOUSES Forecast by March 2021 | HOUSES Forecast 2021-22+ | ORIGINAL forecast (by 2025)
SWAR | Live - in implementation | [12 empty] | 174 | 79% | 220 | 320 | 2350 | 2200
Branston Locks | Live - in implementation | [12 empty] | 49 | 54% | 90 | 340 | 2500 | 2500
Victoria Ground Phase 2 | Live - in implementation | [12 empty] | 0 | N/A | 0 | 70 | 70 | 63
SME Expansion ptogramme | Live - in implementation | [12 empty] | 0 | N/A | 0 | 130 | 130 | 130
City East Link Road | Live - in implementation | [12 empty] | 0 | N/A | 0 | 0 | 499 | 499
Stoke Flood Alleviation | Live - in implementation | [12 empty] | 0 | N/A | 0 | 0 | 450 | 450
Blythe Park Extension Infrastructure project | Approved - pending contract | [12 empty] | 0 | N/A | 0 | 0 | 168 | 168
Stafford Gateway Land Acquisition | Approved - pending contract | [12 empty] | 0 | N/A | 0 | 0 | 48 | 48
|  | SSLEP GD Programme Delivery and Outputs Forecasting - HOUSING 2015: Growth Deal - Housing totals | 223 | 71.94% | 310 | 860 | 5999 | 5842
CITY DEAL |  | 2014: SSLEP City Deal Programme Delivery and Outputs Forecasting - JOBS
Keele SEND (City Deal) | Live - in implementation | [12 empty] | 0 |  | TBC | TBC | 440
DHN (City Deal) | Live - in implementation | [12 empty] | 0 |  | TBC | TBC | 229
AME Hub Phase 1 | Closed - outputs delivered | [12 empty] | 12 | 100% |  |  | 12
Innovative Growth in Stoke-on-Trent and Staffordshire (IGISS) | Closed - outputs delivered | [12 empty] | 251 | 113% |  |  | 222
Stoke-on-Trent and Staffordshire Business Support Programme (SSBSP) | Closed - outputs delivered | [12 empty] | 196 | 147% |  |  | 134
Stoke-on-Trent and Staffordshire Business Support Programme (SSBSP) Business Loan Fund | Closed - outputs delivered | [12 empty] | 251 | 104% |  |  | 241
|  | SSLEP GD Programme Delivery and Outputs Forecasting - HOUSING 2015: City Deal - Jobs totals | 710 | 55% |  |  | 1278
Construction
Outputs
Outputs - benefits realisation
15. Children's contract signature
Construction
Outputs - benefits realisation
Construction/
LEP intervention
Construction/
LEP intervention
Construction
Construction/Delivery - LEP intervention
Construction/
LEP intervention
Construction/Delivery - LEP intervention
Construction/Delivery - LEP intervention
Construction/
LEP intervention
Construction
Construction
Outputs
Phase 1
Outputs
Phase 2
Outputs - benefits realisation
TODAY
Outputs - benefits realisation
Outputs
Outputs - benefits realisation
Outputs
Out
puts
Outputs - benefits realisation
Construction/
LEP intervention
land purchase
Construction/Delivery - LEP intervention
Construction/
LEP intervention
Construction
Construction
Outputs
Phase 2
Outputs - benefits realisation
Outputs - benefits realisation
Outputs
Outputs
Outputs - benefits realisation
Construction/Delivery - LEP intervention
Construction/Delivery - LEP intervention
Construction/Delivery - LEP intervention
Construction/Delivery - LEP intervention
Outputs
Outputs - benefits realisation
Outputs - benefits realisation
Construction/Delivery - LEP intervention
Outputs - benefits realisation
Construction/
LEP intervention
Construction/
LEP intervention
Construction/
LEP intervention
Outputs
Outputs
Outputs
Construction/
LEP intervention
Outputs
Outputs - benefits realisation
Outputs - benefits realisation
Outputs - benefits realisation
Outputs - benefits realisation
Outputs - benefits realisation
Construction
Outputs
Construction
Outputs
Construction
Outputs
Outputs - benefits realisation
Construction
Outputs

## FORECASTING
LGF OUTPUTS - forecast/actual |  | Forecasting is revised annually in Q1. The data below shows change/slippage comparison between Q1 2017 and Q1 2019 forecasts.
73% % of 2019-20 target attained
Note: the columns show cumulative totals
JOBS |  | 15/16 | 16/17 | 17/18 | 18/19 | 19/20 | 20/21 | 21/22+
Lichfield Park | 2017 Forecast | 0 | 0 | 100 | 200 | 400 | 500 | 723
Lichfield Park | 2019 Forecast | 0 | 0 | 0 | 0 | 200 | 400 | 723
| Actual | 0 | 0 | 0 | 0 | 0
Meaford | 2017 Forecast | 0 | 0 | 350 | 750 | 1350 | 1800 | 2200
Meaford | 2019 Forecast | 0 | 0 | 0 | 0 | 80 | 500 | 2200
| Actual | 0 | 0 | 0 | 0 | 80
Bericote 4 Ashes | 2017 Forecast | 0 | 0 | 800 | 900 | 1000 | 1100 | 1100
Bericote 4 Ashes | 2019 Forecast | 0 | 0 | 0 | 250 | 1060 | 1160 | 1360
| Actual | 0 | 0 | 0 | 467 | 488
Branston Locks | 2017 Forecast | 0 | 0 | 0 | 350 | 550 | 750 | 3800
Branston Locks | 2019 Forecast | 0 | 0 | 0 | 0 | 0 | 460 | 3800
| Actual | 0 | 0 | 0 | 0 | 0
Tamworth EQ | 2017 Forecast | 0 | 8 | 23 | 48 | 73 | 98 | 98
Tamworth EQ | 2019 Forecast | 0 | 0 | 8 | 23 | 48 | 98 | 98
| Actual | 0 | 0 | 52 | 67 | 80
Keele SIH | Forecast | 0 | 0 | 0 | 0 | 0 | 38 | 80
| Actual | 0 | 0 | 0 | 0 | 8
Redhill | Forecast | 0 | 0 | 15 | 17 | 89 | 220 | 220
| Actual | 0 | 0 | 15 | 17 | 89
Keele IC5 | Forecast | 0 | 0 | 38 | 68 | 120 | 120 | 120
| Actual | 0 | 0 | 38 | 101 | 162
i54 | Forecast | 0 | 0 | 80 | 80 | 130 | 190 | 190
| Actual | 0 | 0 | 80 | 80 | 80
Stafford Western Access Route | Forecast | 0 | 0 | 0 | 0 | 50 | 50 | 100
| Actual | 0 | 0 | 0 | 0 | 0
Etruria | 2017 Forecast | 0 | 0 | 0 | 0 | 500 | 1000 | 2200
Etruria | 2019 Forecast | 0 | 0 | 0 | 0 | 500 | 1000 | 2200
| Actual | 0 | 0 | 0 | 0 | 0
SME Expansion | Forecast | 0 | 0 | 0 | 0 | 0 | 314 | 314
| Actual | 0 | 0 | 0 | 0 | 0
Spode | Forecast | 0 | 0 | 0 | 0 | 20 | 20 | 20
| Actual | 0 | 0 | 0 | 0 | 0
Stoke on Trent Railway Station Power Upgrade | Forecast | 0 | 0 | 0 | 0 | 0 | 12 | 12
Actual
Victoria Ground Phase 2 | Forecast | 0 | 0 | 0 | 0 | 0 | 44 | 44
Actual
Blythe Park Extension Infrastructure project | Forecast | 0 | 0 | 0 | 0 | 0 | 190 | 415
Actual
Stoke Flood Alleviation | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 186
Actual
Cannock & Silverdale EC's | Forecast | 0 | 0 | 0 | 0 | 0 | 30 | 30
Actual
72% of 2019-20 target attained
HOUSES |  | 15/16 | 16/17 | 17/18 | 18/19 | 19/20 | 20/21 | 21/22+
Branston Locks | 2017 Forecast | 0 | 0 | 60 | 180 | 300 | 450 | 2500
Branston Locks | 2019 Forecast | 0 | 0 | 0 | 10 | 90 | 340 | 2500
| Actual | 0 | 0 | 0 | 3 | 49
Stafford Western Access Route | Forecast | 0 | 0 | 0 | 170 | 220 | 320 | 2350
| Actual | 0 | 0 | 64 | 127 | 174
Victoria Ground Phase 2 | Forecast | 0 | 0 | 0 | 0 | 0 | 70 | 70
| Actual | 0 | 0 | 0 | 0 | 0
Blythe Park Extension Infrastructure project | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 168
| Actual | 0 | 0 | 0 | 0 | 0
Stafford Gateway Strategic Land Acquisition | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 48
| Actual | 0 | 0 | 0 | 0 | 0
SME Expansion programme | Forecast | 0 | 0 | 0 | 0 | 0 | 130 | 130
| Actual | 0 | 0 | 0 | 0 | 0
City East Link Road | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 499
| Actual | 0 | 0 | 0 | 0 | 0
Stoke Flood Alleviation | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 450
| Actual | 0 | 0 | 0 | 0 | 0
Skills - Apprenticeships and Learners - Forecasts (SEF 2)
SEF Round 2 |  |  | Target Apprenticeship Growth |  |  | Target new learners assisted
Ssouth Staffs College |  |  | 60 |  |  | 91
NSCG |  |  | 173 |  |  | 135
Stoke College |  |  | 52 |  |  | 104
TOTAL |  |  | 285 |  |  | 330
SEF 2 will be impacted by Covid as progress is now at a standstill (college-based).