## Programme Dashboard
SSLEP CDGD & EZ Programme Dashboard - 24/04/18 | [11 empty] | Public
[5 empty] | LGF Outputs - total forecast |  |  |  | LGF Outputs - achieved to date
SSLEP Ref | Scheme | Current Month BRAG | Current LEP Delivery Stage | SSLEP Contribution | Forecast Jobs | Forecast Housing | Forecast Skills - participation | Forecast Private Leverage | Actual Jobs | Actual Housing | Actual Skills - participation | Actual Private Leverage | Benefits Commence Date | Forecast Construction End Date
1 | Ceramic Valley Enterprise Zone (EZ) |  | Delivery | - | 6700 | - | - | £83.00m | 594 | - | - | £22.80m | 2016/17
2 | Stoke-on-Trent District Heat Network (City Deal) |  | Delivery | £19.75m | - | - | - | - | - | - | - | - |  | 2019-06-01
3 | Keele Smart Energy Network (City Deal) |  | Delivery | £5.00m | - | - | - | - | - | - | - | - |  | 2021-12-01
4 | Adult Skills Budget Pilot (City Deal) |  | On Hold | - | - | - | - | - | - | - | - | -
5 | Etruria Valley |  | Planning | £8.20m | 2200 | - | - | - | 0 | - | - | - | 2019/20 | 2019-07-01
6 | Stafford Western Access Route (SWAR) |  | Delivery | £22.21m | 100 | 2350 | - | £15.00m | 0 | 64 | - | £0.14m | 2017/18 | 2020-06-01
7 | Meaford Major Employment Site |  | Completed | £4.20m | 2200 |  | - | £2.00m | 0 | - | - | £2.00m | 2018/19 | 2016-06-01
8 | Branston Locks, Burton (Phase 1) |  | Completed | £5.09m | 3800 | 2500 | - | £1.36m | 0 | 0 | - | £0.00m | 2018/19 | 2017-09-01
9 | Lichfield Park |  | Completed | £4.00m | 723 | - | - | £1.16m | 0 | - | - | £1.15m | 2018/19 | 2015-12-01
10 | Bericote Four Ashes Ph1 + Ph2 |  | Completed | £2.86m | 1100 | - | - | £2.13m | tbc | - | - | £2.13m | 2017/18 | 2017-09-01
11 | Advanced Manufacturing Skills Hub - South Staffordshire College |  | Completed | £3.79m | - | - | 1205 | - | - | - | 454 | - | 2018-09-01 | 2017-06-01
12 | Advanced Manufacturing Skills Hub - Stafford College |  | Completed | £2.00m | - | - | 1263 |  | - | - | 1187 | - | 2018-09-01 | 2017-09-01
13 | Advanced Manufacturing Skills Hub - JCB Academy |  | Completed | £1.11m | - | - | 430 | £0.38m | - | - | 279 | £0.38m | 2018-09-01 | 2017-07-01
14 | Local Sustainable Transport Package (LSTP) |  | Delivery | £7.76m | - | - | - | £1.21m | - | - | - | £0.00m |  | 2019-03-01
15 | Town and City Centre Development Programme - Tamworth Enterprise Quarter |  | Delivery | £2.90m | 98 | - | - | £0.15m | 52 | - | - | £0.00m | 2017/18 | 2018-06-01
16 | Town and City Centre Development Programme - Leek Mill Heritage Quarter Regeneration |  | Withdrawn |  |  |  | - |  |  |  | -
17 | Town and City Centre Development Programme - Friarsgate, Lichfield |  | Planning | £2.66m | 330 | 46 | - | £49.92m | 0 | 0 | - | £0.00m | 2018/19 | 2019-09-01
18 | Town and City Centre Development Programme - Rugeley Town Centre Improvement Package |  | Completed | £0.75m | To confirm with CCDC | [8 empty] | 2017-12-01
18a | Town and City Centre Development Programme phase 2 - Rugeley Town Centre Improvement Package Ph 2 |  | Withdrawn
19 | Town and City Centre Development Programme - City Centre Access |  | Delivery | £6.41m | - | - | - | - | - | - | - | - |  | 2021-03-01
22 | Hanley-Bentilee Link |  | Await business case | £8.58m | Awaiting business case to confirm
23 | Spode Church Street Phase 2 |  | Planning | £0.50m | 20 | - | - | £0.23m | 0 | - | - | £0.00m | 2019/20 | 2019-02-01
24 | ROF Featherstone Strategic Employment Site |  | Await business case | £1.50m | Awaiting business case to confirm
25 | Keele Science and Innovation Park Smart Innovation Hub |  | Delivery | £1.00m | 80 | - | - | - | 0 | - | - | - | 2019/20 | 2019-03-01
26 | Skills Capital Equipment Fund |  | Planning | £1.76m | - | - | 300 | £1.76m | - | - | 0 | £0.00m | 2018/19 | 2020-07-01
27 | ROF Featherstone |  | Delivery | £0.57m | - | - | - | - | - | - | - | -
28 | Chatterley Valley West Site Access |  | Delivery | £0.07m | - | - | - | - | - | - | - | -
29 | Economic Regeneration Programme |  | Delivery | £2.09m | - | - | - | - | - | - | - | -
30 | Redhill Business Park |  | Delivery | £0.76m | 140 | - | - | - | 15 | - | - | - | 2017/18
31 | Keele Innovation Centre No.5 (IC5) |  | Delivery | £4.92m | 120 | - | - | - | 28 | - | - | - | 2017/18
32 | I54 South Staffordshire Employment Site |  | Delivery | £0.90m | 130 | - | - | - | 80 | - | - | - | 2017/18
33 | Lichfield Southern Bypass Phase 3 |  | Delivery | £0.33m | - | - | - | £9.07m | - | - | - | £0.00m
34 | Churnet Works small business units |  | Await business case | £0.50m | Awaiting business case to confirm
|  |  |  | £98.87m | 17741 | 4896 | 3198 | £179.50m | 769 | 64 | 1920 | £28.60m

## Project Progress
Active Projects - SSLEP City Deal and Local Growth Deal Programme Overview - 24/04/18 | [18 empty] | Public
[5 empty] | City Deal & Local Growth Deal Funding |  |  |  | Matched Funding, Other Grants & 3rd Party Contributions |  |  |  |  | Total Public & Private Sector Funding
| Project | Lead Organisation | SSLEP Deliverable | Construction start date | City Deal | Local Growth Fund 1 | Local Growth Fund 2 | Local Growth Fund 3 | ESIF | Local Authority | FE College / HE Funding | Growing Places Fund | Other Government Funding Grants | Total Public Funding (£M) | Private Sector Leverage | Total Project Funding (£M) | Anticipated End Date | O/A BRAG Status | Outcomes
| Ceramic Valley Enterprise Zone | SoTCC | Oversee delivery of EZ in accordance with implementation plan and MOU | 2016-04-01 | [14 empty] | Reported separately by Ceramic Valley Enterprise Zone programme
| Stoke-on-Trent District Heat Network | SoTCC | A Smart City District Heat Network across the City of Stoke-on-Trent | 2017-11-01 | 19.753 |  |  |  |  | 2.9 |  |  | 0.37 | 23.023 | 28.25 | 51.273 | Spring 2019 |  | Economic benefits, Social Benefits and Environmental Benefits Total scheme benefits of £76.1m with up to 229 direct jobs. 550 indirect safeguarded and created jobs valued at a further £63.5m. 10% cost saving for domestic heat customers 400 houses and 578 flats taken out of fuel poverty Up to 12,526 tonnes of CO2 per annum saved valued at £2.7m p.a.
| Keele Smart Energy Network | Keele University | A nationally significant, world-class Smart Energy Network Demonstrator at Keele University for research, development and application. | 2017-10-01 | 5 |  |  |  | 8.4 |  | 0.71648 |  |  | 14.1165 | 5 | 19.1165 | 2021-12-01 |  | 440 Jobs by 2021 (120 construction, 20 permanent, 300 indirect) 8,731 tonnes C02 saved
| Adult Skills Budget Pilot | SCC | Provide growth in sector specific traineeship and apprenticeships Upskill the current workforce in the sector to improve productivity Promote careers in the sector and use the facilities and training as a progression route | TBC | [9 empty] | 0 |  | 0 | 2018-05-01 |  | The spokes in the AME hub phase 1 had a collective target of delivering learning programmes to 2,199 learners once fully operational
| Etruria Valley | SoTCC | The Etruria Valley Infrastructure Scheme will deliver a major new gateway from the A500 into the City Centre and improve the highway in the Etruria Valley area, improving traffic flows, reducing congestion, and providing enhanced connectivity to the City Centre, thereby bringing economic and employment growth and environmental improvements | 2017-09-01 |  | 8.2 |  |  |  | 8.299 |  | 2.4 | 21 | 39.899 |  | 39.899 | 2019-07-01 |  | 2200 jobs , by Improved highways infrastructure kick starting development of enterprise area, with typical transport benefits (reduced journey times, etc.) by 2021? (TBC)
| Stafford Western Access Route (SWAR) | SCC | 1.2km road to ease congestion in Stafford town centre, open up housing sites to west of Stafford and promote employment growth | 2018-12-01 |  | 13.71 |  | 8.5 |  | 14.1338 |  |  | 11.09 | 47.4338 | 15.4 | 62.8338 | 2020-06-01 |  | Connected with the delivery of 2,200 houses to west of Stafford (scheme is not held to account on employment or housing benefits)
| Meaford Major Employment Site | SCC | Infrastructure works to open up business park, working with private sector developer | SCHEME COMPLETED |  | 4.1977 |  |  |  | 0.32578 |  |  |  | 4.5235 | 1.9988 | 6.5223 | 2016-06-01 |  | 2200 jobs, improved highways infrastructure by 2021
| Branston Locks, Burton (Phase 1) | SCC | Infrastructure works to open up business park and housing site working with private sector developer | SCHEME COMPLETED |  | 5.088 | [7 empty] | 5.088 | 1.356 | 6.444 | 2017-09-01 |  | 3844 jobs, 2500 houses and improved highways infrastructure partly delivered by 2021
| Lichfield Park | SCC | Infrastructure works to open up business park, working with private sector developer | SCHEME COMPLETED |  | 4 |  |  |  | 0.36 |  |  |  | 4.36 | 1.1143 | 5.4743 | 2015-12-01 |  | 723 jobs, improved highways infrastructure by 2021
| Bericote Four Ashes | SCC | Infrastructure works to open up business park, working with private sector developer | SCHEME COMPLETED |  | 2.86 |  |  |  | 0.18388 |  |  |  | 3.0439 | 2.134 | 5.1779 | 2016-06-01 |  | 1080 jobs, improved highways infrastructure by 2021
| Advanced Manufacturing Skills Hub - South Staffordshire College | South Staffordshire College | AgriSTEM academy comprising Agricultural manufacturing, technology, research and learning facilities | SCHEME COMPLETED |  | 3.791 |  |  |  |  | 1.655 |  |  | 5.446 |  | 5.446 | 2017-06-01 |  | 872 additional learners, 445 indirect jobs created, 156 additional employers engaged
| Advanced Manufacturing Skills Hub - Stafford College | Stafford College | Advanced manufacturing and design centre at Broad Eye Campus to support curriculum development in Science, Technology, Engineering and Maths | SCHEME COMPLETED |  | 2.002 |  |  |  |  | 1.5232 |  |  | 3.5252 |  | 3.5252 | 2017-09-01 |  | 144 additional learners, 75 employers engaged, 10 direct jobs created
| Advanced Manufacturing Skills Hub - JCB Academy | JCB Academy | Additional classroom and workspace areas to increase apprenticeship provision | SCHEME COMPLETED |  | 1.105 |  |  |  |  | 0.40752 |  |  | 1.5125 |  | 1.5125 | 2017-07-01 |  | 184 additional learners, 5 direct jobs created, 23 additional employers engaged
| Local Sustainable Transport Package (LSTP) | SCC and SoTCC | Package of measures to improve/encourage sustainable travel across Staffordshire and Stoke-on-Trent | 2016-04-01 |  | 6.3 |  | 1.46 |  | 2.346 |  |  |  | 10.106 | 6.806 | 16.912 | 2019-03-01 |  | City / town centre regeneration proposals to provide the greatest opportunity to encourage travel by sustainable transport to existing and future jobs
| Town and City Centre Development Programme - Tamworth Enterprise Quarter | Tamworth BC | Refurbishment of Assembly Rooms, Philip Dix Centre and Library to create Enterprise and Leisure opportunities | 2016-10-01 |  |  | 2.9 |  |  | 1.7492 |  |  | 0.715 | 5.3642 | 0.15 | 5.5142 | 2018-06-01 |  | 98 ongoing jobs, new enterprise centre, new restaurant and public realm improvements by 2021
| Town and City Centre Development Programme - Friarsgate, Lichfield | Lichfield DC | Redevelopment of bus station and wider transport improvements | 2018-09-01 |  |  | 2.69 | [5 empty] | 2.4 | 5.09 | 49.918 | 55.008 | 2019-09-01 |  | wider shopping centre development to create 750 jobs by 2021
| Town and City Centre Development Programme phase 1 - Rugeley Town Centre Improvement Package | Cannock Chase DC | Ph 1 - Flood defence works which will facilitate delivery of local employment and housing opportunity Ph 2 - Town centre improvements (allocation withdrawn) | SCHEME COMPLETED |  |  | 0.754 | [5 empty] | 4.3 | 5.054 |  | 5.054 | 2017-12-01 |  | tbc with CCDC
| Town and City Centre Development Programme - City Centre Access | SoTCC | Remodel the main gateway to the City Centre so that it can better meet the needs of all users, including vehicles, pedestrians and customers. Reduce congestion at key pinch points to stimulate economic activity and attract investment | 2016-08-01 |  |  | 6.41 |  |  | 2.1 |  |  |  | 8.51 |  | 8.51 | 2021-03-01 |  | Enhanced sustainable transport links to the City Centre at main gateway. Improved journey times and predictability through reduced congestion, opening up employment opportunity.
| Hanley-Bentilee Link | SoTCC | This is a transport scheme located to the south and east of the centre of Stoke-on-Trent consisting of 3 interdependent sections. Section 1 provides a new link to re-route traffic flows from the existing highway corridors facilitating improved journey times and reliability and provide new sustainable transport infrastructure | TBC |  |  |  | 8.58 |  | 16 |  |  |  | 24.58 |  | 24.58 | 2021-03-01 |  | tbc
| Spode Church Street Phase 2 | SoTCC | Conversion of the Grade 2 listed buildings around the Church Street courtyard off Church Street in Spode, to form an extension of the existing successful Artists Studios scheme | 2018-08-01 |  |  |  | 0.5 |  | 1.19 |  |  |  | 1.69 | 0.23 | 1.92 | 2019-04-01 |  | Renovation of listed building = 850 sqm. Number of studios created = 12 Number of jobs created = 32
| ROF Featherstone Strategic Employment Site | SCC | The ROF Featherstone site is a longstanding employment site in South Staffordshire, which has yet to come forward due to significant abnormal infrastructure costs associated with accessing the site from local highway networks | TBC |  |  |  | 1.5 |  |  |  |  | 6.75 | 8.25 | 4.25 | 12.5 | 2021-03-01 |  | tbc
| Keele Science and Innovation Park Smart Innovation Hub | Keele University | The Centre will be a national hub for intensive start up and business growth programmes designed for innovation intensive enterprises | TBC |  |  |  | 1 | 6.73 | 2.37 | 7.37 |  |  | 17.47 |  | 17.47 | 2019-03-01 |  | 80 additional jobs created by 2021
| Skills Capital Equipment Fund | SCC | The LEP funding will be used to create a skills capital equipment fund to allow local employers and training institutions to submit bids to secure funding to purchase state of the art capital equipment to enable the delivery of high quality and high level training programmes to support the growth in Stoke-on-Trent and Staffordshire's priority economic sectors | 2017-10-01 |  |  |  | 1.76 | [5 empty] | 1.76 | 1.76 | 3.52 | 2020-07-01 |  | 300 learners assisted in courses leading to full qualifications
| ROF Featherstone | SCC | Access and site infrastructure costs | 2016-10-03 |  | 0.57 | [7 empty] | 0.57 |  | 0.57 | 2020-03-31 |  | To be claimed within ROF Featherstone Strategic Employment Site scheme
| Chatterley Valley West Site Access | SCC | Off-site infrastructure works to provide appropriate accesses to the site | 2016-10-03 |  | 0.07 |  |  |  | 0.08 |  |  |  | 0.15 |  | 0.15 | 2021-03-31 |  | To be claimed within Ceramic Valley Enterprise Zone programme
| Economic Regeneration Programme | SCC | To generate economic activity in the short term by addressing immediate infrastructure and site constraints | 2016-10-03 |  | 2.09 | [7 empty] | 2.09 |  | 2.09 | 2021-03-31 |  | To be claimed within Growing Places Fund programme
| Redhill Business Park | SCC | Final construction account along with the payment for the additional electric supply | 2016-10-03 |  | 0.76 | [7 empty] | 0.76 |  | 0.76 | 2018-03-31 |  | 140 additional jobs from final development
| Keele Innovation Centre No.5 (IC5) | SCC | 30,000 sq. ft. net lettable high-quality office and workshop development | 2016-10-03 |  | 4.92 |  |  |  | 1.88 |  |  |  | 6.8 |  | 6.8 | 2018-03-31 |  | 120 additional jobs from remaining lettable area
| i54 South Staffordshire Employment Site | SCC | Site preparation and off site infrastructure servicing | 2016-10-03 |  | 0.9 | [7 empty] | 0.9 |  | 0.9 | 2018-03-31 |  | 130 additional jobs from remaining lettable area
| Lichfield Southern Bypass Phase 3 | SCC | To improve the quality and reliability of travel within Lichfield | 2016-10-03 |  | 0.33 |  |  |  | 0.19 |  |  | 7.76 | 8.28 | 9.07 | 17.35 | 2021-03-31 |  | to be claimed when full business case submitted and approved
| Churnet Works small business units | SMDC | 1003sqm of Commercial Floor Space - 8 business units (20 jobs created). | 2018-10-03 |  |  | 0.5 |  |  | 0.70847 |  |  |  | 1.2085 |  | 1.2085 | 2019-04-01 |  | 20 additional jobs to be created from 8 business unit lets
| Unallocated LGF Grant | [5 empty] | 0.85 | [6 empty] | 0.85 |  | 0.85
| TOTAL |  |  |  | 24.753 | 60.8937 | 14.104 | 23.3 | 15.13 | 54.8161 | 11.6722 | 2.4 | 54.385 | 261.454 | 127.4371 | 388.891