## Overview
SSLEP Programme Risk Management - March 2019
5 x Current "Red "rated risk level activities
Risk area | Risk Statement | Risk actions (mitigations) | Action progress
Strategic | The LEP review required all LEPs to review their functioning economic geographies, removing overlaps and confusion over accountability and responsibility on leadership & priority-setting. LEPs submitted details of their proposed future geographies by end of September 2018. The delay in government confirming future geographies will impact upon confirmation of Core Funding for 2019/20. This funding is partly allocated against delivering the move to incorporated status. | Chair to maintain engagement with government on progress, most recently (15 February) in notifying govt of company formation which aligns with current LEP geography ie county boundaries. Executive Board to discuss once geographies determined. | BEIS has reported that Minister will now determine geographies. Awaiting response
Strategic | Delay in receipt of additional £300k Core Funding for 2018/19 & 2019/20 (see Risk ID 2) means that LEP is undertaking work at risk in order to develop the Local Industrial Strategy (LIS) by Government's timetable of December 2019. Any delay in LIS production could impact upon ability to access forthcoming funding incl. UK Shared Prosperity Funds. If the additional Core funds do not arrive in a timely fashion, LEP will need to find funding and resources from else where. | See Risk above - resolution lies in the hands of government/SoS. | As risk above
CDGD | As a result of wider economic trends e.g. economic downturn, there is a possibility of developers being less likely to undertake speculative developments which could have the effect of Programme not meeting its objectives | Monthly highlight review at CDGD PAG | Active Projects Overview presented at monthly CDGD PAG Recently speculative builds have been completed at Bericote Four Ashes and Meaford. Lichfield Park build scheduled to commence early 2019
CDGD | As a result of the housing market not progressing as quickly as forecast, house builders in control of the absorption rate of build, there is a possibility of slower construction, housing taking longer to complete, which would have the affect of the programme not meeting its 2021 agreed targets | Identify schemes that could deliver housing benefits Review existing housing schemes forecast Lobby key stakeholders to bring forward housing schemes Working relationship with Homes England Have a balanced portfolio, introducing a number of smaller schemes Local authority housing Community builds Non-traditional housing e.g. modular | Regular reviews are undertaken at CDGD PAG. Outcomes dashboard is produced to highlight any potential areas of concern at an early stage. Open call prioritised on shovel ready schemes capable of delivering housing (and/or jobs) within LGF timescale. Action to add on survey of Housing Approvals.
CDGD | As a result of assigned schemes delivery timescales slipping, there is a possibility that the CDGD planned investment will not be achieved by March 2021, which would have the affect of the LEP failing to deliver its agreed Growth Deal objectives, leading to reputational impact and jeopardising future investment | Quarterly grant spend profiling in place for all CDGD projects. Early identification of current pipeline projects to alternatively fund from grant slippage | Quarterly spend reporting to the Audit & Finance Group and the LEP Executive Board to highlight potential scheme/project slippage risks against the current CDGD Delivery Programme Open call prioritised on shovel ready schemes capable of delivering housing (and/or jobs) within LGF timescale. Resulting in four additional schemes being brought into the growth deal programme, total £2.9m investmen

## Strategic
Title: | SSLEP Strategic Risk Register | [18 empty] | SSLEP Use
Updated: | March 2019
Identification | [11 empty] | Respond and Monitor | [7 empty] | Updates
Risk ID | Date identified | Identified by | Risk area | Risk Statement | Risk category | Risk owner | Controls | Current/net impact score | Current/net likelihood score | Current/net risk level | Current/net value of risk | Risk actions (mitigations) | Action owner | Expected Completion date | Action progress | Target impact score | Target likelihood score | Target risk level | Target value of risk | Date updated | Risk status
1 | 2018-12-10 | SSLEP PAG risk team | LEP governance | The LEP Review requires all LEPs to review their governance arrangements and move to incorporated body status by 1 April 2019. Financial penalties may be incurred by LEPs which do not meet this deadline. E.g. prevention of access to new funding. | Economic | Board mandated governance sub group | Board mandated sub group (agreed 18 Oct 2018) comprising: LEP Chair, Audit & Finance Committee Chair & match-funding partners (LEP Accountable Body & City Council). | D - Critical | 3 - Possible | High |  | Secretariat working with LEP Network to commission legal advice on incorporation and draft template on potential articles of association. Sub Group created to lead process Regular reports to Executive Board | Interim Partnership Manager | 2019-03-31 | LEP Network-commissioned legal advice received. Sub group established to determine and enact requirements. Company structure & articles agreed by Board and first 8 directors signed up 7 March 2019 | A - Minor | 1 - Rare | Low |  | 2019-03-12 | Open
2 | 2018-12-10 | SSLEP PAG risk team | LEP governance | The LEP review required all LEPs to review their functioning economic geographies, removing overlaps and confusion over accountability and responsibility on leadership & priority-setting. LEPs submitted details of their proposed future geographies by end of September 2018. The delay in government confirming future geographies is impacting upon confirmation of £300k Core Funding for 2018/19 & 2019/20. This funding is allocated against delivering the LEP Review, including move to incorporated status & increasing capacilty in the team in order to be 'fit' for future investment. | Political | Executive Board | Executive Board provided geographies statement to deadline and, through the Chair and partner organisations, has continued to engage with partner LEPs and with government as requested. | D - Critical | 3 - Possible | High |  | Chair to maintain engagement with government on progress, most recently (3 February) in notifying govt of company formation which aligns with current LEP geography ie county boundaries and (4 April) in agreeing to revisit opportunity for local resolution with GBSLEP. Executive Board to discuss once geographies determined. | Chair/Interim Partnership Manager | 2018-12-31 | BEIS has reported that Minister will now determine geographies. 03/04/19 Minister asked LEPs to revisit opportunity to reach agreement locally & meet with him in May to review. | C - Major | 3 - Possible | Medium |  | 03.Apr.2019 | Open
3 | 2018-12-10 | SSLEP PAG risk team | LEP governance | LEP Partnership Manager is retiring at end of December 2018 and 3 staff on temporary contracts which finish between May & July 2019. Outcome of LEP Review is still emerging, making it imprudent to recruit now for new LEP Director. Potential gap creates difficulties in delivering in a timely manner on LEP Review and wider LEP work programme. | Economic | Executive Board | Interim Partnership Manager put in place enabling handover with current Partnership Manager and ensuring no delays in delivery, while new Director is recruited. LEP Review work, including Resources & Staffing workstream, therefore continuing to timetable. | C - Major | 4 - Likely | Medium |  | Interim Partnership Manager put in place 3 December 2018 enabling handover. Governance review, including move to incorporated body, a review of secretariat and search for new LEP director to be undertaken once full details of the LEP review are known and full requirements can be assessed. | LEP Chair/Interim Partnership Manager | 2019-03-31 | Interim Partnership Manager now in place until 2 June, with option to extend further agreed by Board. Work to review resources underway, enabling LEP Board to agree temporary contract extension for 3 staff (to 30 september) while full details of the Review of Geographies work is awaited. | A - Minor | 4 - Likely | Low |  | 03.Apr.2019 | Open
4 | 10/12/.2018 | SSLEP PAG risk team | LEP governance | Partnership decisions are not made in a timely manner causing delays in the ability of the LEP to: respond to threats to project delivery timetables, creating slippage on programme delivery profiles; and act upon opportunities to increase resources to the partnership. | Economic | Executive Board | A small secretariat and a set of business-led sub-groups are in place, which have clear roles and responsibilities and which operate in accordance with an agreed scheme of delegation, reporting to the Executive Board. | C - Major | 4 - Likely | Medium |  | The agreed scheme of delegation operates within a clear reporting framework, ensuring decision-making is transparent and accountable. | All Sub Group Chairs | ongoing | Set of Sub-Groups and a Scheme of Delegation in place and operational. These will be reviewed as part of the LEP governance review. | A - Minor | 1 - Rare | Low |  | 2019-01-31 | Open
5 | 2018-12-10 | SSLEP PAG risk team | LEP governance | Loss of Executive Board knowledge due to several private sector board members potentially due to rotate in July 2019 | Political | Executive Board | Executive Board Terms of reference provides an opportunity to reduce a significant turnover of members by enabling members to seek re-nomination to the Board for a second 3 year term. | C - Major | 3 - Possible | Medium |  | The LEP Review will require four further private sector board members to be added to the board in order to achieve the required private-public balance. The timing of this will further assist in 'staggering' the rotation dates of board members. | Interim Partnership Manager | 2019-06-30 | this will be reviewed as part of the LEP governance review. | A - Minor | 2 - Unlikely | Low |  | 03.Apr.2019 | Open
6 | 2019-04-11 | Audit & Finance Group | LEP strategy | Delay in receipt of additional £300k Core Funding for 2018/19 & 2019/20 (see Risk ID 2) means that LEP is undertaking work at risk in order to develop the Local Industrial Strategy (LIS) by Government's timetable of December 2019. Any delay in LIS production could impact upon ability to access forthcoming funding incl. UK Shared Prosperity Funds. If the additional Core funds do not arrive in a timely fashion, LEP will need to find funding and resources from else where. | Economic | Executive Board | See Risk ID2 | D - Critical | 3 - Possible | High |  | See Risk ID2 resolution lies in the hands of government/SoS. | LEP Chair/Interim Partnership Manager | Unknown | See Risk ID2 | C - Major | 3 - Possible | Medium |  | 2019-04-11 | Open

## CDGD
Title: | SSLEP City Deal & Growth Deal Programme Risk Register | [18 empty] | SSLEP Use
Updated: | March 2019
Identification | [11 empty] | Respond and Monitor | [7 empty] | Updates
Risk ID | Date identified | Identified by | Risk area | Risk Statement | Risk category | Risk owner | Controls | Current/net impact score | Current/net likelihood score | Current/net risk level | Current/net value of risk | Risk actions (mitigations) | Action owner | Expected Completion date | Action progress | Target impact score | Target likelihood score | Target risk level | Target value of risk | Date updated | Risk status
6 | 2016-04-19 | SSLEP PAG risk team | Wider economy | As a result of wider economic trends e.g. economic downturn, there is a possibility of developers being less likely to undertake speculative developments which could have the effect of Programme not meeting its objectives | Economic | CDGD PAG | Monthly programme reporting in place for all projects; top risks identified | D - Critical | 4 - Likely | High |  | Monthly highlight review at CDGD PAG | All project leads | 2021-03-31 | Active Projects Overview presented at monthly CDGD PAG Recently speculative builds have been completed at Bericote Four Ashes and Meaford. Lichfield Park build scheduled to commence early 2019 | C - Major | 3 - Possible | Medium |  | 2019-01-29 | Open
13 | 2018-05-15 | SSLEP PAG risk team | Delivery of major projects | As a result of the housing market not progressing as quickly as forecast, house builders in control of the absorption rate of build, there is a possibility of slower construction, housing taking longer to complete, which would have the affect of the programme not meeting its 2021 agreed targets | Economic | CDGD PAG | Monthly programme reporting in place for all projects; top risks identified | D - Critical | 4 - Likely | High |  | Identify schemes that could deliver housing benefits Review existing housing schemes forecast Lobby key stakeholders to bring forward housing schemes Working relationship with Homes England Have a balanced portfolio, introducing a number of smaller schemes Local authority housing Community builds Non-traditional housing e.g. modular | Jacqui Casey | 2021-03-31 | Regular reviews are undertaken at CDGD PAG. Outcomes dashboard is produced to highlight any potential areas of concern at an early stage. Open call prioritised on shovel ready schemes capable of delivering housing (and/or jobs) within LGF timescale. Action to add on survey of Housing Approvals. | C - Major | 3 - Possible | Medium |  | 2019-01-29 | Open
18 | 2018-05-15 | SSLEP PAG risk team | LGF Funding | As a result of assigned schemes delivery timescales slipping, there is a possibility that the CDGD planned investment will not be achieved by March 2021, which would have the affect of the LEP failing to deliver its agreed Growth Deal objectives, leading to reputational impact and jeopardising future investment | Economic | CDGD PAG | Profile Finance Report tracker in place; 18/19 quarterly profile in place | D - Critical | 4 - Likely | High |  | Quarterly grant spend profiling in place for all CDGD projects. Early identification of current pipeline projects to alternatively fund from grant slippage | Simon Ablewhite | 2021-03-31 | Quarterly spend reporting to the Audit & Finance Group and the LEP Executive Board to highlight potential scheme/project slippage risks against the current CDGD Delivery Programme Open call prioritised on shovel ready schemes capable of delivering housing (and/or jobs) within LGF timescale. Resulting in four additional schemes being brought into the growth deal programme, total £2.9m investmen | B - Moderate | 3 - Possible | Medium |  | 2019-01-29 | Open
1 | 2016-04-19 | SSLEP PAG risk team | Resourcing | As a result of insufficient or inappropriate resources being assigned to projects, there is a possibility delivery may be delayed, which would have the effect of uncertainty, slippage and inability to attain stated benefits | Political | CDGD PAG | Monthly programme reporting in place for all projects; top risks identified | C - Major | 3 - Possible | Medium |  | Monthly highlight review at CDGD PAG | All project leads | 2021-03-31 | Active Projects Overview presented at monthly CDGD PAG Resourcing issues not raised as being a current issue | B - Moderate | 2 - Unlikely | Low |  | 2019-01-29 | Open
2 | 2016-04-19 | SSLEP PAG risk team | Delivery of major projects | As a result of failure of the vital few projects to deliver, which are concentrated within very few organisations / applicants, there is a possibility of significant impact on the deliverability of programme outcomes, which would have the effect of the overall programme being unable to attain the stated benefits agreed by Government within the time frame, spend / underspend | Political | CDGD PAG | Frequent in depth reviews / attendance at project boards carried out on all key programmes | C - Major | 4 - Likely | Medium |  | Programme of regular reviews of all key projects in place. Reporting back to CDGD PAG | Jacqui Casey | 2021-03-31 | Risk Accepted Regular reviews / project board dates schedule in place and in progress Outcomes dashboard produced to highlight potential areas of concern | C - Major | 4 - Likely | Medium |  | 2019-01-29 | In Control
4 | 2016-04-19 | SSLEP PAG risk team | Contracts | As a result of failure to contract projects to deliver and / or slippage of funding approvals, there is a possibility of failing to deliver projects and outputs within the agreed time frame or budget | Legal | CDGD PAG | Funding tracker in place to highlight status / progress or all agreements | C - Major | 2 - Unlikely | Medium |  | Regular review with Legal lead in place | Dave Nicholls | 2021-03-31 | Risk Accepted All GD1 & GD2 funding agreements fully in place, GD3 schemes in progress in line with business case approvals Open call prioritised on shovel ready schemes capable of delivering housing (and/or jobs) within LGF timescale | C - Major | 2 - Unlikely | Medium |  | 2019-01-29 | In Control
5 | 2016-04-19 | SSLEP PAG risk team | Programme Allocation | As a result of Programme allocation only up to 100%, there is a possibility of no over programming to allow for slippage / project changes, which would have the effect of Programme being unable to recover from slippages / failure of individual project deliverables | Political | CDGD PAG | Reviewed monthly at CDGD PAG | C - Major | 3 - Possible | Medium |  | Review to identify all additional projects that can be brought forward in progress GD3 bid included basket of schemes Open call to refresh pipeline held December 2017 Further open call held September 2018 | Jacqui Casey | 2021-03-31 | Project Slippage scheme identified for 17/18, to be included within programme to alleviate forecast slippage (see also Risk ID: 12) GD3 bid included wider basket of alternative schemes; reviewed at APAG October 17 Open call issued December 2017, recommendations presented to Exec Group February 2018 Exec. Group authorised Churnet Works business case, February 2018; to replace London Mill scheme Further open call to be considered by Exec Board July 2018 for September launch | C - Major | 3 - Possible | Medium |  | 2019-01-29 | Open
7 | 2016-04-19 | SSLEP PAG risk team | Project mix | As a result of not having the right mix of focused projects, there is a possibility of the Programme not being able to deliver the agreed outputs, which could have the effect of the Programme missing its energy, housing, jobs, skills targets | Economic | CDGD PAG | All GD3 submissions assessed against Strategic fit; Value for money; Deliverability criteria | C - Major | 3 - Possible | Medium |  | GD3 schemes agreed; additional basket of alternative schemes also identified | Jacqui Casey | 2021-03-31 | GD3 schemes agreed; due diligence and business case appraisals to be carried out to identify outputs Exec. Group authorised inclusion of Churnet Works scheme, February 2018; to replace London Mill scheme SPMG considered open call shortlisted schemes (29/01/19); recommendations to Executive Board 14th February 2019 | C - Major | 2 - Unlikely | Medium |  | 2019-01-29 | Open
8 | 2016-04-19 | SSLEP PAG risk team | Relationship Management | As a result of a significant proportion of the Programme being reliant upon private sector developers, without a robust relationship management there is a possibility that developers do not perform according to contract, which would have the effect of the Programme missing its energy, housing, jobs, skills targets | Social | CDGD PAG | Monthly programme reporting in place for all projects; top risks identified | C - Major | 3 - Possible | Medium |  | Monthly highlight review at CDGD PAG | All project leads | 2021-03-31 | Risk Accepted Active Projects Overview presented at monthly CDGD PAG Liberty Park - mtng held with developers 24/05/17 SSLEP Programme Consultant appointed to review key programmes | C - Major | 3 - Possible | Medium |  | 2018-07-25 | In Control
9 | 2016-04-19 | SSLEP PAG risk team | Programme Governance | As a result of no robust appraisal of business cases or lack of expertise to challenge projects and oversee delivery, there is a possibility of the Programme underperforming, which would have the effect of overspends / underspends / under achievement of outputs | Social | CDGD PAG | All business case submissions are assessed against: - SSLEP Full Business Case Assessment template - "green book guidance checklist for assessing business cases" | C - Major | 2 - Unlikely | Medium |  | All business cases to be reviewed prior to presentation at CDGD PAG | Jacqui Casey | 2021-03-31 | Meetings arranged with all business case leads ahead of submission to CDGD PAG SSLEP Full Business case Assessment template introduced January 2017 All business cases independently assessed before presentation to CDGD PAG Lessons learned analysis being introduced Take into account an applicant's previous or current delivery of CDGD funded schemes | C - Major | 2 - Unlikely | Medium |  | 2019-01-29 | In Control
14 | 2018-05-15 | SSLEP PAG risk team | Performance Measurement | As a result of over optimism of benefits achievement, there is a possibility of the CDGD programme over estimating the forecast benefits, which would have the affect of the programme missing agreed LEP targets | Economic | CDGD PAG | Quarterly review of all scheme outputs, coincide with national LGF reporting | C - Major | 3 - Possible | Medium |  | Individual scheme review of outputs with all project leads. Report back to CDGD PAG | Dave Nicholls | 2021-03-31 | Monthly highlight reporting in place. Quarterly review of all outputs in place | B - Moderate | 2 - Unlikely | Low |  | 2018-08-30 | Open
15 | 2018-05-15 | SSLEP PAG risk team | LGF Funding | As a result of a number of projects not progressing to original timescale, there is a possibility of the 18/19 LGF funding profile will be significantly underspent, which would have the affect of future LGF funding being cut back | Economic | CDGD PAG | 2018/19 Profile Finance Report tracker in place; quarterly profile in place | C - Major | 4 - Likely | Medium |  | Quarterly profiling in place for all CDGD projects. Early identification of current pipeline projects to alternatively fund from grant slippage | Simon Ablewhite | 2019-04-30 | Initial report and outlook to May CDGD PAG LEP Executive Board (May 18) agreed to run an open call for initiatives to refresh pipeline and identify suitable alternative schemes; recommendations to be presented to LEP Exec Board in Sept/Oct 2018 Exec Group approved SME Expansion Support business case, February 2018; to be utilised to ensure 17/18 spend profile met | A - Minor | 2 - Unlikely | Low |  | 2018-08-30 | Open
16 | 2018-05-15 | SSLEP PAG risk team | Contracts | As a result of no deadlines and/or weak clawback clauses in the funding agreement, there is a possibility that failing schemes cannot be withdrawn in a timely manner, which would have the affect of blocking potential investment in other 'ready to go' schemes that can could deliver same or enhanced outputs | Legal | CDGD PAG | Monthly programme reporting in place for all projects; top risks identified | C - Major | 4 - Likely | Medium |  | Standard funding agreement template in place, agreed with Legal team Programme consultant reviewing effectiveness of template | Dave Nicholls | 2019-03-31 | All GD1,GD2 and majority of GD3 funding agreements already in place A review of existing template has been carried out by programme consultant. This is now part of the Assurance Framework pack - draft of this is subject to formal approval process (including Legal) | B - Moderate | 2 - Unlikely | Low |  | 20.Mar.2019 | Open
17 | 2018-05-15 | SSLEP PAG risk team | Communication | As a result of lack of visibility / understanding of availability of LEP funding sources, there is a possibility that weaker schemes will be considered for inclusion in the CDGD programme, at the expense of unknown stronger candidates, which would have the affect of the LEP failing to maximise its forecast outputs | Political | CDGD PAG | SSLEP website details assurance framework. Open call comms distributed widely via email, website and social media | C - Major | 4 - Likely | Medium |  | Ensure effective, timely and widely distributed communications in place for pipeline submission requests | Jacqui Casey | 2021-03-31 | Annual assurance framework review completed April 2018 Growth deal funding open call communications to be distributed widely | B - Moderate | 3 - Possible | Medium |  | 2019-01-29 | Open
19 | 2018-07-25 | SSLEP PAG risk team | Programme Governance | As a result of the current national review of LEPs, there is a possibility of uncertainty around the future of the CDGD programme in general, which would have an impact on governance, programme investment and outputs | Political | CDGD PAG | Regular reviews at regional & national level SSLEP Executive Board responsible for determining local submission | C - Major | 4 - Likely | Medium |  | PD participating in LEP Network discussions; regular dialogue at regional and national level SSLEP Executive to submit local submission by 30th September 2018 Existing programmes likely to be protected, regardless of review outcome. Potential that unallocated funding could be at risk | Jacqui Casey | 2019-03-31 | LEP Review business sessions organised for w/c 3rd Sept to gain views and support of local private sector businesses Meeting arranged for review with public sector chief executives Regular dialogue at regional & national level | C - Major | 3 - Possible | Medium |  | 2019-01-29 | Open
20 | 2019-04-11 | SSLEP PAG risk team | Programme Allocation | Private sector may not have time to participate in open calls. Recent open call process took 5 months from start to completion. Process should be more streamlined where possible to encourage more private sector led applicants to access funds. | Economic | CDGD PAG | Assurance Framework | B - Moderate | 3 - Possible | Medium |  | Current Independent Technical assistance contract is coming up for renewal. New contract could build in a light touch review for consideration bty S151 Officer & Executive Board | Strategic Programme Management Board | 2019-05-31 | Tender specification under preparation by Interim Partnership Manager | B - Moderate | 3 - Possible | Medium |  | 2019-04-11 | Open
3 | 2016-04-19 | SSLEP PAG risk team | Communication | As a result of lack of or poor communications between delivery teams, partners and CDGD Board, both internally & externally, there is a possibility of bypassing established governance framework and loss of focus on deliverables, which would have the effect of overspend / underspend of expenditure, lack of clear management and lack of accountable governance | Political | CDGD PAG | Monthly programme reporting in place for all projects; top risks identified | B - Moderate | 2 - Unlikely | Low |  | Monthly highlight review at CDGD PAG. CDGD PAG restructured to focus on assurance and strategic areas | All project leads | 2021-03-31 | Risk Accepted Active Projects Overview presented at monthly CDGD PAG Areas of concern escalated to Strategic Board as necessary Channels of communication working well, Strategic Board focus being reassessed | B - Moderate | 2 - Unlikely | Low |  | 2018-07-25 | In Control
10 | 2016-04-19 | SSLEP PAG risk team | Performance Measurement | As a result of inadequate systems in place to capture, monitor & report programme performance, there is a possibility of being unable to accurately measure progress and stated benefits, which would have the effect of inaccurate reporting | Technological | CDGD PAG | Standard template in place for monthly project reporting | A - Minor | 2 - Unlikely | Low |  | Monthly project highlight reporting | Dave Nicholls | 2018-05-15 | Monthly reporting summarised for CDGD PAG; full reports available on request Outputs monitored monthly; request to Gestamp to ensure Bericote jobs outputs - data now received No longer a key risk to the programme | A - Minor | 2 - Unlikely | Low |  | 2018-05-15 | Closed
11 | 2016-05-24 | CDGD PAG | LGF Funding | There is a risk that the 16/17 LGF funding profile will be significantly underspent. As a result of a number of projects not progressing to original timescale there is a possibility of future LGF funding being cut back if current years profile is not met | Economic | CDGD PAG | 2016/17 Profile Finance Report tracker in place; quarterly profile in place | A - Minor | 2 - Unlikely | Low |  | Quarterly profiling introduced for all projects. Review to identify areas that can be brought forward in progress (see also Risk ID 5) | Simon Ablewhite | 2017-05-08 | Monthly reporting to CDGD PAG Project Slippage schemes identified and included within 16/17 LGF programme Overall 16/17 outcome = £0.245m (0.7%) slippage Given GD3 funding profile from Gov't; potential 17/18 could have similar risk | A - Minor | 2 - Unlikely | Low |  | 2017-05-03 | Closed
12 | 2017-05-22 | CDGD PAG | LGF Funding | There is a risk that the 17/18 LGF funding profile will be significantly underspent. As a result of a number of projects not progressing to original timescale and GD3 profile from DCLG larger than expected for 17/18, there is a possibility of future LGF funding being cut back if current years profile is not met | Economic | CDGD PAG | 2017/18 Profile Finance Report tracker in place; quarterly profile in place | A - Minor | 2 - Unlikely | Low |  | Quarterly profiling in place for all projects. Early identification of pipeline projects London Mill, Leek schemes & Rugeley Town Centre Ph 2, identified as projects that will not progress | Simon Ablewhite | 2018-04-30 | Initial report and outlook to June CDGD PAG Executive Group (Oct 17) agreed to run an open call for initiatives to refresh pipeline and identify suitable alternative schemed; recommendations to be presented to Exec Group February 2018 Exec Group approved SME Expansion Support business case, February 2018; to be utilised to ensure 17/18 spend profile met | A - Minor | 2 - Unlikely | Low |  | 2018-05-15 | Closed

## GPF
Title: | SSLEP Growing Places Fund Risk Register | [18 empty] | SSLEP Use
Updated: | March 2019
Identification | [11 empty] | Respond and Monitor | [7 empty] | Updates
Risk ID | Date identified | Identified by | Risk area | Risk Statement | Risk category | Risk owner | Controls | Current/net impact score | Current/net likelihood score | Current/net risk level | Current/net value of risk | Risk actions (mitigations) | Action owner | Expected Completion date | Action progress | Target impact score | Target likelihood score | Target risk level | Target value of risk | Date updated | Risk status
1 | 2018-11-09 | GPF | Programme delivery | GPF calls fail to attract eligible applications from businesses | Economic | LA Accountable Body & GPF Steering Group | GPF Steering Group monthly review | B - Moderate | 2 - Unlikely | Low |  | Replace 10 week bidding window with a continuous bidding call and publicise GPF via a wide range of media, events and partnership activity | GPF |  | Continuous bidding call appears to have worked with a steady number of expressions of interest converting to Stage 2 applications and now progressing to contracted projects. January A&F Group consider this risk to be "In Control" as applications are oversubscribed | B - Moderate | 2 - Unlikely | Low |  | 2019-04-04 | In Control
2 | 2018-11-09 | GPF | Financial | Potential for default or delayed repayment of GPF loans | Legal | LA Accountable Body & GPF Steering Group | GPF Steering Group monthly review | C - Major | 3 - Possible | Medium |  | Loan repayment schedule included in GPF Funding Agreement together with explicit conditions stating the terms of the loan. Regular monitoring and close liaison with business applicant to identify any issues affecting the timely repayment of the loan | GPF |  | Only 1 business applicant has defaulted on their loan to date and the terms and consequences, including additional interest charged on the outstanding balance, were executed for one of the 2 projects of default. All GPF contracted schemes will be closely monitored to identify any potential default situations | B - Moderate | 1 - Rare | Low |  | 2019-04-04 | Open
3 | 2019-04-04 | GPF | Programme delivery | GPF pipeline over-subscribed | Economic | LA Accountable Body & GPF Steering Group | GPF Steering Group monthly review | B - Moderate | 3 - Possible | Medium |  | Utilise GPF panel to consider projects in competitive bidding process as necessary | GPF |  | Likely to be funds decommitted from a previously awarded project which can be included in Call 13 after year end 18/19. Pipeline of projects waiting to apply when call becomes live. | B - Moderate | 1 - Rare | Low |  | 2019-04-04 | Open
4
5
6
7
8
9
13
14
15
16
17
18
19

## Skills
Title: | SSLEP Skills Contract Management Risk Register | [18 empty] | SSLEP Use
Updated: | March 2019
Identification | [11 empty] | Respond and Monitor | [7 empty] | Updates
Risk ID | Date identified | Identified by | Risk area | Risk Statement | Risk category | Risk owner | Controls | Current/net impact score | Current/net likelihood score | Current/net risk level | Current/net value of risk | Risk actions (mitigations) | Action owner | Expected Completion date | Action progress | Target impact score | Target likelihood score | Target risk level | Target value of risk | Date updated | Risk status
1 | 2018-05-24 | ESEG | Advanced Manufacturing Mechanical & Electrical Centres | The provider may not achieve its targets | LGF capital re. the Skills Equipment Fund round 1 | NSCG | monthly project review in place to March 19 followed by quarterly reviews, project reviewed at monthly S&E management meetings | B - Moderate | 2 - Unlikely | Low |  | agree any remedial actions with the provider following review | David Poole | 2019-12-31 | All equipment in place, awaiting details of the project launch from the college. | B - Moderate | 2 - Unlikely | Low |  | 05.Apr.2019 | Open
2 | 2018-06-12 | ESEG | Embedding Technical Capabilities Project | The provider may not achieve its targets | LGF capital re. the Skills Equipment Fund round 1 | Staffordshire University | monthly project review in place to March 19 followed by quarterly reviews, project reviewed at monthly S&E management meetings | B - Moderate | 2 - Unlikely | Low |  | agree any remedial actions with the provider following review | David Poole | 2019-12-31 | All equipment in place bar a few small items. Awaiting details of the project launch from the university. | B - Moderate | 2 - Unlikely | Low |  | 05.Apr.2019 | Open
3 | 2018-06-28 | ESEG | Technical & Curriculum Development Project | The provider may not achieve its targets | LGF capital re. the Skills Equipment Fund round 1 | Stoke-on-Trent College | monthly project review in place to March 19 followed by quarterly reviews, project reviewed at monthly S&E management meetings | B - Moderate | 2 - Unlikely | Low |  | agree any remedial actions with the provider following review | David Poole | 2019-12-31 | All equipment in place. Awaiting details of the project launch by the college. | B - Moderate | 2 - Unlikely | Low |  | 05.Apr.2019 | Open
4 | 2018-08-15 | ESEG | Manufacturing Excellence Centre | The provider may not achieve its targets | LGF capital re. the Skills Equipment Fund round 1 | Perkins Engines Stafford | monthly project review in place to March 19 followed by quarterly reviews, project reviewed at monthly S&E management meetings | B - Moderate | 2 - Unlikely | Low |  | agree any remedial actions with the provider following review | David Poole | 2019-12-31 | All equipment in place, additional match secured. Awaiting details of project launch. | B - Moderate | 2 - Unlikely | Low |  | 05.Apr.2019 | Open
5 | 2018-12-13 | ESEG | The Cannock Engineering Academy | The provider may not achieve its targets | LGF capital re. the Skills Equipment Fund round 2 | South Staffordshire College | monthly project review in place to March 19 followed by quarterly reviews, project reviewed at monthly S&E management meetings | B - Moderate | 2 - Unlikely | Low |  | agree any remedial actions with the provider following review | David Poole | 2020-09-30 | Delays with order deliveries has resulted in £200k LGF slipping in first quarter 19/20. All equipment is scheduled to be recived by the end of April 19, claim early May. | B - Moderate | 2 - Unlikely | Low |  | 05.Apr.2019 | Open
6 | 2018-11-13 | ESEG | The Hybrid Construction Technology Project | The provider may not achieve its targets | LGF capital re. the Skills Equipment Fund round 2 | NSCG | monthly project review in place to March 19 followed by quarterly reviews, project reviewed at monthly S&E management meetings | B - Moderate | 2 - Unlikely | Low |  | agree any remedial actions with the provider following review | David Poole | 2020-09-30 | All equipment in place. Awaiting details of the project launch by the college. | B - Moderate | 2 - Unlikely | Low |  | 05.Apr.2019 | Open
7 | 2018-12-04 | ESEG | The Academy of Technology & Digital Skills | The provider may not achieve its targets | LGF capital re. the Skills Equipment Fund round 2 | Stoke-on-Trent College | monthly project review in place to March 19 followed by quarterly reviews, project reviewed at monthly S&E management meetings | B - Moderate | 2 - Unlikely | Low |  | agree any remedial actions with the provider following review | David Poole | 2020-09-30 | £183k LGF grant has been moved into the first quarter of 19/20 due to extended time necessary for the procurement of the virtalis 3d equipment. | B - Moderate | 2 - Unlikely | Low |  | 05.Apr.2019 | Open
8
9
13
14
15
16
17
18
19

## Funding Group
Title: | SSLEP Funding Group Risk Register | [18 empty] | SSLEP Use
Updated: | March 2019
Identification | [11 empty] | Respond and Monitor | [7 empty] | Updates
Risk ID | Date identified | Identified by | Risk area | Risk Statement | Risk category | Risk owner | Controls | Current/net impact score | Current/net likelihood score | Current/net risk level | Current/net value of risk | Risk actions (mitigations) | Action owner | Expected Completion date | Action progress | Target impact score | Target likelihood score | Target risk level | Target value of risk | Date updated | Risk status
1 | 2018-06-12 | LEP Funding Group | Financial | Failure to spend the allocated 2018/19 budget before the year end. | Economic | LEP Funding Group | LEP Funding Group scheduled to meet monthly to review all activities |  |  |  |  | Some projects require CF such as Mgt and Admin to cover LEP staff payment, and Careers Co that runs by school calendar not the financial year. | Chris McCann | Complete | Reviewed at monthly Funding Group January A&F Group consider this risk to be "In Control", allocatioon will not be spent, however, funding can be rolled over, without risk. No longer risk as now clawback on funding. |  |  |  |  | 2019-03-13 | Closed
7 | 2018-08-21 | LEP Funding Group | Governance | Uncertainty of LEP Review and ability to allocate funds going forward. | Political | LEP Funding Group | LEP Funding Group scheduled to meet monthly to review all activities |  |  |  |  | To get further guidance from HM Government. | Jacqui Casey | 2019-03-31 | Awaiting outcome of LEP Review geography Position to be reviewed at April Funding Group |  |  |  |  | 2019-04-11 | Closed
2 | 2018-06-12 | LEP Funding Group | Financial | The risk of allocating funding to projects that are not in line with LEP priorities. | Economic | LEP Funding Group | LEP Funding Group scheduled to meet monthly to review all activities | B - Moderate | 2 - Unlikely | Low |  | The mitigation is that we will review applications at the LFMG, Strategic Group and Executive Board. | Jacqui Casey | Ongoing | Reviewed at monthly Funding Group | A - Minor | 2 - Unlikely | Low |  | 2019-03-13 | Open
3 | 2018-06-12 | LEP Funding Group | Financial | The risk of allocating £25,000 to the Careers Co for 2018/19 and they will not spend the allocation having carried forward £11,415.31 from 2017/18. | Economic | LEP Funding Group | LEP Funding Group scheduled to meet monthly to review all activities | C - Major | 2 - Unlikely | Medium |  | The Careers Co carry over relates to original commencement of claims over the academic year straggling our financial year. | Jacqui Casey | Ongoing | £11,413 has now been utilised + £6,000 of new allocation | B - Moderate | 2 - Unlikely | Low |  | 2019-03-13 | Open
4 | 2018-06-12 | LEP Funding Group | Financial | Concerns that the Core funds are funding 2 year projects without the certainty that we have future funding. | Economic | LEP Funding Group | LEP Funding Group scheduled to meet monthly to review all activities | B - Moderate | 2 - Unlikely | Low |  | That we state in the funding agreements, that future years' funds will be subject to the LEP receiving Core funds A new funding agreement would need to be raised for 2nd year funding | John Broad | Ongoing | Reviewed at monthly Funding Group | B - Moderate | 2 - Unlikely | Low |  | 2019-03-13 | Open
5 | 12//6/2018 | LEP Funding Group | Governance | Ensure governance is in place and applicants confirm via funding request form. | Legal | LEP Funding Group | LEP Funding Group scheduled to meet monthly to review all activities | C - Major | 3 - Possible | Medium |  | Form updated. Process to be updated to include checks and report back to Funding Group | Jacqui Casey | Ongoing | Amended form in use | A - Minor | 3 - Possible | Low |  | 2019-03-13 | Open
6 | 2018-06-12 | LEP Funding Group | Governance | Making allocations prior to business case approvals e.g. Industrial Strategy, ME DIT Challenge Fund. | Legal | LEP Funding Group | LEP Funding Group scheduled to meet monthly to review all activities | C - Major | 3 - Possible | Medium |  | Prompt submission of forms To be brought to immediate attention of the Funding Group | Jacqui Casey | Ongoing | Instances raised and questioned at Funding Group, to reduce possibility of reoccurrence | A - Minor | 2 - Unlikely | Low |  | 2019-03-13 | Open
8 | 2019-02-06 | LEP Funding Group | Governance | Lack of cash limiting ability to fund pipeline projects | Economic | LEP Funding Group | LEP Funding Group scheduled to meet monthly to review | C - Major | 4 - Likely | Medium |  | Dependancy on the LEP Review for availability of future funding | Jacqui Casey | Ongoing | To be monitored and discussed at April funding meeting | B - Moderate | 2 - Unlikely | Low |  | 2019-03-13 | Open
9
13
14
15
16
17
18
19

## ESIF
Title: | ESIF Risk Register | [18 empty] | SSLEP Use
Updated: | March 2019
Identification | [11 empty] | Respond and Monitor | [7 empty] | Updates
Risk ID | Date identified | Identified by | Risk area | Risk Statement | Risk category | Risk owner | Controls | Current/net impact score | Current/net likelihood score | Current/net risk level | Current/net value of risk | Risk actions (mitigations) | Action owner | Expected Completion date | Action progress | Target impact score | Target likelihood score | Target risk level | Target value of risk | Date updated | Risk status
1 | 2019-01-31 | Nigel Senior | Financial | There is a risk of not reaching full commitment of ERDF by the Spring ERDF call. Currently we have about £17.9m still to commit and whilst we know where most of this could go bids still have to be submitted by partners and progressed through the ERDF gateway assessment. Any residual allocation left after this call will be returned to DCLG for a nation-wide call and lost to addressing local priorities. | Economic | Nigel Senior | Regular review at ESIF sub-committee | C - Major | 3 - Possible | Medium |  | Given the emergence of key projects at Keele, i54 and Spode the bids have to be ready for the last call expected in May/June 2019 | Nigel Senior | 2019-06-30 | Outline bids received for Keele, i54 and Spode | B - Moderate | 2 - Unlikely | Low |  | 04.04.19 | Open
2 | 2019-01-31 | Nigel Senior | Financial | There is a risk of not reaching full commitment of remaining ESF allocation due to the LEP not being invited forward for a secind phase of the DWP Opt in co-financing programme. | Economic | Nigel Senior | Regular review at ESIF sub-committee | C - Major | 3 - Possible | Medium |  | Approximately £21.2 m depends on extensions being agreed with ESFA & Big Lottery Opt In programmes As there is no second phase of DWP more resource can be put into Big Lottery and ESFA along with a range of local open call projects | Nigel Senior | 2019-06-30 | Outside of the Opt Ins, the SSLEP ESIF Committee has been asked to inform DWP about priorities for a final (Summer 2019) Open Call for bids | B - Moderate | 2 - Unlikely | Low |  | 04.04.19 | Open
3 | 2019-04-04 | Nigel Senior | Financial | There is a risk regarding funding profile of projects and the programme as a whole as partners encounter challenges in delivering their projects and have to make adjustments. | Economic | Nigel Senior | Regular review at ESIF sub-committee | B - Moderate | 3 - Possible | Medium |  | Monitor. The mid programme stage spend target at December 2018 has been achieved. | Nigel Senior |  | Continue to monitor | B - Moderate | 3 - Possible | Medium |  | 04.04.19 | Open
4
5

## Blank (hidden)
Title: | SSLEP Blank Risk Register | [18 empty] | SSLEP Use
Updated: | November 2018
Identification | [11 empty] | Respond and Monitor | [7 empty] | Updates
Risk ID | Date identified | Identified by | Risk area | Risk Statement | Risk category | Risk owner | Controls | Current/net impact score | Current/net likelihood score | Current/net risk level | Current/net value of risk | Risk actions (mitigations) | Action owner | Expected Completion date | Action progress | Target impact score | Target likelihood score | Target risk level | Target value of risk | Date updated | Risk status
1
2
3
4
5
6
7
8
9
13
14
15
16
17
18
19

## Risk Matrix
Risk Matrix |  |  | <----------------------------------- IMPACT ------------------------------------->
| A - Minor | B - Moderate | C - Major | D - Critical | E - Catastrophic
5 - Almost certain | Low | Medium | High | High | High
4 - Likely | Low | Medium | Medium | High | High
3 - Possible | Low | Medium | Medium | High | High
2 - Unlikely | Low | Low | Medium | Medium | High
1 - Rare | Low | Low | Low | Medium | Medium

## Risk Analysis (hidden)
| Red | Amber | Green | Total
Strategic | 3 | 3 | 0 | 6 |  |  |  |  | Red
CDGD | 3 | 13 | 1 | 17 |  |  |  |  | Amber
GPF | 0 | 2 | 1 | 3 |  |  |  |  | Green
Skills | 0 | 0 | 7 | 7
Funding Group | 0 | 4 | 2 | 6
ESIF | 0 | 3 | 0 | 3
SSLEP | 6 | 25 | 11 | 42
[6 empty] | 2019-01-01 | 2019-02-01 | 2019-03-01
[5 empty] | Red | 6 | 6 | 6
[5 empty] | Amber | 19 | 22 | 25
[5 empty] | Green | 12 | 12 | 11