## Change (hidden)
CHILDREN AND FAMILIES SERVICES
Revenue Outturn 2010/11 |  | Overspend
£000
| Period 07 Forecast | -147
| Period 09 Forecast | #REF!
| Decrease in Underspend | #REF!
Explanation of Decrease
| DCD | 0
| SAFEGUARDING | 194
| INCLUSION | -55
| TARGETED | -32
107

## 2018-19 Dashboard FINAL OUTTURN
Q4 2018/19 PROVISIONAL OUTTURN - Key Stoke on Trent & Staffordshire Local Enterprise Partnership Funding Streams Headline Summary
|  | In Delivery | Scheme Completed | Contracting
General Commentary
LGD - At Q4, £9.837m (73%) of total LGF Grant has to date been spent of the total £13.444m LGF funding available in 2018/19. Of this year's LGF Grant funding, circa £3.606m (an increase of £1.146m on Q3) is now estimated as grant slippage which is likely to be 'switch funded'
against SCC's Capital Prog'. The £2.86m LGF Grant balance from the recent withdrawal of funding from certain LGD2 Rnd schemes has been reassigned to 4 new projects from the LEP's updated project pipeline. These 4 Grant Funding Agreements are to be finalised in early 19/20.
LGF Grant - Total Local Growth Deal (LGD) funding is £98.275m. Of this sum, £76.56m (77.9%) has now cumulatively been spent up to and including 18/19, leaving a balance of £21.715m (22.1%) in LGD funding yet to be invested by 2020/21 against approved schemes.
City Deal & Growth Hub Grant - At Q4, £4.013m or 90% of the £4.445m City Deal reprofiled spend has been spent to date. The Keele SEND scheme has spent to its quarterly profile whilst the DHN has claimed £2.388m of its total planned 2018/19 City Deal spend
with funding slippage of £0.432m now carried forward into future years. The Growth Hub Unit has now claimed and banked its 4th and final quarterly claim to give a total of £0.205m in grant allocation.
ESIF – ERDF & ESF committed funding stands at £116m or 75% of allocation. FOREX exchange rate adjustment has provided a further £12.5m ERDF. The total ERDF allocation now stands at £90.9m. The last call yielded 4 bids totalling £11m in grant request leaving almost £18m
to be allocated in the final bidding call in Summer 2019. ERDF claimed to date now stands at almost £35m against the N+3 target of £38.6m (as @ Dec 18). For ESF an expression of interest for a 2nd phase ESFA Opt In for 2 years from April 19 & 2nd Phase ESF Opt In for BWP & Big
Lottery is expected to soon follow. Contracting of ESF Open Call for Skills Hub & Higher Skills Progs is progressing and a second call is planned for Summer 2019. Together this will result in the full commitment of ESF funding (£64.3m)
GPF - Approved commitments = £14.2m (11 loans & 3 grants). The GPF cashflow currently holds a balance of £0.474m for future loans following the recent Open Call. 1 new Stage 1 GPF loan application has now been recently approved by Panel and is now progressing to contract.
Core & Capacity Grant - At Q4, total planned spend commitments equate to the total grant allocation of £0.613m including the £113k 2017/18 grant carry forward. To date, £0.470m or 75% of grant funding has now been spent and a carry forward sum is expected at year end.
2015/16 Revenue Grant Funding = £250,000 +£3,050 c/fwd from 2014/15 Grant

## DCD (hidden)
Families First Services - General | [7 empty] | 2014/2015
Responsible Officer | Service Area | Node/Cost Centre | Gross Budget | Net Budget | Projected | Variance | Comments |  | PSLT
[5 empty] | Outturn | Over/(Under) |  |  | Commissioner
|  |  | £000 | £000 | £000 | £000
Richard Hancock | Improving Practice / Families First | SC4910 | 946 | 920 | 567 | -353 | Assumes that all Families First 2014/15 redundancy and actuarial strain expenditure will be funded through loans taken over the next 5 financial years |  | Care
Richard Hancock | Care Works | SC4920 | 500 | 500 | 500 | 0 | Assumes all Care Director capital financing of £500k is fully spent |  | Care
Total | Families First Services - General | SC-DCD | 1446 | 1420 | 1067 | -353
|  | Care | 1446 | 1420 | 1067 | -353
|  | Care (AAD) | 0 | 0 | 0 | 0
|  | Learning & Skills | 0 | 0 | 0 | 0
|  | Safety | 0 | 0 | 0 | 0

## SAFE (hidden)
Specialist Safeguarding Delivery | [7 empty] | 2014/2015
Responsible Officer | Service Area | Node/Cost Centre | Gross Budget | Net Budget | Projected | Variance | Comments |  | PSLT
[5 empty] | Outturn | Over/(Under) |  |  | Commissioner
|  |  | £000 | £000 | £000 | £000
Clive Cartman-Frost | Responsive Services (First Response, EDS, Risk Management) | SC-RESPO | 2443 | 2190 | 2231 | 41 | Overspend on staffing within the EDS team |  | Care
Tony McGregor | Safeguarding Units - East | EASTSUS | 4150 | 4150 | 4648 | 498 | Overspend against staffing and home to school transport Glascote and Rawlett SU team are projected to overspend by £315k |  | Care
Colleen Male | Safeguarding Units - Mid | MIDSUS | 3897 | 3897 | 3792 | -105 | Underspend against Section 17 and transport budgets partially offset by overspends on staffing |  | Care
Teresa Murray | Safeguarding Units - North (includes Family Group Conferencing, CAMHS and SW's in YOI's) | NORTSUS | 2710 | 2622 | 2532 | -90 | Projected underspend against Section 17 budgets |  | Care
Total | Specialist Safeguarding Delivery | FF-SAFE | 13200 | 12859 | 13203 | 344
|  | Care | 13200 | 12859 | 13203 | 344
|  | Care (AAD) | 0 | 0 | 0 | 0
|  | Learning & Skills | 0 | 0 | 0 | 0
|  | Safety | 0 | 0 | 0 | 0

## LAC (hidden)
Looked After Children and Disability | [7 empty] | 2014/2015
Responsible Officer | Service Area | Node/Cost Centre | Gross Budget | Net Budget | Projected | Variance | Comments |  | PSLT
[5 empty] | Outturn | Over/(Under) |  |  | Commissioner
|  |  | £000 | £000 | £000 | £000
Marian Richards | Case Management - East Court and Care Planning Teams | SC-CASEE | 2362 | 2362 | 2247 | -115 | Projected underspend against staffing and S17 budgets |  | Care
Jacqui Sims | Case Management - West Court and Care Planning Teams | SC-CASEW | 2097 | 2097 | 2215 | 118 | Projected overspend against staffing |  | Care
Nic Hull | Case Management - Through Care (including Leaving Care Central team) | SC-CASETC (Excl. SC3150 GL49331) | 3387 | 3387 | 3454 | 67 | Overspend against staffing parially offset through MTFS NSPCC funding of £100k which will not be utilised in 2014/15 |  | Care
Deborah Ramsdale | Families First Legal Assessments | SC3150 GL 49331 | 528 | 528 | 528 | 0 |  |  | Care
Liz Kelay | Provider Services - Central | SC-PROVC | 579 | 579 | 564 | -15 | Underspend against Supported Lodgings allowances budget |  | Care
Liz Kelay | Independent Sector Placements | SC-INDSEC | 16893 | 16893 | 20053 | 3160 | Placement Unit's current projected outturn forecast as at 31st December 2014 - 394 Independent Sector Placements |  | Care
Liz Kelay / Nic Hull | Social Work Practice | SC-SWP | 3989 | 3985 | 4062 | 77 | Placement Unit's current projected outturn forecast as at 31st December 2014 - 394 Independent Sector Placements |  | Care
Liz Kelay | Asylum Seekers | SC3510 | 631 | 220 | 174 | -46 |  |  | Care
Scott Crawford | Fostering Services | SC-PROVFST | 14601 | 13512 | 13883 | 371 | Overspend on carers allowances as well as adaptation/car grants given to carers. Includes all Staying Put additional expenditure which has partially been offset through DfE grant funding. Includes £70k of funding from YOS in respect of the MTFS Recovery Plan |  | Care
Scott Crawford | Adoption Services | SC-PROVADO | 3475 | 2656 | 2057 | -599 | Increase in level of external inter-agency placement fee income received. Includes £320k of funding from ARG in respect of the MTFS Recovery Plan |  | Care
Scott Crawford | Business Unit | SC0610 | 588 | 588 | 570 | -18 |  |  | Care
Liz Kelay | Residential Mainstream | SC-RESMAIN | 2899 | 1981 | 1848 | -133 | Underspend against employees budget within Shaping Futures and The Alders |  | Care
Nic Hull | Sustain | SC-SUSTAIN | 519 | 519 | 519 | 0 |  |  | Care
Liz Kelay | Aiming High Grant | SC0900 | 804 | 804 | 804 | 0 | Projected to be fully spent as per Amy Evans at meeting held on 22nd July 2014 |  | Care (AAD)
Liz Kelay | Family Support / Respite Care / Family Link | SC-PROFAM | 1235 | 1235 | 1230 | -5 | Underspend against staffing |  | Care (AAD)
Liz Kelay | Residential Disability | SC-RESDIS | 1987 | 1907 | 1808 | -99 | Underspend due to increased levels of traded income anticipated to be received |  | Care (AAD)
Liz Kelay | Intensive Prevention Service | SC4981 | 584 | 584 | 509 | -75 | Underspend against staffing and commissioning budgets |  | Safety
Sarah Rivers | Virtual School | LP7011 | 458 | 0 | -116 | -116 | Underspend against staffing and PEA allowances |  | Learning & Skills
Julia Anderson | Specialist Support Services | LP-SSS | 5722 | 0 | -59 | -59 | Underspend against staffing |  | Care
Total | Looked After Children and Disability | AE-LAC | 63338 | 53837 | 56350 | 2513
|  | Care | 58270 | 49307 | 52115 | 2808
|  | Care (AAD) | 4026 | 3946 | 3842 | -104
|  | Learning & Skills | 458 | 0 | -116 | -116
|  | Safety | 584 | 584 | 509 | -75
Note on F15: apalm1ss: Shahid's projected outturn report less In House Fostering recharge underspend plus Leaving Care UASC overspend
Note on F16: apalm1ss: Cheryl's expenditure spreadsheet @ 31st October 2014 less UASC income less Leaving Care income plus 2013/14 overclaimed income

## TARGET (hidden)
Targeted Services | [7 empty] | 2014/2015
Responsible Officer | Service Area | Node/Cost Centre | Gross Budget | Net Budget | Projected | Variance | Comments |  | PSLT
[5 empty] | Outturn | Over/(Under) |  |  | Commissioner
|  |  | £000 | £000 | £000 | £000
Karl Hobson | Local Support Teams - East | EASTLSTS | 4729 | 3077 | 2914 | -163 | Underspend against employees and transport. Operational and commissioning budgets are taken from discussions in the extraordinary District Leads meeting |  | Safety
Dave Bates | Local Support Teams - West | WESTLSTS | 4601 | 2965 | 2816 | -149 | Underspends against supplies and services budgets as well as on transport. Operational and commissioning budgets are taken from discussions in the extraordinary District Leads meeting |  | Safety
Sue Coleman | Targeted Services - General | SC4980 | 181 | 47 | 28 | -19 |  |  | Safety
Julia Anderson | Psychologists | LP5007 / LP5017 | 1820 | 0 | -15 | -15 |  |  | Care
Barbara Elks | Youth Offending Service | SYOS | 3553 | 1657 | 1657 | 0 |  |  | Safety
Sue Coleman | Main Children Centres | EN-CCS | 2152 | 2082 | 1861 | -221 | Additional pension contribution following transfer of childcare to market not now required. |  | Safety
Sharon Moore | Early Years Central Costs | AE-CENT | 858 | 0 | 0 | 0 |  |  | Safety
Total | Targeted Services | AE-TARGT | 17894 | 9828 | 9261 | -567
|  | Care | 1820 | 0 | -15 | -15
|  | Care (AAD) | 0 | 0 | 0 | 0
|  | Learning & Skills | 0 | 0 | 0 | 0
|  | Safety | 16074 | 9828 | 9276 | -552

## P&D (hidden)
Partnership and Development | [7 empty] | 2014/2015
Responsible Officer | Service Area | Node/Cost Centre | Gross Budget | Net Budget | Projected | Variance | Comments |  | PSLT
[5 empty] | Outturn | Over/(Under) |  |  | Commissioner
|  |  | £000 | £000 | £000 | £000
Sarah Piggott | Business Improvement and Development Service | SC4760 | 681 | 484 | 438 | -46 | Underspend against staffing |  | Care
Sarah Piggott | Community Engagement and Service Delivery | SC7610 | 252 | 252 | 262 | 10 | Overspend against transport |  | Care
John Maddox | Families First Service Development | SC7500 | 308 | 308 | 220 | -88 | Underspend against staffing due to vacant County Managers post |  | Care
Steve Lycett | Support Services | SC-SUPPORT | 0 | 0 | -177 | -177 | Underspend against staffing as a result of vacant posts as well as supplies and services budgets. All SC-SUPPORT budgets re-charged to operational services totalling £6.2m |  | Care
Kate Sharratt | Workforce Development | SC-TRAIN | 1446 | 403 | 403 | 0 | Projected to be fully spent as per Kate Sharratt at meeting held on 15th October 2014. MTFS efficiency savings of £175k will be fully achieved |  | Care
Total | Partnership and Development | FF-PARTNER | 2687 | 1447 | 1146 | -301
|  | Care | 2687 | 1447 | 1146 | -301
|  | Care (AAD) | 0 | 0 | 0 | 0
|  | Learning & Skills | 0 | 0 | 0 | 0
|  | Safety | 0 | 0 | 0 | 0

## PSLT Commissioner (hidden)
Families First Services - Period 9 Forecast | [7 empty] | 2014/2015
Responsible Officer | Service Area | Node/Cost Centre | Gross Budget | Net Budget | Projected | Variance | Comments
[5 empty] | Outturn | Over/(Under)
|  |  | £000 | £000 | £000 | £000
Martin Samuels | Children in Need of Care and Support |  | 77423 | 65033 | 67516 | 2483
Martin Samuels | All Age Disability |  | 4026 | 3946 | 3842 | -104
Anna Halliday | Learning and Skills |  | 458 | 0 | -116 | -116
Mick Harrison | Safety |  | 16658 | 10412 | 9785 | -627
Total | PSLT Commissioners |  | 98565 | 79391 | 81027 | 1636

## CINCARE (hidden)
Children In Need of Care and Support - Period 9 Forecast | [7 empty] | 2014/2015
Responsible Officer | Service Area | Node/Cost Centre | Gross Budget | Net Budget | Projected | Variance | Comments |  | PSLT
[5 empty] | Outturn | Over/(Under) |  |  | Commissioner
|  |  | £000 | £000 | £000 | £000
Denise Tolson | Commissioning for Children's Care and Support | SC9100 | 432 | 432 | 413 | -19 |  |  | Care
Denise Tolson | CAMHS Grant | SC0440 | 459 | 459 | 447 | -12 |  |  | Care
Total | Children in Need of Care and Support | CINCARE | 891 | 891 | 860 | -31
|  | Care | 891 | 891 | 860 | -31
|  | Care (AAD) | 0 | 0 | 0 | 0
|  | Learning & Skills | 0 | 0 | 0 | 0
|  | Safety | 0 | 0 | 0 | 0

## LP8000 (hidden)
EDU Commissioning - Period 9 Forecast | [7 empty] | 2014/2015
Responsible Officer | Service Area | Node/Cost Centre | Gross Budget | Net Budget | Projected | Variance | Comments |  | PSLT
[5 empty] | Outturn | Over/(Under) |  |  | Commissioner
|  |  | £000 | £000 | £000 | £000
Anna Halliday | EDU Commissioning | LP8000 | 1429 | 204 | 388 | 184 | Redundancy costs |  | Learning and Skills
Total | EDU Commissioning |  | 1429 | 204 | 388 | 184
|  | Care | 0 | 0 | 0 | 0
|  | Care (AAD) | 0 | 0 | 0 | 0
|  | Learning & Skills | 0 | 0 | 0 | 0
|  | Safety | 0 | 0 | 0 | 0

## Underlying Uspend (hidden)
Vulnerable Children 2007/8
Underlying Underspend (Excluding ISP)
Underspend
£000
| Latest forecast Outturn 2007/8 |  | #REF!
| Add back forecast overspend on ISP |  | 1164
Add back one-off expenditure included in forecast
|  | Pisces project contribution | 150
|  | Secure Unit Deficit | 420
General contribution to budget from
|  | Secure Unit reserve not being made | 278
Deduct one-off income included in forecast
|  | Asylum Seekers Grant previous year | -208
| Underlying Underspend on VC excluding ISP |  | #REF!

## CDH - Jo McCloy (hidden)
Commissioning Delivery Hub - Period 9 Forecast | [7 empty] | 2014/2015
Responsible Officer | Service Area | Node/Cost Centre | Gross Budget | Net Budget | Projected | Variance | Comments |  | PSLT
[5 empty] | Outturn | Over/(Under) |  |  | Commissioner
|  |  | £000 | £000 | £000 | £000
Anne Strowger / Caroline Dunn | Case Conference Chairs | SC1050 | 1054 | 1054 | 1145 | 91 | Overspend against staffing as a result of the recruitment of agency staff and the planned recruitment of a further 4 IRO's prior to April 2015. |  | Business Improvement
Nicola Gibson | PSR Team | SC3409 | 236 | 236 | 158 | -78 | Underspend against staffing due to vacant posts |  | Business Improvement
Total | Commissioning Delivery Hub |  | 1290 | 1290 | 1303 | 13
|  | Care | 0 | 0 | 0 | 0
|  | Care (AAD) | 0 | 0 | 0 | 0
|  | Learning & Skills | 0 | 0 | 0 | 0
|  | Safety | 0 | 0 | 0 | 0

## SAFETY - Simon Ablewhite (hidden)
Safety - Period 9 Forecast | [7 empty] | 2014/2015
Responsible Officer | Service Area | Node/Cost Centre | Gross Budget | Net Budget | Projected | Variance | Comments |  | PSLT
[5 empty] | Outturn | Over/(Under) |  |  | Commissioner
|  |  | £000 | £000 | £000 | £000
Paul Woodcock | Commissioning for Children's Wellbeing | SC9200 | 504 | 504 | 490 | -14 |  |  | Safety
Sharon Moore | Early Years Training | EN-TRAIN | 1030 | 737 | 545 | -192 | Revised PVI training projections |  | Safety
Total | Safety |  | 1534 | 1241 | 1035 | -206
|  | Care | 0 | 0 | 0 | 0
|  | Care (AAD) | 0 | 0 | 0 | 0
|  | Learning & Skills | 0 | 0 | 0 | 0
|  | Safety | 1534 | 1241 | 1035 | -206

## Revenue data - DO NOT PRINT
2018/19 LEP Quarterly Outturn Report - Budget Profiles & Final Net Revenue Outturn | [6 empty] | 2018/19 Q4 REVENUE OUTTURN (as @ 31/03/2019)
| SoT DHN budget | SoT DHN Spend | Keele SEN Budget | Keele SEN Spend | Growth Hub Budget | Growth Hub Spend
Q1 | 67 | 2383.2711 | 45 | 41.4 | 62.75 | 0
Q2 | 98 |  | 45 |  | 65.25
Q3 | 280 |  | 100 |  | 63.25
Q4 | 700 |  | 100 |  | 57.75
| 1145 |  | 290 |  | 249
City Deal |  | Quarter 4 | Quarter 4 | Quarter 4
| Budget | Spend to Date | Forecast | Variance | %
Total | 4445 | 4013.2711 | 431.7289 | 431.7289 | 90.29% | 0
SOT DHN | 2815 | 2383.2711 | 431.7289 | 431.7289 | 84.66% | 0
Keele SEND | 1425 | 1425 | 0 | 0 | 100% | 0
Growth Hub | 205 | 205 | 0 | 0 | 100% | 0
Local Growth Deal 1 Schemes
| Etruria Valley Budget | Etruria Valley Spend | Lichfield BP Budget | Lichfield BP Spend | Branston Locks Budget | Branston Locks Spend | Meaford Budget | Meaford Spend | Bericote Budget | Bericote Spend | SWAR Budget | SWAR Spend
Q1 | 480 | 15213.5547 | 1850 | 845.6 | 40.5 | 0 | 354.187 | 102.1 | 951.905 | 0.962 | 280 | 38.6
Q2 | 1230 |  | 622 |  | 49.25 |  | 1773.138 |  | 962.033 |  | 280
Q3 | 1300 |  |  |  | 89.25 |  | 1451.407 |  | 1093.783 |  | 1602
Q4 | 1350 |  |  |  | 130.06 |  | 1194 |  | 984.792 |  | 5222
| 4360 |  | 2472 |  | 309.06 |  | 4772.732 |  | 3992.513 |  | 7384
Checks | 1456.337 |  | 3267.552 |  | 469.8723 |  | 4466.647 |  | 1233.702 |  | 1478.2068
Local Growth Funding - LGD 1, 2 & 3 |  |  | Quarter 4 | Quarter 4 | Forecast
|  | Budget | Spend to Date | Commitments | Spend
13444 | LGF Grant 18/19 | £'m | £'m | £'m | £'m | % Spent
FUNDING COMPLETED 1 | Stafford Western Access | 3180 | 3180 | 0 | 3180 | 100%
2 | Tamworth Enterprise Quarter | 1625 | 1511 | 114 | 1625 | 92.98%
SCHEME DEFERRED TO 2019/20 3 | City East Link Road | 0 | 0 | 0 | 0 | SCHEME DEFERRED
4 | City Centre Access | 1258 | 881 | 377 | 1258 | 70.03%
FUNDING COMPLETED 5 | Doxey Rd & SWAR | 1784 | 1784 | 0 | 1784 | 100%
SCHEME DEFERRED TO 2019/20 6 | Spode Incubator Space | 0 | 0 | 0 | 0 | SCHEME DEFERRED
FUNDING COMPLETED 7 | Keele Smart Innovation Hub | 490 | 490 | 0 | 490 | 100%
SCHEME DEFERRED TO 2019/20 8 | LSPT (SoTCC) | 0 | 0 | 0 | 0 | #DIV/0!
9 | Skills Capital Equipment Fund | 2375 | 1992 | 383 | 1975 | 83.87%
| Totals | 10712 | 9838 | 874 | 10312 | 91.84% | 10712
[5 empty] | Actuals % of Grant | 73.18%
Growing Places Fund - Loans Cash Flow Model |  |  | As at 31st March 2019. |  |  | Growth Hub Funding
| Date | £m |  |  |  | As at 31st March 2019. |  |  |  |  | Checks
| 2015-06-01 | 10.2313 | Q1 | 2015/16 |  |  |  | Contracted | Budget
| 2015-09-01 | 10.1347 | Q2 |  |  | Growth Hub | 205 | 205 | 205 | 100%
| 2015-12-01 | 10.1347 | Q3
| 2016-03-01 | 10.0471 | Q4
| 2016-06-01 | 10.0063 | Q1 | 2016/17 |  | As at 31st March 2019. | Actual spend to date | 449673.44 | 74.76%
| 2016-09-01 | 8.7998 | Q2 |  |  | LEP Core Fund 2017/18 |  | Approved | Outturn
| 2016-12-01 | 8.1388 | Q3
| 2017-03-01 | 8.1388 | Q4 |  |  | LEP Office & Delivery Team |  | 257269 | 257269 | 42.77%
| 2017-06-01 | 8.1105 | Q1 | 2017/18 |  | Business Engagement & Support |  | 91872.99 | 91872.99 | 15.27%
| 2017-09-01 | 8.6613 | Q2 |  |  | Strategic Planning |  | 25000 | 25000 | 4.157%
| 2017-12-01 | 8.4413 | Q3 |  |  | Project & Programme Development |  | 217345.8 | 217345.8 | 36.14%
| 2018-03-01 | 3.2779 | Q4 |  |  | Unallocated Funds |  | 9978 | 5930 | 1.659%
| 2018-06-01 | 3.2779 | Q1 | 2018/19 |  | Total |  | 601465.79 | 597417.79 | 100%
| 2018-09-01 | 3.5779 | Q2 |  |  |  | Check Total | 613466
| 2018-10-01 | 3.2461 | Q3 |  |  | ESIF Funding Themes |  | As at 31st March 2019.
| 2019-03-01 | 1.1831 | Q4 |  |  | Round 1 2 & 3 (Dec 2017) - Pipeline Outline Allocations
| 2019-06-01 | 0.84385 | Q1 | 2019/20 |  |  |  | % ERDF Funding | 80.21%
| 2019-09-01 | 1.4907 | Q2 |  |  | Theme | ESIF Comtmts | ESIF Alloc'ns
| 2019-12-01 | 2.1714 | Q3 |  |  | PA1 Innovation | 18.88 | 25.17
| 2020-03-01 | 0.4742 | Q4 |  |  | PA 2 ICT | 0 | 0.48
| 2020-06-01 | 0.4742 | Q1 | 2020/21 |  | PA3 SME | 39.55 | 45.94
| 2020-09-01 | 0.4742 | Q2 |  |  | PA 4 Low Carbon | 12.32 | 15.01
| 2020-12-01 | 0.4742 | Q3 |  |  | PA 5 Climate Change | 0 | 1
| 2021-03-01 | 1.8579 | Q4 |  |  | PA 6 Environment | 2.12 | 3.25
| 2021-06-01 | 1.9329 | Q1 | 2021/22 |  | PA 8&9 Skills, Employt | 43.1309 | 64.3 | 67.0776 | %
| 2021-09-01 | 1.9329 | Q2 |  |  | Total | 116.0009 | 155.15 | 74.77%
| 2021-12-01 | 1.9329 | Q3 |  |  | Budget | 116.0009 | 155.15
| 2022-03-01 | 2.173 | Q4
| 2022-06-01 | 2.173 | Q1 | 2022/23 |  |  |  | As at 31st March 2019.
| 2022-09-01 | 2.173 | Q2 |  |  | Total GPF Approved Schemes Rounds 1-9 Inclusive - Status of Schemes
| 2022-12-01 | 2.173 | Q3 |  |  | Round & Scheme/Project Title | £m |  | No.
| 2022-03-01 | 2.4229 | Q4 |  |  | 1 Etruria Valley (GRANT) | 2.4 | COMPLETED | 1
[6 empty] | 2 DBV 1 | 0.586 | COMPLETED & REPAID | 2
[6 empty] | 3 Leekbrook Ind Est Extn | 0 | WITHDRAWN | 3
[6 empty] | 4 Hellermann Tyton | 0.75 | COMPLETED & REPAID | 4
[6 empty] | 5 Hilton Garden Hotel (GRANT) | 2.96 | COMPLETED | 5
[6 empty] | 6 DBV 2 | 0.73 | ON HOLD | 6
[6 empty] | 7 Lichfield South | 0.89558 | IN PROGRESS | 7
[6 empty] | 8 London House (Phase 2) | 1.0625 | COMPLETED & REPAID | 8
[6 empty] | 9 Omicron Service Centre | 0.4 | COMPLETED | 9
[6 empty] | 10 Oak House Res Home | 0.22 | COMPLETED & REPAID | 10
[6 empty] | 11 London House (Phase 3) | 0.45 | COMPLETED | 11
[6 empty] | 12 Harper St, Middleport Pottery | 0.37 | IN PROGRESS | 12
[6 empty] | 13 Canalside Farm | 0.3 | IN PROGRESS | 13
[6 empty] | 14 Gestamp (GRANT) | 3 | COMPLETED | 14
[6 empty] | Scott FM | 0.075 | IN PROGRESS | 15
[7 empty] | 14.1991 | 14199.0827 | check
|  | Financial Year | LGF Grant | Actual Spend & Forecast
|  | #REF! | 0
LGD1 Funding 2015/16 |  | #REF! | #REF!
| Budget |  | #REF! |  | %
Total | #REF! |  | #REF! |  | 0%
Etruria Valley | #REF! | #REF! | 0 |  | 0%
Lichfield B P | #REF! | #REF! | 0 |  | 0%
Branston Locks | #REF! | #REF! | #REF! |  | 0%
Meaford | 1456.337 |  |  |  | 0%
Bericote | 0 | Lichfield B P | Branston Locks |  | 0%
Stafford Western | #REF! | #REF! | #REF! |  | 0%
0
Funding | Total | #REF! | #REF! |  | Meaford
LGF | #REF! | LGF Grant Allocations 17/18 to 20/21 |  |  | #REF!
Other | #REF! |  |  |  | #REF!
Total | #REF! | Financial Year | Total LGF Grant Funding (£) |  | #REF!
76559434 | LGF Grant Spend to Date | 2015-16 | 14400000 | 12480209.05 | 1919790.95
|  | 2016-17 | 33356869 | 24216408.83 | 9140460.17
77.9% |  | 2017-18 | 17518643 | 8725182 | 8793461
|  | 2018-19 | 11283922 | 9838000 | 1445922
21715507 |  | 2019-20 | 6370448 | 6370448 | 0 | Est
|  | 2020-21 | 15345059 | 15345059 | 0 | Est
|  | TOTAL LGF Grant | 98274941 | 76975306.88 | 21299634.12
|  | Grant & Spend 2 Date | 76559434 | 55259799.88 | 21299634.12
|  | Estimated LGF Grant Slippage to Date |  | 21299634.12
|  |  | LGF Grant STD | 77.9%
56.23%
Note on H68: Broad, John (People): Includes £10m 'Fund of Funds' commitment with West Mids.

## LGF Phase 1, 2 & 3
Chart 1: Local Growth Deals - LGD 1, 2 & 3 |  |  |  | As @ | 2018/19 Q4 REVENUE OUTTURN (as @ 31/03/2019)
Lichfield Business Park (CDX8604) Phase 1 & 2 |  |  | SCHEME COMPLETED |  | Responsible Officer - |  |  | Steve Knott |  | As per Q2 Reported | LGF Q2 Funding Check
| 2013/14 | 2014/15 | 2015/16 | 2016/17 | 2017/18 | 2018/19 | 2019/20 | Total
Actual | 49544.37 | 1616929.73 | 3267552 | 454047.21 | 31437.81 |  |  | 5419511.12
Forecast | [7 empty] | 0
Total Expenditure | 49544.37 | 1616929.73 | 3267552 | 454047.21 | 31437.81 | 0 | 0 | 5419511.12
FUNDING SURPLUS | [7 empty] | 0
LGF Fund |  | 1307641.13 | 2692358.87 |  |  |  |  | 4000000 | OK |  | 4000000
SCC Funding | 49544.37 | 269288.6 | [5 empty] | 318832.97
LEP Funding |  | 40000 | [5 empty] | 40000
Developer Funding |  |  | 575193.13 | 454047.21 | 31437.81 |  |  | 1060678.15
Total Funding | 49544.37 | 1616929.73 | 3267552 | 454047.21 | 31437.81 | 0 | 0 | 5419511.12 | OK | 5406026.1
Spend to Date | 49544.37 | 1616929.73 | 3267552 | 454047.21 | 31437.81 | 0 | 0 | 5419511.12
Branston Locks Burton (CDX8605; CDX8620 & DCDX8621) |  |  |  |  | Responsible Officer - |  |  | Sean Geraghty
Greg Watkins
| 2013/14 | 2014/15 | 2015/16 | 2016/17 | 2017/18 | 2018/19 | 2019/20 | Total
Actual | 16602.48 | 15568.81 | 469872.35 | 4602743 | 1741099 |  |  | 6845885.64
Forecast | [7 empty] | 0
Total Expenditure | 16602.48 | 15568.81 | 469872.35 | 4602743 | 1741099 | 0 | 0 | 6845885.64
LGF Fund |  |  | 469872.35 | 4602743 | 20000 |  |  | 5092615.35 | OK |  | 5090000.35
SCC Funding | 16602.48 | 15568.81 | [5 empty] | 32171.29
Developer Funding |  |  |  |  | 1721099 | 0 |  | 1721099
Total Funding | 16602.48 | 15568.81 | 469872.35 | 4602743 | 1741099 | 0 | 0 | 6845885.64 | OK | 7210991.64 |  | £28.2k Additional Developer contribution
Spend to Date | 16602.48 | 15568.81 | 469872.35 | 4602743 | 1741099 | 0 | 0 | 6845885.64
Meaford (CDX8618 & CDX8628) |  |  | SCHEME COMPLETED |  | Responsible Officer - |  |  | Mark Snape
| 2013/14 | 2014/15 | 2015/16 | 2016/17 | 2017/18 | 2018/19 | 2019/20 | Total
Actual | 100606.74 | 562031.43 | 4466646.98 | 928435.43 | 20577 |  |  | 6078297.58
Forecast |  |  |  | 3340.65 |  |  |  | 3340.65
Total Expenditure | 100606.74 | 562031.43 | 4466646.98 | 931776.08 | 20577 | 0 | 0 | 6081638.23
FUNDING SURPLUS | [7 empty] | 0
LGF Fund |  |  | 3700000 | 928435.43 |  |  |  | 4628435.43 | OK |  | 4200000
SCC Funding | 100606.74 | 476428.38 |  | -251259.81 |  |  |  | 325775.31
Developer Funding |  | 85603.05 | 766646.98 | 254600.46 | 20577 |  |  | 1127427.49
Other Funding | [7 empty] | 0
Total Funding | 100606.74 | 562031.43 | 4466646.98 | 931776.08 | 20577 | 0 | 0 | 6081638.23 | OK | 5848653.9 |  | £380.86k funding surplus removed from Project
Spend to Date | 100606.74 | 562031.43 | 4466646.98 | 928435.43 | 20577 | 0 | 0 | 6078297.58
Developer Funding within 30%
Bericote (CDX8615) Phase 1 & Phase 1a - 3 |  |  | SCHEME COMPLETED |  | Responsible Officer - |  |  | Sean Geraghty
Greg Watkins
| 2013/14 | 2014/15 | 2015/16 | 2016/17 | 2017/18 | 2018/19 | 2019/20 | Total
Actual |  | 190417.21 | 1233701.98 | 422205.59 | 15906.58 |  |  | 1862231.36
Forecast | [7 empty] | 0
Total Expenditure | 0 | 190417.21 | 1233701.98 | 422205.59 | 15906.58 | 0 | 0 | 1862231.36
LGF Fund |  | 6532.91 | 1233701.98 | 422205.59 | 15906.58 |  |  | 1678347.06 | OK |  | 1625234.89 | £104.494k Add'l LGF Funding |  | 2129907
SCC Funding | 0 | 183884.3 | [5 empty] | 183884.3 | [5 empty] | -15000
Developer Funding | [5 empty] | 0 |  | 0 |  |  |  | NEW £15k Contribution |  | -104494
Total Funding | 0 | 190417.21 | 1233701.98 | 422205.59 | 15906.58 | 0 | 0 | 1862231.36 |  | 3939026.97 |  | £2,129,907k Developer Contribution removed?
Spend to Date | 0 | 190417.21 | 1233701.98 | 422205.59 | 15906.58 | 0 | 0 | 1862231.36
Berticote (CDX8633) Phase 2 - Growing Places Funded NOT Local Growth Deal
| 2013/14 | 2014/15 | 2015/16 | 2016/17 | 2017/18 | 2018/19 | 2019/20 | Total
Actual |  |  |  | 531605.93 | 3053728 |  |  | 3585333.93
Forecast | [5 empty] | 180554.18 |  | 180554.18
Total Expenditure | 0 | 0 | 0 | 531605.93 | 3053728 | 180554.18 | 0 | 3765888.11
LGF Fund |  |  |  | 531605.93 | 3053728 |  |  | 3585333.93
GPF Grant | [7 empty] | 0
Highways England | [5 empty] | 180554.18 |  | 180554.18
Developer (Lichfield) | [7 empty] | 0
Developer (Meaford) | [7 empty] | 0
LGF Grant (Meaford) | [5 empty] | 0 |  | 0
Total Funding | 0 | 0 | 0 | 531605.93 | 3053728 | 180554.18 | 0 | 3765888.11
Spend to Date | 0 | 0 | 1233701.98 | 531605.93 | 3053728 | 0 | 0 | 4819035.91
Stafford Western LDG1 (CDM0012 & CDM0013) |  |  |  |  | Responsible Officer - |  |  | Dean Sargeant
| 2013/14 | 2014/15 | 2015/16 | 2016/17 | 2017/18 | 2018/19 | 2019/20 | Total
Actual | 38269.27 | 910513 | 1478206.81 | 5019904.52 | 4272460.39 |  |  | 11719353.99
Forecast | [5 empty] | 20462720.59 | 4642940.44 | 25105661.03
Total Expenditure | 38269.27 | 910513 | 1478206.81 | 5019904.52 | 4272460.39 | 20462720.59 | 4642940.44 | 36825015.02
LGF Fund |  |  | 1478206.81 | 4727699.56 | 4272460.39 | 10892300.44 |  | 21370667.2 | OK |  | 24298206.81
SCC Funding | 38269.27 | 860513 | [5 empty] | 898782.27
LEP Funding |  | 50000 | [5 empty] | 50000
Developer Funding |  |  |  | 292204.96 |  | 73447.15 |  | 365652.11
Other Funding | [5 empty] | 9496973 | 4642940.44 | 14139913.44
Total Funding | 38269.27 | 910513 | 1478206.81 | 5019904.52 | 4272460.39 | 20462720.59 | 4642940.44 | 36825015.02 | OK | 44390743.23
Spend to Date | 38269.27 | 910513 | 1478206.81 | 5019904.52 | 4272460.39 | 0 | 0 | 11719353.99
Etruria Valley |  |  |  |  | Responsible Officer - |  |  | Joe Tyzzer
| 2013/14 | 2014/15 | 2015/16 | 2016/17 | 2017/18 | 2018/19 | 2019/20 | Total
Actual |  | 391159 | 1456337 | 1894050 | 1190951 |  |  | 4932497
Forecast | [6 empty] | 8200000 | 8200000
Total Expenditure | 0 | 391159 | 1456337 | 1894050 | 1190951 | 0 | 8200000 | 13132497
LGF Fund | [6 empty] | 8200000 | 8200000 | OK |  | 8200000
SOTCC Funding | 0 |  | 149000 | 1092546 | 1190951 |  |  | 2432497
LEP Funding |  | 391159 | 307337 | 801504 |  |  |  | 1500000
Other Funding |  |  | 1000000 |  |  |  |  | 1000000
Total Funding | 0 | 391159 | 1456337 | 1894050 | 1190951 | 0 | 8200000 | 13132497 | OK | 12256021 |  | £61k Additional Developer contribution
No figures available for 2015/16 onwards at this stage.
Spend to Date | 0 | 391159 | 1456337 | 1894050 | 1190951 | 0 | 0 | 4932497
Local Sustainable Transport Packages (CDT6616, CDT6598, CDB0251) |  |  |  |  | Responsible Officer - |  |  | Annabel Chell |  | 1450000
David Stubbs
| 2013/14 | 2014/15 | 2015/16 | 2016/17 | 2017/18 | 2018/19 | 2019/20 | Total
Actual |  |  | 815037.25 | 5124164.04 | 360750 |  |  | 6299951.29
Forecast | [7 empty] | 0
Total Expenditure | 0 | 0 | 815037.25 | 5124164.04 | 360750 | 0 | 0 | 6299951.29 |  | 7329000.25
LGF Fund |  |  | 815037.25 | 5124164.04 | 360750 |  |  | 6299951.29 | OK |  | 5000000.25
SCC Funding | 0 | [6 empty] | 0
Other Funding (SoTCC) | [5 empty] | 0 |  | 0
Total Funding | 0 | 0 | 815037.25 | 5124164.04 | 360750 | 0 | 0 | 6299951.29 | OK | 5000000.25
Spend to Date | 0 | 0 | 815037.25 | 5124164.04 | 360750 | 0 | 0 | 6299951.29
Advanced Manufacturing Skills Hub - South Staffordshire College |  |  |  |  | Responsible Officer - |  |  | David Poole
| 2013/14 | 2014/15 | 2015/16 | 2016/17 | 2017/18 | 2018/19 | 2019/20 | Total
Actual |  |  | 735442.34 | 3056457.66 |  |  |  | 3791900
Forecast | [7 empty] | 0
Total Expenditure | 0 | 0 | 735442.34 | 3056457.66 | 0 | 0 | 0 | 3791900
0
LGF Fund |  |  | 735442.34 | 3056457.66 |  |  |  | 3791900 | OK |  | 3800000
SCC Funding | 0 | [6 empty] | 0
Other Funding |  |  |  |  | 0 | 0 |  | 0
Total Funding | 0 | 0 | 735442.34 | 3056457.66 | 0 | 0 | 0 | 3791900 | OK | 3800000
Spend to Date | 0 | 0 | 735442.34 | 3056457.66 | 0 | 0 | 0 | 3791900
Advanced Manufacturing Skills Hub - Stafford College |  |  |  |  | Responsible Officer - |  |  | David Poole
| 2013/14 | 2014/15 | 2015/16 | 2016/17 | 2017/18 | 2018/19 | 2019/20 | Total
Actual |  |  |  | 2002400 |  |  |  | 2002400
Forecast | [7 empty] | 0
Total Expenditure | 0 | 0 | 0 | 2002400 | 0 | 0 | 0 | 2002400
0
LGF Fund |  |  | 0 | 2002400 |  |  |  | 2002400 | OK |  | 2000000
SCC Funding | 0 | [6 empty] | 0
Other Funding |  |  |  |  | 0 | 0 |  | 0
Total Funding | 0 | 0 | 0 | 2002400 | 0 | 0 | 0 | 2002400 | OK | 2000000
Spend to Date | 0 | 0 | 0 | 2002400 | 0 | 0 | 0 | 2002400
Advanced Manufacturing Skills Hub - JCB Academy |  |  |  |  | Responsible Officer - |  |  | David Poole
| 2013/14 | 2014/15 | 2015/16 | 2016/17 | 2017/18 | 2018/19 | 2019/20 | Total
Actual |  |  |  | 444356.85 | 670000 |  |  | 1114356.85
Forecast | [7 empty] | 0
Total Expenditure | 0 | 0 | 0 | 444356.85 | 670000 | 0 | 0 | 1114356.85
0
LGF Fund |  |  | 0 | 444356.85 | 670000 |  |  | 1114356.85 | OK |  | 1110220 | £4.52k correction
SCC Funding | 0 | [6 empty] | 0
Other Funding |  |  |  |  | 0 | 0 |  | 0
Total Funding | 0 | 0 | 0 | 444356.85 | 670000 | 0 | 0 | 1114356.85 | OK | 1110220
Spend to Date | 0 | 0 | 0 | 444356.85 | 670000 | 0 | 0 | 1114356.85
Lynne Pugh
Tamworth Enterprise Quarter |  |  |  |  | Responsible Officer - |  |  | David Hunter
TBC
| 2013/14 | 2014/15 | 2015/16 | 2016/17 | 2017/18 | 2018/19 | 2019/20 | Total
Actual |  |  |  | 689993.62 | 643916.79 |  |  | 1333910.41
Forecast |  |  |  |  | 0 |  |  | 0
Total Expenditure | 0 | 0 | 0 | 689993.62 | 643916.79 | 0 | 0 | 1333910.41
0
LGF Fund |  |  |  | 689993.62 | 643916.79 |  |  | 1333910.41 | OK |  | 2950000
SCC Funding | 0 | [6 empty] | 0
Other Funding | [5 empty] | 0 |  | 0
Total Funding | 0 | 0 | 0 | 689993.62 | 643916.79 | 0 | 0 | 1333910.41 | OK | 2950000
Spend to Date | 0 | 0 | 0 | 689993.62 | 643916.79 | 0 | 0 | 1333910.41
Leek Mill Heritage Quarter (LGF Grant Offer Withdrawn) |  |  |  |  | Responsible Officer - |  |  | Helen Pakpahan
SMDC
| 2013/14 | 2014/15 | 2015/16 | 2016/17 | 2017/18 | 2018/19 | 2019/20 | Total
Actual | [7 empty] | 0
Forecast |  |  |  | 0 | 0 | 0 |  | 0
Total Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
LGF Fund |  |  |  | 0 | 0 | 0 |  | 0 | OK |  | 800000
SCC Funding | 0 | [6 empty] | 0
Other Funding |  |  |  |  | 0 | 0 |  | 0
Total Funding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OK | 800000
Spend to Date | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rugeley Town Centre Improvements (LGF Grant Offer Withdrawn) |  |  |  |  | Responsible Officer - |  |  | Will Groves
Environment Agency
| 2013/14 | 2014/15 | 2015/16 | 2016/17 | 2017/18 | 2018/19 | 2019/20 | Total
Actual |  |  |  | 754260 |  |  |  | 754260
Forecast | [6 empty] | 0 | 0
Total Expenditure | 0 | 0 | 0 | 754260 | 0 | 0 | 0 | 754260
0
LGF Fund |  |  |  | 754260 |  |  | 0 | 754260 | OK |  | 1300000
SCC Funding | 0 | [6 empty] | 0
Other Funding |  |  |  |  | 0 | 0 | 0 | 0
Total Funding | 0 | 0 | 0 | 754260 | 0 | 0 | 0 | 754260 | OK | 1737000
Spend to Date | 0 | 0 | 0 | 754260 | 0 | 0 | 0 | 754260
Friarsgate, Lichfield |  |  |  |  | Responsible Officer - |  |  | Helen Bielby
LDC
| 2013/14 | 2014/15 | 2015/16 | 2016/17 | 2017/18 | 2018/19 | 2019/20 | Total
Actual |  |  |  | 0 | 70925 |  |  | 70925
Forecast |  |  |  | 0 | 0 | 2389075 | 200000 | 2589075
Total Expenditure | 0 | 0 | 0 | 0 | 70925 | 2389075 | 200000 | 2660000
0
LGF Fund |  |  |  | 0 | 70925 | 2389075 | 200000 | 2660000 | OK |  | 2660000
SCC Funding | 0 | [6 empty] | 0
Other Funding |  |  |  |  | 0 | 0 |  | 0
Total Funding | 0 | 0 | 0 | 0 | 70925 | 2389075 | 200000 | 2660000 | OK | 2660000
Spend to Date | 0 | 0 | 0 | 0 | 70925 | 0 | 0 | 70925
North West Approach to City Centre (SoTCC) |  |  |  |  | Responsible Officer - |  |  | Alan Smith
(SoTCC)
| 2013/14 | 2014/15 | 2015/16 | 2016/17 | 2017/18 | 2018/19 | 2019/20 | Total
Actual |  |  | 60000 | 805766.68 | 626000 |  |  | 1491766.68
Forecast |  |  |  |  | 0 | 500000 | 1358233.32 | 1858233.32
Total Expenditure | 0 | 0 | 60000 | 805766.68 | 626000 | 500000 | 1358233.32 | 3350000
0
LGF Fund |  |  | 60000 | 805766.68 | 626000 | 500000 | 1358233.32 | 3350000 | OK |  | 3210000
SoTCC Funding | [7 empty] | 0
Other Funding | [7 empty] | 0
Total Funding | 0 | 0 | 60000 | 805766.68 | 626000 | 500000 | 1358233.32 | 3350000 | OK | 4810000
Spend to Date | 0 | 0 | 57056 | 805766.68 | 626000 | 0 | 0 | 1488822.68
South East Approach to City Centre (SoTCC) |  |  |  |  | Responsible Officer - |  |  | Alan Smith |  |  |  |  | Total LGF
[8 empty] | (SoTCC) |  |  |  |  | 3350000
| 2013/14 | 2014/15 | 2015/16 | 2016/17 | 2017/18 | 2018/19 | 2019/20 | Total |  |  |  |  | 3349668
Actual |  |  |  | 0 | 82668 |  |  | 82668 |  |  |  |  | 1010000
Forecast |  |  |  | 0 |  | 750000 | 2517000 | 3267000 |  |  |  |  | 7709668
Total Expenditure | 0 | 0 | 0 | 0 | 82668 | 750000 | 2517000 | 3349668 |  |  |  |  | 7710000
[8 empty] | 0 |  | -332
LGF Fund |  |  |  |  | 82668 | 750000 | 2517000 | 3349668 | OK |  | 2200000
SoTCC Funding | [7 empty] | 0
Other Funding | [7 empty] | 0
Total Funding | 0 | 0 | 0 | 0 | 82668 | 750000 | 2517000 | 3349668 | OK | 2700000
Spend to Date | 0 | 0 | 0 | 0 | 82668 | 0 | 0 | 82668
South West Approach to City Centre (SoTCC) |  |  |  |  | Responsible Officer - |  |  | Alan Smith
(SoTCC)
| 2013/14 | 2014/15 | 2015/16 | 2016/17 | 2017/18 | 2018/19 | 2019/20 | Total
Actual |  |  |  | 1721009 | 515805 |  |  | 2236814
Forecast |  |  |  |  | 2195 |  |  | 2195
Total Expenditure | 0 | 0 | 0 | 1721009 | 518000 | 0 | 0 | 2239009
0
LGF Fund |  |  |  | 1721009 | 518000 | -1229009 |  | 1010000 | OK |  | 2300000 |  | 1010000
SoTCC Funding | [5 empty] | 1229009 |  | 1229009
Other Funding | [7 empty] | 0
Total Funding | 0 | 0 | 0 | 1721009 | 518000 | 0 | 0 | 2239009 | OK | 2300000
Spend to Date | 0 | 0 | 0 | 1721009 | 515805 | 0 | 0 | 2236814
ROF Featherstone LGD3 (CDX8624)
| 2013/14 | 2014/15 | 2015/16 | 2016/17 | 2017/18 | 2018/19 | 2019/20 | Total
Actual |  |  |  |  | 369148 |  |  | 369148
Forecast | [5 empty] | 2175258.48 |  | 2175258.48
Total Expenditure | 0 | 0 | 0 | 0 | 369148 | 2175258.48 | 0 | 2544406.48
0
LGF Fund | [5 empty] | 1500000 |  | 1500000
SoTCC Funding | [5 empty] | 174000 |  | 174000
SCC Funding |  |  |  |  | 369148 |  |  | 369148
Developer Funding | [5 empty] | 501258.48 |  | 501258.48
Total Funding | 0 | 0 | 0 | 0 | 369148 | 2175258.48 | 0 | 2544406.48
Spend to Date | 0 | 0 | 0 | 0 | 369148 | 0 | 0 | 369148
LSTP (LDG3)
| 2013/14 | 2014/15 | 2015/16 | 2016/17 | 2017/18 | 2018/19 | 2019/20 | Total
Actual |  |  |  |  | 460000 |  |  | 460000
Forecast |  |  |  |  | 0 |  |  | 0
Total Expenditure | 0 | 0 | 0 | 0 | 460000 | 0 | 0 | 460000
0
LGF Fund |  |  |  |  | 460000 | 0 |  | 460000
SoTCC Funding | [7 empty] | 0
Other Funding | [7 empty] | 0
Total Funding | 0 | 0 | 0 | 0 | 460000 | 0 | 0 | 460000
Spend to Date | 0 | 0 | 0 | 0 | 460000 | 0 | 0 | 460000
| 2013/14 | 2014/15 | 2015/16 | 2016/17 | 2017/18 | 2018/19 | 2019/20 | Total
Total Expenditure | 205022.86 | 3686619.18 | 13982796.71 | 28454740.18 | 14127567.57 | 26457608.25 | 16918173.76 | 103832528.51 |  |  |  | CHECK TOTALS FORMULA
| OK | OK | OK | OK | OK | OK | OK | 0
Total Funding | 205022.86 | 3686619.18 | 13982796.71 | 28454740.18 | 14127567.57 | 26457608.25 | 16918173.76 | 103832528.51 |  | 117697351.34 | 74743662.3 | CHECK TOTALS FORMULA
Total Spend to Date | 205022.86 | 3686619.18 | 15213554.69 | 28451399.53 | 14125372.57 | 0 | 0 | 54166118.92
Balance to be spent in yr | 0 | 0 | -1230757.98 | 3340.65 | 2195 | 26457608.25 | 16918173.76 | 49666409.59
% of planned spend |  |  | 108.8%
£.
NOTE - Project Lead for Spode Church Street (Phase 2) is Neil Clarke (SoTCC)
Note on D22: Broad, John (People): Forecast spend was £729,524 as at 14th Sept. Revised down to £500k as per the Funding Review paper 21st Sept 15.
Note on C39: Zala, Anita (Place): this includes main works, statutory undertakers - All SCC funded???
Note on F69: Broad, John (People): £2.389m now funded from LGF Grant 17/18 instead of GPF.
Note on E105: Broad, John (People): RGF funding 2016/17.
Note on H240: Broad, John (People): Note - £200k to be spent in 2020/21.

## The City Deal
Chart 3 -The City Deal 2015/16 to 2020/21 - Summary
Scheme/Project/Programme | Project Lead | Total Project Cost (£m) | Year 2 Project Cost (£m) | Spend to Date (£m) | Commitments (£m) | Forecast Outturn (£m) | Variance | % Variance
ENERGY
E1 - Stoke on Trent Distict Heat Network | Andrew Briggs (SOT) | 51.27 | 2.815 | 2.3833 | 0.43173 | 2.815 | 0 | 100%
E2 - Keele University Smart Energy Network Demonstrator | Philip Butters (Keele University) | 15 | 1.425 | 1.425 | 0 | 1.425 | 0 | 100%
ENERGY TOTAL |  | 66.27 | 4.24 | 3.8083 | 0.43173 | 4.24 | 0 | 100%
ENTERPRISE & INNOVATION
EI1 - Stoke-on-Trent and Staffordshire LEP (Growth Hubs) | Nicola Kent (SCC) | 3.945 | 0.205 | 0.205 | 0 | 0.205 | 0 | 100%
ENTERPRISE & INNOVATION TOTAL |  | 3.945 | 0.205 | 0.205 | 0 | 0.205 | 0 | 100%
SKILLS
No Schemes | N/A |  | 0 | 0 | 0 | 0 | 0 | #DIV/0!
SKILLS TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
SITES INFRASTRUCTURE & LOCAL DEVELOPMENT
No Schemes | N/A | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
SITE INFRASTRUCTURE & LOCAL DEVELOPMENT TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CITY DEAL SUB TOTAL |  | 70.215 | 4.445 | 4.0133 | 0.43173 | 4.445 | 0 | 100%
2018/19 Q4 REVENUE OUTTURN (as @ 31/03/2019)
Growth Hub Funding 2018/19
| Actuals |  | Budget
| £. |  | £.
Claim 1 (April 18 - June 18) | 56057 | Received | 56057
Claim 2 (July 18 - Sept 18) | 47038 | Received | 47038
Claim 3 (Oct 18 - Dec 18) | 47068 | Received | 47068
Claim 4 (Jan 19 - Mar 19) | 54837 | Received | 54837
Total Claimed to Date | 205000 |  | 205000
Total Growth Hub Funding Approved | 205000 | # | 205000
Notes:
Grant is to be spent on Client Referral Management System, Website maintenance & development
and Business Help Line. Project Management & Consultation; Evaluation & Monitoring.
Note on C5: Broad, John (People): DO we report £51.77m as per SOT figures?
Note on E6: Broad, John (People): Claims 1,2 & 3 submitted - Passport Agreement now signed by all parties.

## ESIF Summary
Chart 5: Overall Financial Summary of European Structural and Investment Fund (ESIF)
1. Breakdown of Total ESIF funding by Theme
The percentage breakdown of expenditure is determined by Government and LEP's broadly follow this.
| Theme | Strategy |  | Emerging Pipeline - ESIF (Round 1 2 & 3) |  | Variance (minus figures = over allocated)
|  | £m | % | £m | % | £m | Percentage (-over or +under allocated) |  | Previous ESIF Strat Figures
| PA1 Innovation | 25.17 | 16.22% | 18.88 | 75.01% | 6.29 | 24.99% | ERDF | 21.736
| PA 2 ICT | 0.48 | 0.3094% | 0 | 0% | 0.48 | 100% | ERDF | 0.41
| PA3 SME | 45.94 | 29.61% | 39.55 | 86.09% | 6.39 | 13.91% | ERDF | 39.84
| PA 4 Low Carbon | 15.01 | 9.675% | 12.32 | 82.08% | 2.69 | 17.92% | ERDF | 12.959
| PA 5 Climate Change | 1 | 0.6445% | 0 | 0% | 1 | 100% | ERDF | 0
| PA 6 Environment | 3.25 | 2.095% | 2.12 | 65.23% | 1.13 | 34.77% | ERDF | 3.5
| PA 8&9 Skills, Employt | 64.3 | 41.44% | 43.1309 | 67.08% | 21.1691 | 32.92% | ESF | 56
| Total | 155.15 | 100% | 116.0009 | 74.77% | 39.1491 | 25.23% |  | 134.445
2018/19 Q4 REVENUE OUTTURN (as @ 31/03/2019)
|  |  | ERDF | 80.21%
|  |  | ESF | 67.08%
Notes:
Q2 | PA3 SME Theme has been reduced by -£1.697m @ Q2.
Q2 | PA8&9 Skills & Employability Theme increased by £1m @ Q2.
Q3 | PA5 Climate Change £1m introduced @ Q3.
Q3 | PA3 SME Theme reduced by a further £0.2m @ Q3.
Q3 | PA6 Environment Theme reduced by £0.8m @ Q3.
Q3 | PA8&9 Skills & Employability Theme increased by a further £8.3m @ Q3.
Note on C11: Wilkes, William (Finance): 0.5 added to reconcile to the SIA in the strategy
Note on K11: Wilkes, William (Finance): 0.5 added to reconcile to the SIA in the strategy

## GPF - Rnd 1-13
Growing Places Fund ¦ Capital Financial Overview ¦ Round 1 - 13 schemes
As @ 18 03 2019
|  | INCOME | EXPENDITURE & REPAYMENT | [39 empty] | Fund Balance |  |  | Fund Balance (Stoke) |  |  | Fund Balance (Staffordshire - Countywide)
|  | GPF funding | Round 1 |  | Round 2 |  |  |  | Round 3 |  | Round 4 |  | Round 5 |  | Round 6 |  | Round 7 | [5 empty] | Round 8 |  | Round 9 | [5 empty] | Round 10 |  | Round 11 |  | Round 12 & 13 | [5 empty] | Underwriting Overprogramming in LGF
|  |  | Etruria Valley without public enquiry |  | Dunston Business Village |  | Leekbrook Ind. Est. Extn. |  | HellermannTyton |  | None |  | Hilton Garden Hotel |  | None |  | Dunston Business Village |  | Lichfield South |  | London House |  | None |  | Caverswall Castle |  | Omicron Training Centre |  | Oak House Residential Home |  | None |  | London House Ph3 |  | Harper Street, Middleport Pottery |  | Canalside Farm |  | Scott FM |  |  |  | Expenditure | Income | Running total | Expenditure | Income | Running total | Expenditure | Income | Running total
|  |  | Exp | Inc | Exp | Inc | Exp | Inc | Exp | Inc | Exp | Inc | Exp | Inc | Exp | Inc | Exp | Inc | Exp | Inc | Exp | Inc | Exp | Inc | Exp | Inc | Exp | Inc | Exp | Inc | Exp | Inc | Exp | Inc | Exp | Inc | Exp | Inc | Exp | Inc | Exp | Inc | Exp | Inc |  | Exp | Inc |  | Exp | Inc
2011/12 |  | -10593330 | [40 empty] | 0 | 0 | -10593330 | 0 | 0 | -5296665 | 0 | 0 | -5296665
2012/13 | Q1 | [41 empty] | 0 | 0 | -10593330 | 0 | 0 | -5296665 | 0 | 0 | -5296665
| Q2 | [41 empty] | 0 | 0 | -10593330 | 0 | 0 | -5296665 | 0 | 0 | -5296665
| Q3 | [41 empty] | 0 | 0 | -10593330 | 0 | 0 | -5296665 | 0 | 0 | -5296665
| Q4 | [41 empty] | 0 | 0 | -10593330 | 0 | 0 | -5296665 | 0 | 0 | -5296665
2013/14 | Q1 | -34110 | [40 empty] | 0 | -34110 | -10627440 | 0 | 0 | -5313720 | 0 | 0 | -5313720
| Q2 | [41 empty] | 0 | 0 | -10627440 | 0 | 0 | -5313720 | 0 | 0 | -5313720
| Q3 | [41 empty] | 0 | 0 | -10627440 | 0 | 0 | -5313720 | 0 | 0 | -5313720
| Q4 | [41 empty] | 0 | 0 | -10627440 | 0 | 0 | -5313720 | 0 | 0 | -5313720
2014/15 | Q1 | -46516.26 | [40 empty] | 0 | -46516.26 | -10673956.26 | 0 | 0 | -5336978.13 | 0 | 0 | -5336978.13
| Q2 | [41 empty] | 0 | 0 | -10673956.26 | 0 | 0 | -5336978.13 | 0 | 0 | -5336978.13
| Q3 |  |  |  | 308253.38 | [37 empty] | 308253.38 | 0 | -10365702.88 | 0 | 0 | -5182851.44 | 308253.38 | 0 | -5182851.44
| Q4 |  |  |  | 91374 | [37 empty] | 91374 | 0 | -10274328.88 | 0 | 0 | -5137164.44 | 91374 | 0 | -5137164.44
2015/16 | Q1 | -46695.85 |  |  | 89733 | [37 empty] | 89733 | -46695.85 | -10231291.73 | 0 | 0 | -5115645.865 | 89733 | 0 | -5115645.865
| Q2 |  |  |  | 96640 | [37 empty] | 96640 | 0 | -10134651.73 | 0 | 0 | -5067325.865 | 96640 | 0 | -5067325.865
| Q3 | [41 empty] | 0 | 0 | -10134651.73 | 0 | 0 | -5067325.865 | 0 | 0 | -5067325.865
| Q4 | [15 empty] | 87510.16 | [25 empty] | 87510.16 | 0 | -10047141.57 | 0 | 0 | -5023570.785 | 87510.16 | 0 | -5023570.785
2016/17 | Q1 | [15 empty] | 40847.08 | [25 empty] | 40847.08 | 0 | -10006294.49 | 0 | 0 | -5003147.245 | 40847.08 | 0 | -5003147.245
| Q2 | [7 empty] | 543271 | [7 empty] | 23432.67 |  |  |  | 639749 | [21 empty] | 1206452.67 | 0 | -8799841.82 | 639749 | 0 | -4080046.41 | 566703.67 | 0 | -4399920.91
| Q3 | [7 empty] | 206729 | [7 empty] | 31538.11 |  |  |  | 422751 | [21 empty] | 661018.11 | 0 | -8138823.71 | 422751 | 0 | -3858036.355 | 238267.11 | 0 | -4069411.855
| Q4 | [41 empty] | 0 | 0 | -8138823.71 | 0 | 0 | -4069411.855 | 0 | 0 | -4069411.855
2017/18 | Q1 | [15 empty] | 28336.92 | [25 empty] | 28336.92 | 0 | -8110486.79 | 0 | 0 | -4055243.395 | 28336.92 | 0 | -4055243.395
| Q2 |  |  |  |  | -585999.99 | [10 empty] | 35234.03 | [25 empty] | 35234.03 | -585999.99 | -8661252.75 | 0 | 0 | -4330626.375 | 35234.03 | -585999.99 | -4330626.375
| Q3 | [27 empty] | 220000 | [13 empty] | 220000 | 0 | -8441252.75 | 220000 | 0 | -4110626.375 | 0 | 0 | -4220626.375
| Q4 |  | 702835 | [9 empty] | 2960000 | [8 empty] | -1069111.15 |  |  |  |  | 400000 |  |  | -220000 | [10 empty] | 2389635 |  | 6452470 | -1289111.15 | -3277893.9 | 3662835 | -1289111.15 | -452085.025 | 2789635 | 0 | -1638946.95
2018/19 | Q1 | [41 empty] | 0 | 0 | -3277893.9 | 0 | 0 | -1638946.95 | 0 | 0 | -1638946.95
| Q2 | [8 empty] | -750000 | [22 empty] | 450000 | [9 empty] | 450000 | -750000 | -3577893.9 | 450000 | 0 | -1563946.95 | 0 | -750000 | -1788946.95
| Q3 | [15 empty] | 101167.07 |  | 230625 | [23 empty] | 331792.07 | 0 | -3246101.83 | 0 | 0 | -1623050.915 | 331792.07 | 0 | -1623050.915
| Q4 | [15 empty] | 117705.29 |  | 664957 | [15 empty] | 370000 |  | 300000 |  |  |  | 610365 |  | 2063027.29 | 0 | -1183074.54 | 370000 | 0 | -406537.27 | 1693027.29 | 0 | -591537.27
2019/20 | Q1 | [15 empty] | 264229 | [21 empty] | 75000 |  |  |  | 339229 | 0 | -843845.54 | 0 | 0 | -421922.77 | 339229 | 0 | -421922.77
| Q2 | [16 empty] | -246899 | [9 empty] | -400000 | [14 empty] | 0 | -646899 | -1490744.54 | 0 | 0 | -745372.27 | 0 | -646899 | -745372.27
| Q3 | [18 empty] | -230625 | [13 empty] | -450000 | [8 empty] | 0 | -680625 | -2171369.54 | 0 | -450000 | -1310684.77 | 0 | -230625 | -1085684.77
| Q4 |  | 1697165 | [39 empty] | 1697165 | 0 | -474204.54 | 1697165 | 0 | 611480.23 | 0 | 0 | -237102.27
2020/21 | Q1 | [41 empty] | 0 | 0 | -474204.54 | 0 | 0 | -237102.27 | 0 | 0 | -237102.27
| Q2 | [41 empty] | 0 | 0 | -474204.54 | 0 | 0 | -237102.27 | 0 | 0 | -237102.27
| Q3 | [41 empty] | 0 | 0 | -474204.54 | 0 | 0 | -237102.27 | 0 | 0 | -237102.27
| Q4 | [16 empty] | -483101 |  | -230625 | [15 empty] | -370000 |  | -300000 |  |  |  |  | 0 | -1383726 | -1857930.54 | 0 | -370000 | -1113965.27 | 0 | -1013726 | -928965.27
2021/22 | Q1 | [38 empty] | -75000 |  |  | 0 | -75000 | -1932930.54 | 0 | 0 | -966465.27 | 0 | -75000 | -966465.27
| Q2 | [41 empty] | 0 | 0 | -1932930.54 | 0 | 0 | -966465.27 | 0 | 0 | -966465.27
| Q3 | [41 empty] | 0 | 0 | -1932930.54 | 0 | 0 | -966465.27 | 0 | 0 | -966465.27
| Q4 | [18 empty] | -240083 | [22 empty] | 0 | -240083 | -2173013.54 | 0 | 0 | -1086506.77 | 0 | -240083 | -1086506.77
2022/23 | Q1 | [41 empty] | 0 | 0 | -2173013.54 | 0 | 0 | -1086506.77 | 0 | 0 | -1086506.77
| Q2 | [41 empty] | 0 | 0 | -2173013.54 | 0 | 0 | -1086506.77 | 0 | 0 | -1086506.77
| Q3 | [41 empty] | 0 | 0 | -2173013.54 | 0 | 0 | -1086506.77 | 0 | 0 | -1086506.77
| Q4 | [18 empty] | -249929 | [22 empty] | 0 | -249929 | -2422942.54 | 0 | 0 | -1211471.27 | 0 | -249929 | -1211471.27
TOTAL |  | -10720652.11 | 2400000 | 0 | 586000.38 | -585999.99 | 0 | 0 | 750000 | -750000 | 0 | 0 | 2960000 | 0 | 0 | 0 | 730000.33 | -730000 | 895582 | -951262 | 1062500 | -1069111.15 | 0 | 0 | 0 | 0 | 400000 | -400000 | 220000 | -220000 | 0 | 0 | 450000 | -450000 | 370000 | -370000 | 300000 | -300000 | 75000 | -75000 | 3000000 | 0 | 14199082.71 | -5901373.14 |  | 7462500 | -2109111.15 |  | 6736582.71 | -3792261.99
Underwriting Over programming in LGF
|  |  |  | Round 1 |  | Round 2 |  | Round 3 |  | Round 4 |  |  | Round 5 |  |  |  | Round 6 |  | Round 7 |  | Round 8 |  | Round 9 |  | Round 10 |  | Round 11 |  | Round 12 | Over Programming |  |  | Total allocation | [9 empty] | 8297709.57 | 8297709.57
[35 empty] | checks | [7 empty] | CHECKS | CHECKS |  |  |  |  | 14199082.71 | 14199082.71 | 0
Overall scheme allocations |  |  | = | 2400000 |  | 586000.38 |  | 750000 |  | 0 |  |  | 2960000 |  |  |  | 0 |  | 2688082.33 |  | 0 |  | 620000 |  | 0 |  | 450000 |  | 745000 | 3000000 |  | = | 14199082.71 |  | 14199082.71
Overall scheme repayments |  |  | = | 0 |  | -585999.99 |  | -750000 |  | 0 |  |  | 0 |  |  |  | 0 |  | -2750373.15 |  | 0 |  | -620000 |  | 0 |  | -450000 |  | -745000 | 0 |  | = | -5901373.14 |  | -5901373.14 | [13 empty] | -5901373.14 | -5901373.14 | 0
Investment as grant |  |  | = | 2400000 |  | 0.39 |  | 0 |  | 0 |  |  | 2960000 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 3000000 |  | = | 8360000.39 |  | 8360000
Total Capital GPF allocated to Stoke & Staffs LEP = |  |  |  |  | -10720652.11 |  | Grant & Interest accrued
Percentage under/over allocated = |  |  |  | -232.4%
NOTES.
1 |  | Current quarter
2 |  | Low point for overall fund
Changes - new changes
| 1 | LGF underwriting. Full expenditure in Q4 2017/18
| 2 | EV GPF Grant spend Profile merged into 1 Q4 payment in both 2018/19 and 2020/21 due to SoTCC claiming GPF to finance their respective capital programme at the year end.
| 3 | Round 12 GPF Schemes included from 12/11/18 - Harper Street, Middleport Pottery (£370k loan) and Canalside (£300k loan) to be paid out in Q4 2018/19 and then repaid in Q4 2020/21.
Previous raft of changes
| 1 | Oak House Residential Care home - repayment brought forward to Q1 2018/19
| 2 | Rd 2. Leekbrook Industrial Estate Extension de-allocated
| 3 | rd 11. London House Phase 3 repayment moved to Q3 of 2018/19
| 4 | Anomaly in Funding Balance 'Expenditure' & 'Income' calculation corrected
| 5 | Rd. 1. Etruria Valley re-profiled after claim No. 1
| 6 | Rd. 7 Dunston Business Village Ph 2 reprofiled
7
8
9
Note on D5: Broad, John (People): EV spend profile based on expected Public Inquiry.
Note on C12: Broad, John (People): Accrued Interest on GPF 2012/13
Note on C16: Broad, John (People): Accrued Interest on GPF 2013/14
Note on C20: Broad, John (People): Accrued Interest on GPF 2014/15
Note on D32: Henderson, Eric (E,I&S): = 88069 + (858998 - 702835) = 88069 + 156163 = 244232
Note on T34: Henderson, Eric (E,I&S): 230624 + 461250
Note on AJ58: Broad, John (People): NOTE - Total fund less 3 x accrued interest.

## Core Fund Grant
LEP Core & Capacity Grant 2018/19
Activity | Approved | Spent | Outturn | Balance
| £ | £ | £ | £
LEP Office & Delivery Team
LEP Delivery Team (incl New Support Post & Project Manager) | 113519 | 93679.29 | 113519 | 0
Programme Manager (Consultant) | 78000 | 71500 | 78000 | 0
LEP Board Activities & Chair (incl Honorarium) | 35000 | 22970.77 | 35000 | 0
Research & Studies (Bank Searches) | 8000 | 8000 | 8000 | 0
Office Rental | 12250 | 9187.5 | 12250 | 0
Drawing Room/ Reception Contribution (Chamber of Commerce) | 5500 | 4125 | 5500 | 0
Branding & Communications | 3000 | 1109 | 3000 | 0
Legal Costs | 2000 | 312 | 2000 | 0
Sub Total | 257269 | 210883.56 | 257269 | 0
Business Engagement & Support
Business Engagement & Events | 21872.99 | 20281.68 | 21872.99 | 0
Midlands Engine | 20000 | 20000 | 20000 | 0
MIPIM (France) | 50000 | 50000 | 50000 | 0
Sub Total | 91872.99 | 90281.68 | 91872.99 | 0
Strategic Planning
Regulation (includes 2017/18 c/fwd of £2.5k ) | 15000 | 15000 | 15000 | 0
Investment Services Review (incl 2017/18 c/fwd) | 5000 | 5000 | 5000 | 0
Industrial Strategy | 5000 |  | 5000 | 0
Sub Total | 25000 | 20000 | 25000 | 0
Project & Programme Development
Approved GD Project Development Work - SoTCC (2017/18 grant c/fwd) | 14012.49 | 2350 | 14012.49 | 0
Agri-Tech (includes 2017/18 c/fwd) | 12750 | 2750 | 12750 | 0
Visitor Economy Research | 25000 | 13750 | 25000 | 0
Careers Company (2017/18 c/fwd) | 11415.31 | 11415.31 | 11415.31 | 0
Careers Company | 25000 | 6049.46 | 25000 | 0
M6 Junction 14a Study | 15000 | 10980 | 15000 | 0
Construction Skills Pipeline Analysis | 2000 | 2000 | 2000 | 0
Constellation Partnership Urban Development Fund (Ex Ante) | 34833 | 34833 | 34833 | 0
Platform (2017/18 c/fwd) | 6335 | 6335 | 6335 | 0
Platform Phase 2 (New Funding Proposal) | 20000 | 6615.43 | 20000 | 0
Apprenticeship Graduation Ceremony | 7000 |  | 7000 | 0
Cultural Development Fund - Full Application Submission | 17000 | 17000 | 17000 | 0
Cultural Development Fund EOI | 8500 | 8500 | 8500 | 0
Apprentice Ladder | 18500 |  | 18500 | 0
Sub Total | 217345.8 | 122578.2 | 217345.8 | 0
Unallocated Funds | 9978 | 5930 | 9978 | 0
Total | 601465.79 | 449673.44 | 601465.79 | 0
Carry Forward 17/18 (Core Fund & Capacity Grant) |  | 113466
Total Core Grant Budget Available |  | 500000
Total LEP Grant Funding 2018/19 |  | 613466 |  | 73.3%
2018/19 Q4 REVENUE OUTTURN (as @ 31/03/2019)
| 601465.79 | Check
601465.79
151792.35
Note Smarter Staffordshire C&C Grant funding bid - circa £100k (TBC)
|  | 471048.44 | Check to LEP Funding Management Group schedule
includes Other Funding contributions to projects.
Note on B48: Broad, John (F&R): Spode Studios (£8,618.74) plus Hanley Bentilee Link (£5,393.75) c/fwd from 17/18.

## ESIF Pipeline (hidden)
Stoke-on-Trent and Staffordshire Enterprise Partnership
ESIF Programme 2014-2020
Emerging project pipeline as @ 20th January 2016
DRAFT - Incl National Opt In Projects
ESIF Theme | Lead partner/SRO | Bidding type | Bidding stage | Status | Value (£) |  |  | Bidding call
[5 empty] | Total | ESIF | Match |  | Full Appl'n
Priority 1- Innovation
Keele Global R & D Gateway | Keele Uni (Mark Bacon) | Local/Open | Outline | Submitted | 3168579 | 1901148 | 1267431 | March | Y
Innovation Product Support Services | University of Wolverhampton | National Opt In | Outline | Submitted | 2634464 | 79034 | 2555430 | ? | Y
Innovation Network 1518 | Coventry University Enterprises Ltd | ? | Outline | Submitted | 0 | 0 | 0 |  | N
Focus Digital | Coventry University Enterprises Ltd | ? | Outline | Submitted | 0 | 0 | 0 |  | N
Stoke & Staffs - Alternative Raw Materials with Low Impact | International Synergies | ? | Outline | Submitted | 0 | 0 | 0 |  | N
EBRI | Aston University | National Opt In | Outline | Submitted | 2595670 | 129784 | 2465886 | ? | Y
Staffs Business Innovation & Innovation Support 3 (SBIIS3) | Staffs BIC (Geoff Riley) | Local/Open | Outline | Submitted | 2515179 | 1509107 | 1006072 | March | Y
Stoke on Trent and Staffordshire Medical Research & Development Centre | Keele University | ? |  |  | 12506339 | 12506339 | 0 |  | Y
TOTAL |  |  |  |  | 23420231 | 16125412 | 7294819 |  | OK
Priority 3 - Business Support
Growth Hub | Stoke City Council (Jon Phipps) | Local/Open | Outline | Submitted | 4389449 | 2465670 | 1923779 | March | Y
Staffordsheer Excellence | Staffs CC (Graeme Whitehead) | Local/Open | Outline | Submitted | 6020000 | 3612000 | 2408000 | March | Y
Tamworth Enterprise Qtr (Philip Dix Centre) | Tamworth BC (David Hunter) | Local/Open | Outline | Submitted | 982166 | 589300 | 392866 | March | Y
Mentoring for Growth Programme | Staffs Chamber (Adele Cope) | Local/Open | Outline | Submitted | 1314272 | 788563 | 525709 | March | Y
Grants for Growth | Stoke City Council (Jon Phipps) | Local/Open | Outline | Submitted | 7062479 | 2237488 | 4824991 | March | Y
Enterprise Coaches | BES (Judith Kirkland) | Local/Open | Outline | Submitted | 1649173 | 990599 | 658574 | March | Y
Be Inspired Staffordshire Hub (biSH) | Staffs Uni (Claire Hameed) | Local/Open | Outline | Submitted | 1000000 | 600000 | 400000 | March | Y
HS2 | Birmingham City Council | National Opt In | Outline | Submitted | 40000000 | 1196720 | 38803280 | ? | Y
STAR | Birmingham City Council | National Opt In | Outline | Submitted | 11357950 | 567898 | 10790052 | ? | Y
Business Development Programme | Birmingham City Council | National Opt In | Outline | Submitted | 10662508 | 426500 | 10236008 | ? | Y
Business Innovation Programme | Birmingham City Council | National Opt In | Outline | Submitted | 7900000 | 316000 | 7584000 | ? | Y
Green Bridge Supply Chain | Birmingham City Council | National Opt In | Outline | Submitted | 15100000 | 755000 | 14345000 | ? | Y
SPARK | University of Wolverhampton | ? |  |  | 0 | 0 | 0 |  | N
The Prince's Trust - 'Better off in Business' project | The Prince's Trust | ? |  |  | 0 | 0 | 0 |  | N
Stoke & Staffordshire Industrial Symbiosis Network | International Synergies | ? |  |  | 0 | 0 | 0 |  | N
Get Set for Growth | YTKO Ltd | ? |  |  | 0 | 0 | 0 |  | N
The Regeneration of the Wedgwood Institute , Burslem | The UK Historical Building Preservation Trust | ? |  |  | 0 | 0 | 0 |  | N | *
The New Funding Paradigm: The Alternative Finance Readiness Accelerator | Entrepreneurs & Education | ? |  |  | 0 | 0 | 0 |  | N
Better Off in Business | The Prince's Trust | ? |  |  | 579041 | 347425 | 231616 |  | Y
Get Set for Growth | YTKO Ltd | ? |  |  | 0 | 0 | 0 |  | N
Keele Institute for Entrepreneurship, Innovation & Leadership (KIEIL) | Keele University | ? |  |  | 9624614 | 5774768 | 3849846 |  | Y
Cornhill East | Staffordshire Moorlands DC | ? |  |  | 0 | 0 | 0 |  | N
Leek Mill Quarter | Staffordshire Moorlands DC | ? |  |  | 4017128 | 1397136 | 2619992 |  | Y
Horizon to Growth Support to SME's | Pathway First ltd | ? |  |  | 0 | 0 | 0 |  | N
Rural Enterprise Programme | Staffordshire County Council | ? |  |  | 5285545 | 2256147 | 3029398 |  | Y
The Regeneration of the Wedgwood Institute , Burslem | The UK Historical Building Preservation Trust | ? |  |  | 6552218 | 3931330 | 2620888 |  | Y
TOTAL |  |  |  |  | 133496543 | 28252544 | 105243999 |  | OK
Priority 3 - Trade
Enhancing International Trade Performance Through Clusters | Coventry University Enterprises Ltd | ? |  |  | 12534000 | 1395786 | 11138214 |  | Y
TOTAL |  |  |  |  | 12534000 | 1395786 | 11138214 | 0 | OK
Priority 3 - Manufacturing
Enhanced Business Growth Service - West Midlands (Manufacturing Advisory Service & Growth Accelerator for Manufacturers) | West Midlands Manufacturing Consortium Ltd | ? |  |  | 6163575 | 595856 | 5567719 |  | Y
TOTAL |  |  |  |  | 6163575 | 595856 | 5567719 | 0 | OK
Priority 3 - High Growth
Enhanced BGS (Access to Finance for High Growth Potential SME's) | Grant Thornton UK LLP | ? |  |  | 871000 | 168750 | 702250 |  | Y
West Midlands Growth Accelerator Extension | Pera Consulting UK Ltd | ? |  |  | 5616000 | 1125000 | 4491000 |  | Y
TOTAL |  |  |  |  | 6487000 | 1293750 | 5193250 | 0 | OK
Priority 4 - Low Carbon
Keele SEND & CEESR | Keele Uni (Mark Bacon) | Local/Open | Outline | Submitted | 12500000 | 7500000 | 5000000 | March | Y
Fast Tracking Energy Efficient Retrofitting | CoRE (Hardial Bhogul) | Local/Open | Outline | Submitted | 0 | 0 | 0 | March | N
The Low Carbon Business Evolution Programme (sben) | Staffs CC (Di Roberts) | Local/Open | Outline | Submitted | 1117383 | 670430 | 446953 | March | Y
Smart Measures in Local Enterprise (SMILE) | Ngage Solutions | ? |  |  | 0 | 0 | 0 |  | N
Four Ashes Direct Wire & District Heat Network | Staffordshire County Council | ? |  |  | 0 | 0 | 0 |  | N
Built Environment Climate Change Innovations (BECCI) | University of Wolverhampton | ? |  |  | 0 | 0 | 0 |  | N
National Forest Sustainable Growth | National Forest Company | ? |  |  | 0 | 0 | 0 |  | N
Staffordshire & Potteries Incubator for Community Energy (SPICE) | Sharenergy Cooperative Ltd | ? |  |  | 0 | 0 | 0 |  | N
Staffordshire Energy Savers | UKSS Renewable Energy Services Ltd | ? |  |  | 0 | 0 | 0 |  | N
Watts not Waste for Stoke & Staffordshire | EON Energy Solutions | ? |  |  | 0 | 0 | 0 |  | N
TOTAL |  |  |  |  | 13617383 | 8170430 | 5446953 |  | OK
Priority 5 - Environment & Resources Efficiency
IMPRESS | International Synergies | ? |  |  | 0 | 0 | 0 | July | N
Trent Urban Land Improvement Project (TULIP) | Stoke on Trent City Council | ? |  |  | 0 | 0 | 0 | October | N
TOTAL |  |  |  |  | 0 | 0 | 0 |  | OK
Priority 6 - ERDF & ESF Technical Assistance
Capacity Proposal # 1
ERDF composite proposal (incorporating LA, LEP, & HE sector capacity proposals) | Stoke CC (Kate Round/Nigel Senior) | National | Outline | Submitted | 992103 | 595262 | 396841 | March | N/A
ESF composite proposal (incorporating LA, FE & VCSE sector capacity proposals) | Stoke CC (Kate Round/Nigel Senior) | National | Outline | Submitted | 831603 | 498962 | 332641 | March | N/A
TOTAL |  |  |  |  | 1823706 | 1094224 | 729482 |  | OK
OVERALL TOTAL |  |  |  |  | 197542438 | 56928002 | 140614436
Key:
Round 1 bids
Round 2 bids |  |  | Round 2 bids | Round 2 bids
Note on F18: Broad, John (People): What is the Total value of the project? TBC