## 2018-19 Dashboard FINAL OUTTURN
2018/19 FINAL OUTTURN - Key Stoke on Trent & Staffordshire Local Enterprise Partnership Funding Streams Headline Summary
|  | In Delivery | Scheme Completed | Contracting
General Commentary
LGD - At Final Outturn, £9.851m (73%) of total LGF Grant was spent against the total £13.444m 2018-19 LGF funding available. £1.433m of LGF Grant slippage has been utilised to fund SWAR on SCC's Capital Programme & £2.16m has again been carried forward to fund the remaining 2 years
of the LGD Programme.The £2.86m LGF Grant balance arising from the withdrawal of funding for certain LGD2 Rnd schemes has been reassigned to 4 new projects from the LEP's project pipeline. The Funding Agreements are now progressing & are expecting to be finalised in early 19-20.
LGF Grant - Total Local Growth Deal (LGD) funding is £98.275m. Of this sum, £76.56m (77.9%) has now cumulatively been spent up to and including 18/19, leaving a balance of £21.715m (22.1%) in LGD funding yet to be invested by 2020/21 against approved schemes.
City Deal & Growth Hub Grant - At Outturn, £4.013m or 90% of the £4.445m City Deal reprofiled spend has been spent to date. The Keele SEND scheme has spent to its quarterly profile whilst the DHN has claimed £2.388m of its total planned 2018/19 City Deal spend
with funding slippage of £0.432m now carried forward into future years. The Growth Hub Unit has now claimed and banked its 4th and final quarterly claim to give a total of £0.205m in grant allocation.
ESIF – ERDF & ESF committed funding stands at £116m or 75% of allocation. FOREX exchange rate adjustment has provided a further £12.5m ERDF. The total ERDF allocation now stands at £90.9m. The last call yielded 4 bids totalling £11m in grant request leaving almost £18m
to be allocated in the final bidding call in Summer 2019. ERDF claimed to date now stands at almost £35m against the N+3 target of £38.6m (as @ Dec 18). For ESF an expression of interest for a 2nd phase ESFA Opt In for 2 years from April 19 & 2nd Phase ESF Opt In for BWP & Big
Lottery is expected to soon follow. Contracting of ESF Open Call for Skills Hub & Higher Skills Progs is progressing and a second call is planned for Summer 2019. Together this will result in the full commitment of ESF funding (£64.3m)
GPF - Approved commitments = £14.2m (11 loans & 3 grants). The GPF cashflow currently holds a balance of £0.479m for future loans following the recent Open Call. 1 new Stage 1 GPF loan application has recently been Panel approved and is now progressing to contracting.
Core & Capacity Grant - At Final Outturn, total grant spend equated to £0.551m or 86.3% of the £0.613m total 2018-19 grant allocation (incl. the £113k 2017/18 grant carry forward) with £0.084m carried forward in to 2019-20 to fund on-going spend LEP Delivery Team commitments.
2015/16 Revenue Grant Funding = £250,000 +£3,050 c/fwd from 2014/15 Grant