## LGD1,2 & 3 Q1 19-20
APPENDIX C
2019-20 Local Growth Deals 1- 3 Annual & Quarterly Spend Profiles
2018/19 Quarterly Spend Profile & Actuals
Scheme / Project | April 2019 Approved Allocation | LGF Grant Allocation 2019/20 | Q1 2019/20 | Q1 2019/20 Actual | Q2 2019/20 | Q2 2019/20 Actual | Q3 2019/20 | Q3 2019/20 Actual | Q4 2019-20 | Q4 2019/20 Actual | Total 2019/20 Budget Profile | Total 2019/20 Actuals | 2020/21
Local Growth Deal 1 | £m |  | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m
LTB - Etruria Valley (SoTCC) | 8.2 | 8.2 |  |  |  |  | 3.5 |  | 3.12 |  | 6.62 | 0 | 1.58
Local Growth Deal 2
Town & City Centre Development Programme
Tamworth Enterprise Quarter | 0.11 | 0.11 |  |  | 0.055 |  | 0.055 |  |  |  | 0.11 | 0
City Centre Access (SoTCC) | 1.689 | 0.83 | [6 empty] | 0.83 |  | 0.83 | 0 | 0.859
Churnet Works Small Business Units | 0.5 | 0.5 | [8 empty] | 0 | 0 | 0
Local Growth Deal 3
City East Link Road (SoTCC) | 8.58 | 3 | 0 |  | 0.867 |  | 0.597 |  | 1.536 |  | 3 | 0 | 5.58
Spode Church Street - Phase 2 (SoTCC) | 0.5 | 0.5 |  |  |  |  | 0.205 |  | 0.295 |  | 0.5 | 0
Local Sustainable Transport Programme (SoTCC) | 0.9861 | 0.3 | 0.005 | 0.012254 | 0.17 |  | 0.025 |  | 0.1 |  | 0.3 | 0.012254 | 0.6861
Skills Capital Equipment Fund | 0.383 | 0.383 | 0.383 | 0.37843 | [6 empty] | 0.383 | 0.37843
New Local Growth Deal Schemes/Projects
Victoria Ground (Phase 2) | 1.4 | 1.4 |  |  | 0.27 |  | 0.71 |  | 0.33 |  | 1.31 | 0 | 0.09
Power Upgrade to Stoke Railway Station | 0.1 | 0.1 |  |  |  |  | 0.06 |  | 0.04 |  | 0.1 | 0
Stafford Station Gateway Land Purchase | 0.15 | 0.15 | [6 empty] | 0.15 |  | 0.15 | 0
Blythe Park Extension Infrastructure Project | 1.25 | 1.25 |  |  |  |  | 1.25 |  |  |  | 1.25 | 0
Cannock Chase and Silverdale Enterprise Centres | 0.26 | 0.26 | [8 empty] | 0.26
Stoke Flood Aleviation Scheme | 1.2 | 1.2 | [8 empty] | 1.2 | 0
Totals | 25.3081 | 18.183 | 0.388 | 0.39068 | 1.362 | 0 | 6.402 | 0 | 6.401 | 0 | 16.013 | 0.39068 | 8.7951
[7 empty] | Annual Local Growth Fund Allocations |  |  |  | 9.961 | 9.961 | 15.347
[7 empty] | (Over) or Underspend of LGF Grant Allocation |  |  |  | -6.052 | 9.5703 | 6.5519
[11 empty] | STD/Grant | 3.922%
Q1 2019/20
1.)
2.)
3.)
4.)
5.)
Q2 2019/20
Q3 2019/20
Q4 2019/20 PROVISIONAL
FINAL 2019/20
£0.5m unallocated - Churnet Works have withdrawn
Note on L12: Broad, John (F&R): £110k split 50:50 between Q2 & Q3 until full spend plan has been agreed by TBC in mid June.
Note on J13: Broad, John (F&R): CCA profile is deferred at this stage (Q1). Now likely to be set at Q2
Note on O14: Broad, John (F&R): Project change of request now expected to be submitted, so deferred LGF Grant allocation to 2020-21.
Note on E20: Broad, John (F&R): SoT College 1st claim (£80,281.86); 2nd claim (£114,854.61); Stoke College 3rd Claim (£183,291.44)

## City Deal Q1 19-20 (hidden)
City Deal Schemes 2019/20 Quarterly Spend Profiles
2018/19 Quarterly Spend Profile & Actuals
Scheme / Project | April 2019 Approved Allocation | Q1 2019/20 | Q1 2019/20 Actual | Q2 2019/20 | Q2 2019/20 Actual | Q3 2019/20 | Q3 2019/20 Actual | Q4 2019-20 | Q4 2019/20 Actual | Total Budget | Total 2019/20 Actuals | 2020/21 | Control totals
City Deal |  | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m
Stoke District Heat Network | 8.817 | 0.958 | 0.29285 | 0.843 |  | 0.879 |  | 0.843 |  | 3.523 | 0.29285 | 4.84 | 13.657
Keele SMART Energy Network Demonstrator | 1.7 | 0.7 | 0.7 | 0.4 |  | 0.3 |  | 0.3 |  | 1.7 | 0.7 |  | 1.7
Local Growth Deal |  | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m | £m
Etruria Valley (DfT Retained Scheme) | 17.525 |  |  |  |  | 2.509 |  |  |  | 2.509 | 0 | 15.016 | 32.541
Note:
This profile is based on the without Public Inquiry scenario. If the project were to be the subject of a Public Inquiry then the start date on site date would be pushed back by approcimately 18 months dpending on the number of landowners
The 'With Public Inquiry' profile would be:
2018/19 | £0m
2019/20 | £7.854m
2020/21 | £10.646m
Total | £18.500m
Notes:
Q1 2019/20
1.)
2.)