## Sheet1
Lessons Learned Project Name: Keele University Science & Business Park Smart Innovation Hub / IC6 Project
I.D. | Category | Observation | Lesson | Recommendation
Example | E.g:Initiation, Planning, Legal, Finance, Risk management, Communications etc | What worked well? What didn’t go so well or caused issues or delays? | Why did it work well/not go well? What could be learned from this? | What could be put in place on future projects of this type to ensure beneficial activities are noted and included, or to suggest preventative activities to avoid these issues or delays from happening again?
Governance | Risk Management | The Project Executive Group (PEG) governance model that is widely used on projects delivered by the university was a single point of focus for all elements of the delivery to be scrutinised, challenged, supported at all stages of the delivery | It is a proven model that has worked well for us on other projects and provides a full audit trail of evidence of discussions, decisions, and ultimately the PEG is the unit that is responsible for the compliant delivery of the project. | Having a group that is ultimately responsible also means having members of that group at a level that is senior enough to enact the required high level decisions - e.g. Deputy Vice-Chancellor.
Risk Register | Risk Management | A 9 level of risk Risk Register was produced to monitor any potential risks, actual occurring risks, future impact risks. This included an 'untreated' risk and residual risk scoring. | Clear colour coded visual document that was easy to present and digest at group meetings | A Risk Register is an essential document for any major capital project
Funding Management | Finance | The capital funding came from 5 separate sources, all of which needed to be managed via reports and draw down of funds against invoices. | Having a dedicated resource within the Operational Support Unit meant that the requirements of the funders, transactions, etc, could all be meshed in with the University's existing financial procedures, while remaining compliant to any funding requirements. | A project of this size and complexity should not be handled as just another part of the institution's daily operations; meaning that a dedicated team / resource is essential for the smooth operation and monitoring / reporting.
Construction | Delivery | As well as having a main contractor to deliver the physical building work, employing external QS consultants gave a level of expertise and control that was conducted along side the institution's own monitoring and PM activities. | Having all of the relevant expertise (internal and external) on hand throughout the whole planning and construction process is essential on a project of this size, value and complexity | A project of this standing is subject to many detailed regulations, compliance issues, etc and so all areas need to have specialist (independent) advice available to them, to ensure full adherence at every stage of the process. All advisors need to be fully certified in their area of expertise, and provide evidence of such.
Project Level Organisational Groups | Communications | Due to the various work streams moving within differing timeframes, and with specific responsibilities, a number of sub groups - Project Level Organisational Groups were set up to allow a 'deep dive' in to the granularity of each element, that would then feed in to a higher level Management Level Organisational Group, and ultimately in to the governance group. | Having a number of sub-groups that had detailed communications around specific elements allowed for granular level reporting, and a mechanism that was then able to feed in the 'headline' points to an over arching Management Project Organisational Group(POG), which in turn could then distil down the key points for reporting in to PEG governance. This enabled the retention of important detailed information, but prevented the more strategic groups becoming bogged down in the operational day to day activities. | A dedicated team, with no distractions of the day to day main core business (in the case of a university - educating students) that fully understands the funding process and requirements for compliance, is a must for a project of this size and complexity.
Previous Capital & Revenue Project Experience | Delivery | Keele University has previous experience of delivering both capital and revenue projects that have involved multiple source funding. These have included new buildings and business support programmes, aimed at adding value to the local LEP area. | Taking on this size of project without the experiences and lessons learned from previous projects would have been much more difficult to manage and deliver on time and within budget, while also ensuring funders and stakeholders were kept fully informed. The key lesson is that there is no substitute for experience, and a team with the relevant knowledge and skill-set are essential in delivering a project of this complex nature. | Make sure that experienced staff are in place for all positions. This should include a full understanding of the various compliance requirements.
Operational Support Unit | Monitoring & Compliance | A dedicated team are in place at Keele to support the various funded projects that are taking place across the university. This team focus on the monitoring and compliance (including financial reporting) of all of the projects, and helps them to both comply with requirements (e.g. of funders) and liaises with external partners. It also works with the institution's own processes and procedures to ensure a smooth meshing of systems. | Due to the complexity of having funding from various sources, with differing conditions attached to each, a team with the specific knowledge of compliance and reporting procedures, that is dedicated to working solely on projects, is essential. It enables project delivery staff to concentrate on their deadlines and metrics, while the 'back-office' requirements are being monitored separately. | Having a team in place that looks after 'back-office' monitoring and compliance, allows the delivery team to concentrate on getting the building completed and producing outputs.
Stakeholder Management | Communications | With a medium to long term project like this, involving a lengthy construction period, there is a need to manage communications to both internal and external stakeholders. This could be managing the expectations of funders and producing timely reports, through to ensuring that all internal teams are aware of progress, obligations and requirements. | We found that having dedicated project teams, with an intensive knowledge of the granularity of the project meant that we were able to access the specific information required by each stakeholder / funder, and produce reports accordingly. Also, having a dedicated marketing resource meant that we were able to control how and when information was disseminated and ensure that all compliance (logos, statements, etc) were complied with. Leaving this type of communication to general staff carries a serious risk of falling foul of compliance requirements, which can have a direct financial implication. | Controlling communications (external and internal) on a longer term project is important, to ensure that the right message is presented at the right time, to the right audience. Having a dedicated project resource, with a full understanding of the comms plan, is recommended.
Procurement Contracts | Procurement | The high value and complexity of the various procurements, coupled with the high impact risks of any non-compliance, called for a procurement team with specific knowledge of capital construction projects as well as compliant procurement processes, including OJEU and sub OJEU tenders. | Ensure that this team are in place and ready to act in good time, before any contracts need to be awarded and work needs to commence. Lead times for high value tender procurements are long and complex, and if staff are not in situ in good time, placing compliant contracts / orders can be delayed. | Having a procurement team with the specific knowledge of tenders, processes, procedures, compliance is absolutely essential on this type of project, especially with the values involved. Not having experienced staff in these positions is a serious financial risk to the deliverer, with potential non-compliance and claw-back being a key factor.
Module' Responsibility | Comms & Delivery | By having 'modular' teams - planning, procurement, capital delivery, revenue delivery, operational support, it enables very detailed, specialist knowledge to be brought to bear on the specific elements of the overall larger project | This allowed specialist teams to focus on very specific elements of the project, without needing to become 'bogged down' with areas that were not directly relevant to them. | This allows for granular levels of detail across specific areas, but needs a system in place where this granularity can be distilled down in to more concise, strategic points for upward reporting