## Risk summary
Risks to be escalated to SSLEP Company Executive Board Risks for which the Company Executive Board is the owner, or Risks which by their nature or severity are to be escalated to the Board. |  |  |  |  | 2020-02-01 | CONFIDENTIAL
Risk ID | Risk area | Risk Statement | Risk owner | Current/net risk level | Risk actions (mitigations) | Action owner | Action progress
Strategic 2 | LEP governance | The LEP review required all LEPs to review their functioning economic geographies, removing overlaps and confusion over accountability and responsibility on leadership & priority-setting. LEPs submitted details of their proposed future geographies by end of September 2018. The delay in government confirming future geographies is impacting upon confirmation of £300k Core Funding for 2018/19 & 2019/20. This funding is allocated against delivering the LEP Review, including move to incorporated status & increasing capacity in the team in order to be 'fit' for future investment. | Executive Board |  | Chair to maintain engagement with government on progress, most recently (3 February) in notifying govt of company formation which aligns with current LEP geography i.e. county boundaries and (4 April) in agreeing to revisit opportunity for local resolution with GBSLEP. Executive Board to discuss once geographies determined. | Chair/Interim Partnership Manager | BEIS has reported that Minister will now determine geographies. 03/04/19 Minister asked LEPs to revisit opportunity to reach agreement locally & meet with him in May to review. The most recent date that Acting Chair has liaised with govt was by letter to BEIS & MHCLG in October 2019. Govt has requested a further position statement on local resolution by 12 Dec 2019. All District Council partners agreed to become Board Directors/Alternates in June 2019, although, as of 4 Dec 2019 Cannock Chase DC has written to former Ministers (Berry & Nahawi) stating a preference to be included in GBSLEP only. A further letter has been received from Ministers (Berry & Nahawi) requesting that LEPs make a further attempt at local resolution and report back by 27 February 2020. A meeting took place between SSLEP and GBSLEP & WLEP Chairs on 19 February 2020.
Strategic 3 | LEP governance | LEP Partnership Manager is retiring at end of December 2018 and 3 staff on temporary contracts which finish between May & July 2019. Outcome of LEP Review is still emerging, making it imprudent to recruit now for new LEP Director. Potential gap creates difficulties in delivering in a timely manner on LEP Review and wider LEP work programme. | Executive Board |  | Interim Partnership Manager put in place 3 December 2018 enabling handover. Governance review, including move to incorporated body and review of secretariat requirements has been undertaken. JD for recruitment of Chief Executive Officer has been agreed by the new LEP Chair. | LEP Chair/Interim Partnership Manager | Option to retain Interim Partnership Manager until end of March 2020 has been put in place by SCC. Work to review resources and future secretariat requirements was completed. Future team was agreed by Board on 18 July 2019 however the lack of partner support to resource the required team presents the most significant risk to the partnership. Partnership Manager is realigning existing resources to support new team requirements where possible & seeking new funding partner arrangements. New Independent Technical Appraisers, a new Programme Manager, the LEP Strategy & Research Officer, Business Engagement Officer (part funded by the Chambers of Commerce partner) and Project Officer are now in place. The Interim Partnership Manager is now progressing the PR and marketing support.
Strategic 4 | LEP governance | Partnership decisions are not made in a timely manner causing delays in the ability of the LEP to: respond to threats to project delivery timetables, creating slippage on programme delivery profiles; and act upon opportunities to increase resources to the partnership. | Executive Board |  | The agreed scheme of delegation operates within a clear reporting framework, ensuring decision-making is transparent and accountable. | All Sub Group Chairs | A revised Scheme of Delegation was approved at the 18 July Board meeting. Sub-Groups review has commenced: revised ToR for Skills Advisory Panel approved 18 July; Programme Assurance Group and Strategic Programme Management Group currently completed subject to sign off of new ToR for SPMG. PAG to be discontinued once new SPMG is functional. Operational sub group chairs were agreed in December and revised ToRs were agreed by February Board.
Strategic 5 | LEP governance | Loss of Executive Board knowledge due to several private sector board members potentially due to rotate in July 2019 | Executive Board |  | The LEP Review will require four further private sector board members to be added to the board in order to achieve the required private-public balance. The timing of this will further assist in 'staggering' the rotation dates of board members. | Interim Partnership Manager | New Board Member Skills and Experience discussed at 18 July 2019 Board. Advert for new Board Members was issued in September 2019 with a good return. Four new Board Members are now in place . and the recruitment of the new Chair is complete. as this was an internal appointment, one further private sector board Director's place remains under active recruitment and will be filled as soon as possible.
Strategic 6 | LEP strategy | Delay in receipt of additional £300k Core Funding for 2018/19 & 2019/20 (see Risk ID 2) means that LEP is undertaking work at risk in order to develop the Local Industrial Strategy (LIS) by Government's timetable of December 2019. Any delay in LIS production could impact upon ability to access forthcoming funding incl. UK Shared Prosperity Funds. If the additional Core funds do not arrive in a timely fashion, LEP will need to find funding and resources from else where. | Executive Board |  | See Risk ID2 resolution lies in the hands of government/SoS. | LEP Chair/Interim Partnership Manager | See Risk ID2 Response to all LEPs required Partnerships to provide position statement on local resolution of geographies issue by 12 December 2019 and now a further position statement by 28 February 2020. Local resolution at this stage would only release £100k. Local Resolution is not possible in SSLEP's case so all funding is likely to be lost. New govt (post election) will determine outcome and any further penalties for non-compliance. LEP Core budget has been protected for use against the LIS (which is essential to drawing down of future funds) which has led to further delay in the staff recruitment due to lack of funds.
Strategic 7 | LEP strategy | New governments bring new policy positions, initiatives & delivery mechanisms. Ministers are considering a range of policy options & papers (e.g. Rising Tides). LEPs are vulnerable to the outcomes and this inability to move/lack of self-determination presents a unique risk for the company and limits the ability to plan for the future. | Executive Board |  | The Chair and Board Members are engaging in local regional and national discussions on future policy and delivery mechanisms The LEP is supporting the LEP Network in work being undertaken to demonstrate the added value from LEPs. SSLEP has been transforming itself in terms of its governance, systems ,processes and the capacity & capability of its Board and Secretariat to demonstrate readiness for the next phase of delivery of the government's economic growth agenda. | Executive Board | The LEP has completed 21 of the work action areas within its Improvement Plan. Of the 4 remaining areas, most work has been completed and in most instances, the minor remaining actions are underway. Two key areas of activity underway but not yet completed are the recruitment of the CEO and development of the new Communications Plan. CLGU briefing with Partnership Manager on 11/03/2020 stated that Budget 2020 includes a central role for LEPs on delivery of the government's "levelling up" agenda.
Strategic 8 | SSLEP delivery | Recruitment of CEO – there is a risk that the CEO will not have been appointed before the Interim Partnerships Manager completes her contract, or that there will not be enough time for an effective handover. | Executive Board |  | The Interim Partnership Manager is now taking the CEO post through job evaluation in order to set the appropriate salary. Job evaluation takes 20 working day after which Union agreement is required and then a recruitment process | Executive Board | Consider potential to extend interim Partnership Manager contract or alternative arrangements in the event of delays in appointing CEO.
Strategic 9 | SSLEP delivery | COVID 19 Coronavirus - impact on resources and programme delivery; impact on economy. | Executive Board |  | Note Government advice re mitigations. Government process to mitigate against impact on the economy. Internally: apply remote working practices and other government advice to ensure continued working of SSLEP secretariat |  | Monitor
CDGD 13 | Delivery of major projects | (Risk 13 has been Merged with Risk 6, which has been closed) There is a risk of impact from Economic and Political trends which are beyond the control of the SSLEP. Brexit, national elections, general downturn in the economy could all impact negatively on the schemes within the programme. Programmes could slow or stall as a result of any of these external factors, which would have the affect of the programme not meeting its 2021 agreed targets | CDGD SPMG |  | Keep abreast of political and economic trends. Identify schemes that could deliver housing benefits Review existing housing schemes forecast Lobby key stakeholders to bring forward housing schemes Working relationship with Homes England Have a balanced portfolio, introducing a number of smaller schemes | Jacqui Casey | Regular reviews are undertaken at SPMG Outcomes dashboard is produced to highlight any potential areas of concern at an early stage. Open call and subsequent pipeline prioritised on shovel ready schemes capable of delivering housing and/or jobs within LGF timescale. Action to add, on survey of Housing Approvals. Tightening of future funding agreements re timings and clawback will help to mitigate. Revised funding agreement drafted by Legal. Close links are maintained with BEIS
CDGD 18 | LGF Funding | As a result of assigned schemes delivery timescales slipping, there is a possibility that the CDGD planned investment will not be achieved by March 2021, which would have the affect of the LEP failing to deliver its agreed Growth Deal objectives, leading to reputational impact and jeopardising future investment | CDGD SPMG |  | Quarterly grant spend profiling in place for all CDGD projects. Early identification of current pipeline projects to alternatively fund from grant slippage | Simon Ablewhite | Quarterly spend reporting to the Audit & Finance Group and the LEP Executive Board to highlight potential scheme/project slippage risks against the current CDGD Delivery Programme Funding from withdrawn schemes has been reallocated . Funding agreements for high risk schemes which are due to commence and complete in year 2020/21 include monitoring plans linked to financial penalties. An additional funding agreement has been contracted to mitigate against further slippage or failure.
CDGD 21 | Programme/ Reputation | Based on current outputs estimates, there is a risk that the SSLEP may not achieve its housing output targets of 1000 houses by March 2021. This could result in reputational damage and could impact on future funding allocation from central government. | CDGD SPMG |  | An Outputs report/position statement and recommendations has been taken to PAG 27/08/19, and is subsequently to be taken to Executive Board. (Review pipeline, open call). | SA/SP | Paper taken to Board on 19/19/2019. Board requested that Notice letters are to be sent to lagging schemes, giving deadlines for position statements/progress reports these were brought to the Board (Oct/Nov 2019). Quarterly output reporting is taken to Audit & Finance Group, SPMG and Executive Board. Forecasts are revised annually in Q1 - a deep dive into forecasting will take place April 2020
CDGD 22 | Programme/ Reputation | There is a risk that 4 schemes (2 of which are very large) in the current programme may not spend their grant allocation by the deadline of March 2021. This could severely impact on the LEP's ability to spend the LGF grant and to attain the required outputs. | CDGD PAG |  | An Outputs report/position statement and recommendations has been taken to PAG 27/08/19, and is subsequently to be taken to Executive Board on 19/09/19. (Review pipeline, open call). | SA/SP | Churnet Works has now withdrawn (21/08/19). CCAP - Notice letter sent 27/09/19. Response letter received from SoTCC, (Exec Board agenda for 17/10/19) provided reassurance that spend/delivery targets could be met. Spend is due to recommence in Q4 19/20 CELR business case was approved by Exec Board subject to T&C's and Monitoring Plan including penalty milestones - these have been contracted . Funding agreement now signed - Etruria brought a report to Exec Board on 21/11/19. All elements of the business case have been submitted to DfT - awaiting outcome of business appraisal by DfT.
GPF | Programme delivery | Liquidation of Pochin as builders appointed for Hilton Garden hotel development part funded via GPF grant means project remains dormant / not completed | GPF Steering Group |  | Legal maintaining dialogue with Stoke City Council and their legal representation. | GPF | Legal ensuring mitigation measures in place. Letter re Revised Funding Conditions was brought to Executive Board 17/10/19. Extension to practical completion date approved to May 2020.

## Project RAG rating
PROJECT - overall RAG rating of scheme | Deliverables | Finances | Reputation | RAG Rating PREVIOUS Q2 19/20 | RAG Rating Q3 19/20 | Change to overall risk level in Q3
Lichfield Park | 3 | 1 | 2 | AG | AG
Meaford | 3 | 1 | 2 | AG | AG
Bericote Four Ashes | 2 | 1 | 1 | AG | AG
Stafford Western Access Route | 3 | 1 | 2 | A | AG
Etruria Valley | 4 | 4 | 4 | AR | AR
LSTP (SoTCC & SCC) | 1 | 1 | 2 | AG | AG
Branston Locks | 2 | 1 | 1 | AG | AG
Advanced Manufacturing Skills Hub - South Staffordshire College |  |  |  | Closed | Closed
Advanced Manufacturing Skills Hub - Stafford College |  |  |  | Closed | Closed
Advanced Manufacturing Skills Hub - JCB Academy |  |  |  | Closed | Closed
Tamworth Enterprise Quarter | 1 | 1 | 1 | G | G
Leek Mill Heritage Quarter |  |  |  | Withdrawn | Withdrawn
Rugeley Town Centre | 2 | 1 | 1 | AG | AG
Friarsgate, Lichfield |  |  |  | Withdrawn | Withdrawn
Economic Regeneration Programme | 1 | 1 | 1 | G | G
ROF Featherstone | 1 | 1 | 1 | G | G
Chatterley Valley West Site Access | 1 | 1 | 1 | G | G
Redhill Business Park | 1 | 1 | 1 | G | G
Keele Innovation Centre No.5 (IC5) | 1 | 1 | 1 | G | G
I54 South Staffordshire Employment Site | 1 | 1 | 1 | G | G
Lichfield Southern Bypass Phase 3 | 1 | 1 | 1 | G | G
Bericote Four Ashes Phase 2 | 1 | 1 | 1 | G | G
City East Link Road (formerly Hanley - Bentilee Link) | 3 | 3 | 3 | A | A
Spode Works | 1 | 1 | 1 | G | G
ROF Featherstone - Strategic Employment Site |  |  |  | Withdrawn | Withdrawn
Keele Smart Innovation Hub | 1 | 1 | 1 | G | G
Skills Capital Equipment Fund | 1 | 1 | 1 | G | G
City Centre Access | 2 | 2 | 1 | AG | AG
Churnet Works Small Business Units |  |  |  | Withdrawn | Withdrawn
SME Expansion Support Programme | 1 | 1 | 1 | G | G
Stoke-on-Trent Railway Station Power Upgrade | 2 | 1 | 1 | AG | AG
Victoria Ground (Phase 2) | 1 | 1 | 1 | G | G
Blythe Park Extension Infrastructure Project | 1 | 3 | 1 | A | AG
Stafford Gateway Strategic Land Acquisition | 3 | 1 | 1 | AG | AG