## 2020-21 SSLEP Dashboard
Stoke on Trent & Staffordshire Local Enterprise Partnership Finance Dashboard - 2nd Quarter Outturn 20-21
LEP CAPITAL FUNDING | [9 empty] | LEP REVENUE & CAPITAL INVESTMENT FUNDING |  |  |  | LEP REVENUE GRANT FUNDING
| The Local Growth Deal, The City Deal & Getting Building Fund - Headlines | [9 empty] | The Growing Places Fund (GPF) - Grants & Loans Facility
[5 empty] | Total Grant Allocation (£m) |  | Spend to Date (£m) | % Spend To Date | Funding Remaining (£m) |  | * Since 2013-14, 3 grants totalling £7.855m in value, plus 14 GPF loans totalling £6.543m have been awarded by SSLEP to local SMEs - a £14.398m total investment to date which has
|  |  | Local Growth Deal |  | 98.275 |  | 82.9299 | 84.39% | 15.3451 |  | leveraged in over £79.43m of Private Sector Investment in to the local economy over a 7 year period.
(Total Funding & Spend as @ 31st March 20)
* As at Q2 2020, after taking into account all outstanding contractual loan payments and repayments the GPF Loans Fund currently holds an available 'rolling' fund balance of £2.921m.
|  |  | 20-21 LGF Grant Allocation |  | 24.398 |  | 13.5778 | 55.65% | 10.8202
|  |  | (as @ Q2 20-21) | [7 empty] | * As at the 30th Sept 2020, the total value of GPF loans currently outstanding, i.e. in circulation, is £3.078m. Of this sum, £0.450m of loan is expected to be repaid back into the GPF
Loans Fund during 20-21.
|  |  | The City Deal |  | 24.75 |  | 17.97 | 72.61% | 6.78
(Total Funding & Spend as @ 31st March 20)
|  |  | 20-21 City Deal Grant Allocation |  | 4.13 |  | 1.3931 | 33.73% | 2.7369
(as @ Q2 20-21)
|  |  | Getting Building Fund |  | 23.7 |  | 0 | 0% | 23.7
(as @ Q2 20-21)
The Local Growth Deal (Local Growth Fund Grant)
* All LGD funding has to be spent by 31st March 21. The one exception to 'this rule' is the £18.5m Etruria Valley DfT Retained scheme which has been permitted to spend its LFG Grant funding beyond the set LGD deadline
following DfT approval of its final business case. The SSLEP's LGF Grant funding over the 6 year LGD programme has therefore increased to £116.775m in total.
* Following a review of the SSLEP's Local Growth Deal Q1 spend & risks by the Cities & Local Growth Unit, BEIS has confirmed that they are shortly to release the remaining 1/3rd of this year's LGF grant funding of £5.115m.
The 2020-21 SSLEP Core Budget - £0.730m : £0.141m or 19.25% Spend to Date
* As at 30th Sept 2020, the SSLEP has contractual committed 98.6% of the total £98.3m original LGD funding and currently has 2 LGD Grant Funding Agreements that are yet to be finalised with partners.
|  |  |  | LGD Programme | LGF Funding (£m) | Current Status of Funding Agreement | [8 empty] | * The annual Core Fund Grant of £0.5m is provided by the BEIS and is expected to be spent by 31st March 21. The 20-21 LEP Core budget of £0.730m was approved at
|  | Blythe Park Development |  | OPEN CALL | 1.25 | LGD Funding Agreement drafted – Currently waiting for the GPF Agreement to be finalised for the match funding before both Agreements are signed. | [8 empty] | the 27th February 20 SSLEP Executive Board.
|  | Stoke Power Upgrade |  | OPEN CALL | 0.1 | LGD Funding Agreement drafted – Currently waiting on finalised contract to be signed by all parties.
* At Q2 20-21, the Core Budget is currently anticipated to underspend by -£0.136m. The majority of this underspend is due to a reduced planned LIS development spend;
| * At Q2 20-21, a total of £13.578m in LGF Grant funding (56%) has, to date, been spent against the remaining balance of LGF Grant funding of £24.398m. At this stage, SSLEP remains 'on course' to fully spend its final year | [13 empty] | a Project Officer vacancy within the LEP Secretriat, plus minor underspends on both LEP Operational Costs (Board activities) & Business Engagement, offset by an
| LGD Grant funding allocation. Any LGD grant slippage arising against the current Programme will be utilised to fund the i54WE scheme to ensure the grant is spent at the year-end. | [13 empty] | increase in LEP Insurance premiums.
[18 empty] | Budget | Forecast | Variance
AMBER |  |  | The LGD Programme continues to have an overall AMBER RAG rating due to delays in the completion of the 2 remaining LGD Scheme Funding arising Agreements. Any LGF Grant slippage against the final | [14 empty] | £. | £. | £.
|  |  | year of the LGD Programme will be utilised to fund the i54 WE Scheme to ensure that the LGF Grant is fully spent in 20-21. | [12 empty] | Staffing - SSLEP Secretariat |  | 385108 | 345493.36 | -39614.64
[11 empty] | * A new 'Open Call' (Round 15) is now open and will close on the 9th October 20 for new SME loan bids up to a value of £0.280m. |  |  |  |  | LEP Operational Costs |  | 158250 | 137031.69 | -21218.31
| Getting Building Fund - A NEW £23.7m Grant Funding Stream | [14 empty] | Business Engagement & Support |  | 37500 | 32500 | -5000
[11 empty] | * There currently remains 3 SME Stage 1 GPF loan approvals, totalling £1.6m, awaiting finalisation of Stage 2 due diligence procedures and respective Funding Agreements (FA) before |  |  |  |  | Strategic Planning - LIS Development |  | 100000 | 30000 | -70000
| * The SSLEP has been successful in securing £23.7m of Getting Building Fund (GBF) to invest in 'shovel ready' schemes. This funding is expected to be paid as a S31 grant in September & is to be spent over the following | [9 empty] | GPF loan payments can be made. These are as follows: |  |  |  |  | Project & Programme Development |  | 49500 | 49500 | 0
| 18 months up to the 31st March 2022. Gov't has since now published both the grant's terms & conditions and has also confirmed that the annual grant spend profile is to be split 50% in 20-21 and 50% of funding in 21-22. i.e. | [14 empty] | Gross Expenditure |  | 730358 | 594525.05 | -135832.95
| £11.85m in each of the two financial years. | [9 empty] | - Blythe Properties Ltd = £1.40m (Specified loan funding conditions now met by the Company & Stage 2 Due Diligence completed - FA expected to be signed shortly & payment made.)
* This Core Fund Budget underspend will be transferred to the LEP General Reserve balance (£0.094m) at the year-end to support future Programme development.
| * The July 20 SPMG, following a shortlisting exercise coordinated & conducted by Hatch Regeneris, approved the 12 schemes, plus a further 7 contingency projects if any Stage 2 business case ere to be unsuccessful or | [9 empty] | - Dog & Bone Properties Ltd = £0.150m (Stalled due to Covid-19 implications at the applicant's request).
| GBF grant slippage were to arise over the 18 months of the Programme. The total cost of the GBF Programme is £90.262m. Of which, 74% is matched funding. | [12 empty] | GREEN |  | No issues arising - Any outturn underspend of the Core Budget will be caried forward on the LEP balance sheet to 21-22.
- Scott FM Ltd = £0.050m (Suspended due to Covid-19 implications at the applicant's request).
* Two GBF Business Cases - Innovation Centre 7 (£6.1m GBF) & Staffordshire University Health Innovation Centre (£2.890m GBF) have since been approved at the September 20 SPMG under delegated authority from
| the SSLEP Executive Board and are now progressing to full Funding Agreement. The Shire Hall Regeneration Project Business Case (at a total cost of £4.68m including a £1.6m GBF ask) is due to be presented at the | [8 empty] | GREEN |  | No issues arising - The 3 outstanding GPF loans are nearing Stage 2 completion and are expected to progress to Funding Agreements in the next quarter. |  |  | Annual Growth Hub Grant - £0.205m : £0.106m or 51.6% Spend to Date
| forthcoming 25th October SPMG. | [10 empty] | After taking in to account all outstanding contractual loan payments and repayments, the available 'rolling' GPF Loan Fund balance is £2.921m.
* This Grant is offered under Section 11 of the Industrial Development Act 1982 to support the further development of Growth Hubs to aligned to the Government's
AMBER |  |  | At this early stage, the GBF Programme currently has an overall AMBER RAG rating due to the tight timeframe to spend the grant & the timing of getting all Business Case approved & Funding Agreements in place. | [7 empty] | ESIF Funding - European Regional Development Fund (ERDF) & European Social Fund (ESF) |  | NO FURTHER UPDATE OF FIGURES AVAILABLE |  | commitment to ensure that businesses across regions have access to high quality advice & guidance via Growth Hubs & to further simplify access to Business support.
|  |  | Each of the approved GBF Grant funded projects and schemes are currently progressing their respective business cases for SSLEP Executive Board approval over the coming months. | [11 empty] | An annual Growth Hub Grant Spending Plan was approved by BEIS in March 20.
The City Deal
* The 20-21 Growth Hub Grant allocation is £0.205m & to date £0.106m of this sum has been claimed and received by Q2.
[14 empty] | GREEN |  | No issues arising.
Supplementary 'One Off' Growth Hub Grant - £0.331m : £0.184m or 55.4% Spend to Date
* To further support LEP Growth Hubs, this 'one off' revenue grant is to provide additional capacity to ensure businesses have access to high quality free and impartial advice
& guidance. In addition, the funding was awarded in recognition of immediate pressures faced by Growth Hubs in responding to the covid-19 pandemic.
* A Supplementary Growth Hub Grant Spending Plan was submitted by the Growth Hub on 18th June 2020 and approved by BEIS. The outline Spend Plan is as follows:
£.
[17 empty] | Employees - Additional Advisor Capacity |  | 228000
[17 empty] | Economic Growth Planning |  | 72000
[17 empty] | Growth Marketing Campaign |  | 20000
[17 empty] | Growth Market Plans |  | 11500
[17 empty] | Total Supplementary Grant Funding |  | 331500
| * At Q2 20-21, a total of £1.393m or 33.7% of this year's City Deal's profiled spend has now been spent. | [9 empty] | * As at Q2 20-21, £143.1m or 91.5% of the total ESIF Programme funding has, to date, been committed to projects with £107.33m or 75% of this total committed funding sum claimed to |  |  |  | * To date, at Q2, the Growth Hub has claimed and received £0.184m of this Supplementary Growth Hub Grant.
date. The ESIF Programme currently remains on target to commit its remaining theme allocations by the 31st March 21 and to have all grant claimed by 30th June 23.
* The Keele SMART Energy Network Demonstrator scheme has a final planned City Deal spend of £0.630m profiled for the year and has, to date, spent £0.576m or 91.4% of this funding at Q2 20-21.
[11 empty] | ERDF - European Regional Development Fund |  |  | GREEN |  | No issues arising.
| * The Stoke On Trent District Heat Network (DHN) has spent £0.817m (or 23.3%) of its planned £3.5m 20-21 City Deal profiled spend leaving a remaining balance of £2.65m of City Deal funding yet to be spent in 21-22. | [9 empty] | * The ERDF Programme remains at a high level of commitment of £83.4m or 92% of its total funding with many projects & programmes now contracted and 'in delivery'. In comparison,
the national average is c70% for ERDF commitments. The last ERDF Open Call yielded 27 new & extended bids seeking £22.5m in total. All but 3 of these applications are passing
GREEN |  |  | No immediate issues - Keele SEND is expected to spend its remaining balance of grant funding in 20-21. Whilst the DHN is expected to spend its remaining £2.65m balance of City Deal funding, | [7 empty] | through to the full application stage including extensions to the Growth Hub and Low Carbon Programmes, plus a new Information Technology Business Enhancement Programme. Keele |  |  |  | Peer Network (£0.405m) : £Nil Spend to Date
|  |  | plus, any unspent 20-21 City Deal funding allocation, post 20-21. | [7 empty] | University also featured strongly in the response to the call with bids for IC7 and extensions to SEND and Business Bridge Programmes. Decisions on these bids at the full
[11 empty] | application stage are expected throughout Autumn 2020. |  |  |  | * The SSLEP has been successful in securing £0.405m of 'one off' Peer Network funding which it is planned to involve up to 250+ SME participants and it is expected that
| CVEZ Enterprise Zone Investment (18-19 to date) |  |  |  |  | * Key Risks include the pace of delivery; road infrastructure may not accommodate predicted CVEZ growth; Viability of sites may | [8 empty] | this work will be put out to contract. This funding stream will be claimed on a quarterly basis, to a set timetable, following the recent signing of the BEIS Grant Funding
[6 empty] | be underestimated & significantly the potential impact of any delays to the delivery of the Etruria Valley Link Road. |  |  |  |  | * With ERDF grant commitment being high, grant spend or grant claimed is now a critical factor to retain the ERDF allocation in full although ERDF monies are now being re-prioritised due |  |  |  | Agreement. However, there has been a short delay, imposed by BEIS, in the releasing of this funding stream nationally to LEPs.
to the crisis. Updated programme management information is usually reported to each ESIF Committee providing the actual position each quarter. No ESIF Committees have been held
|  |  |  | Value (£m) |  | * Anticipated CVEZ Business Rates to be collected over 25 yrs is estimated at £118.69m. SOTCC is expecting to produce a |  |  |  |  | since Nov 2019, however, a written update was recently provided on 3rd August 20. This important role for LEP ESIF Committee is to continue to monitor spend to ensure contracted |  |  |  | * To date, none of this 'one off' grant funding has yet been committed but the SSLEP's Funding Agreement is now in place.
|  | Total Capital Expenditure |  | 4.852 |  | Business Rates surplus by 25-26 & for SCC / Newcastle-under-Lyme BC a surplus by 23-24 (Source - CVEZ SIP). |  |  |  |  | projects and programmes remain on profile
|  | Total Revenue Expenditure |  | 2.264 | [9 empty] | AMBER |  | BEIS have delayed the formal issuing of the grant to redraft the Funding Agreement. Potentially shortening the time for the LEP to spend this
|  | Interest Paid on Borrowings |  | 0.235 |  | * Anticipated CVEZ business rates uplift per annum is currently estimated at £5.644m with £3.029m of rates forecast to be |  |  |  |  | * Total ERDF & EAFRD claimed to date by applicants remains at £53.32m or 63.9% of the £83.38m total ERDF committed leaving £7.47m of funds yet to be fully committed in 20-21. |  |  |  |  | grant by the 31st March 2021 spend deadline initially set.
|  | Total Expenditure to Date |  | 7.351 |  | delivered by the end of 20-21.
|  | Less, Total Business Rates Income |  | -3.029 | [6 empty] | * Any remaining allocations after the full application stage will feature in a national ERDF reserve fund calls targeted at COVID response actions. Already allocations of £1.1m and £0.872m |  |  |  | The Skills Advisory Panel Grant (£0.075m) : £0.035m or 47.2% Spend to Date
|  | Deficit Balance (as @ 01-10-2020) |  | 4.322 |  | * Total forecast SIP CVEZ Capital Investment is estimated at £28.340m (incl. EV Link Road). Forecast 20-21 spend is estimated |  |  |  |  | has now been made available to the SSLEP area for the Reopening the High Streets Safely and SME Restart and Kickstarting Tourism programmes, and are being implemented.
[6 empty] | at £12.86m and prior year capital spend totalled £8.4m. |  |  |  |  | These allocations reflect the economic needs and challenges facing the SSLEP area as well as it’s EU Transitional Area status. The Reopening of the High Streets Safely funding has now |  |  |  | * In 20-21, the 2nd year of Skills Advisory Panel (SAP) funding, the Gov't approved a further £0.075m in SAP Grant funding to enable and encourage SAPs to continue to
|  | DRAFT Q2 20-21 Figures (subject to change) | [8 empty] | been fully claimed and paid to the District Authorities. To date, 600+ applications have, so far, been made in respects to the new SME Restart & Tourism Kick Start Programmes and are |  |  |  | increase its analytical capability; support the on-going development of the LIS; increase their local influence & their ability to address local skills challenges and to grasp
[6 empty] | * Total target CVEZ jobs when completed is is estimated at 7,328. Of which, 897 jobs (12.2%) have been delivered to date. |  |  |  |  | currently being evaluated by the LEP's Growth Hub. |  |  |  | local skills opportunities.
[6 empty] | * Total CVEZ floor space when completed is is estimated at 3,747,862 sq ft. Of which, 688,000 sq ft of floor space (or 18.3%) has |  |  |  |  | ESF - European Social Fund |  |  |  | * The SSLEP's SAP has now received its £0.075m SAP Grant from the DfE and is to be spent by 31 March 2021.
| I54 Enterprise Zone & Western Extension |  |  |  |  | been delivered to date. |  |  |  |  | * Of the £59.72m of ESF committed to date, 91.2% of the £65.48m total ESF allocation. £54m of this sum is to be delivered through 3 national 'Opt In' Programmes by the DWP; The Skills
[11 empty] | Funding Agency & the Big Lottery (Building Better Opportunities). In comparison, the national average is c70% for ESF commitments. Expressions of interest for a 2nd phase of |  |  |  | * A SAP Spend Plan has been agreed & set - £0.050m is to fund a SAP Analyst post & £0.025m has been allocated to Other Hired Services. Of which, £0.015m has been
| * The initial borrowing to deliver the i54 Western Extension EZ development, which is currently 80% occupied, is expected to be fully repaid by April 26. Following this date, all business rates attained will be utilised to repay the | [9 empty] | the ESF 'Opt In' Prog has been submitted. DWP & Big Lottery 'Opt In' applications are currently being processed. Any returned funds will go to the Reserve Fund but due to the COVID |  |  |  | spent on the purchase of the EMSI data. To date, £0.035m of this year's SAP Grant has been spent in total and is expected to be fully spent in year.
| £10m planned Investment that the LEP Exec Board has agreed to invest for the i54 Western Extension. To date, £3.537m this year's LGF Grant allocation slippage has been reassigned to the I54WE. | [9 empty] | pandemic, this has now been postponed indefinitely as gov't refocus their response post Covid.
GREEN |  |  | No issues arising for either the Ceramic Valleyor the i54 Western Extension Enerprise Zones | [6 empty] | GREEN |  | There is a 'high level of confidence' that the balance of ESIF funding remains 'on course' to meet the grant commitments deadline (31st March 21) & the grant |  | GREEN |  | No issues arising.
spend (30th June 23), subject to any Gov't national review of uncommitted ESIF Funding being undertaken to refocus financial resources on the pandemic.