## Overview (hidden)
SSLEP Programme Risk Management - April 2020
Key "Red" rated risk level activities
Risk area | Risk Statement | Risk actions (mitigations) | Action progress
Strategic 2 | LEP Geography Resolution | Chair to maintain engagement with government on progress, most recently (15 February) in notifying govt of company formation which aligns with current LEP geography ie county boundaries. Executive Board to discuss once geographies determined. | BEIS has reported that Minister will now determine geographies. 03/04/19 Minister asked LEPs to revisit opportunity to reach agreement locally & meet with him in May to review. The most recent date that Acting Chair has liaised with govt was by letter to BEIS & MHCLG in October 2019. Govt has requested a further position statement on local resolution by 12 Dec 2019. All District Council partners agreed to become Board Directors/Alternates in June 2019, although, as of 4 Dec 2019 Cannock Chase DC has written to former Ministers (Berry & Nahawi) stating a preference to be included in GBSLEP only. A further letter has been received from Ministers (Berry & Nahawi) requesting that LEPs make a further attempt at local resolution and report back by 27 February 2020. A meeting has been held between SSLEP and GBSLEP & WLEP Chairs on 19 February 2020 and resulted in a further letter send advising that local resolution was not possible. Ministerial response is now likely to be aligned with the publication of the Devolution White Paper however removal of overlaps continues to be govt policy.
Strategic 7 | In the light of the unprecedented Covid-19 crisis, its economic impacts and the requirement for an emergency package of support for business, the new Government must refocus to address new challenges through adoption of new policy positions, initiatives & delivery mechanisms. Ministers are considering a range of new policy options. LEPs are vulnerable to the policy outcomes and this inability to move/lack of self-determination presents a unique risk for the company and limits the ability to plan for the future. | The LEP is working with the LEP Network in articulating the added value from LEPs in supporting recovery planning, providing business expertise on how to remobilise supply chains and stimulate demand. Through its Annual Performance Review outcomes, SSLEP has verified its transformational improvements across governance, accountable systems & processes and the capacity & capability of its Board and Secretariat and, working together & using strengths of all partners, can demonstrate our readiness to take on the current challenges and deliver economic recovery & growth across SSLEP. | The LEP is continuing to strengthen its performance, through developing & delivering a new Improvement Plan for 20/21. The CEO recruitment and the development of the new Communications Plan are underway. The Chair & interim Partnership Manager contribute to recovery planning through weekly regional LEP meetings and feed into Network work directly and through the regional grouping. The SSLEP Covid Taskforce enables partners discussion & coordination on recovery, renewal & resilience work.
Strategic 8 | RECRUITMENT OF CEO (interim in place currently) | The Interim Partnership Manager is now taking the CEO post through job evaluation in order to set the appropriate salary. Job evaluation takes 20 working day after which Union agreement is required and then a recruitment process | Job evaluation has been completed. The Chair & CEO have undertaken investigations into the current market and preparations are underway to advertise the post. Approval to Consider potential to extend interim Partnership Manager contract or alternative arrangements in the event of delays in appointing CEO.
Strategic 9 | COVID 19 - impact resources /programme delivery / economy. | Note Government advice and mitigations. Government process to mitigate against impact on the economy. Internally: apply remote working proactices and other government advice to ensure contimued working of secretariat | SSLEP Secretariat has a business continuity plan in place and this is working well so far. The Programme Manager is assessing the impact upon current programme delivery ensuring that 20/21 spend profiles are as accurate as possible and keeping in touch with BEIS on key issues arising. At LEP Board of 19 March 2020, the LIS Implementation Sub Groups were charged with identifying immediate, short & medium term actions for inclusion in recovering planning. Data and intelligence is being gathered by the full range of LEP partners in order to ensure a detailed understanding of economic impacts are available in considering required actions.
CDGD 13 | Macroeconomic Impacts on Programmes Brexit Implications / Recession / COVID Impacts. Programmes could stall which would affect programmes not meeting its 2021 targets | Identify schemes that could deliver housing benefits Review existing housing schemes forecast Lobby key stakeholders to bring forward housing schemes Working relationship with Homes England Have a balanced portfolio, introducing a number of smaller schemes Local authority housing Community builds Non-traditional housing e.g. modular | Regular reviews are undertaken at SPMG. Outcomes dashboard is produced to highlight any potential areas of concern at an early stage. Open call prioritised on shovel ready schemes capable of delivering housing (and/or jobs) within LGF timescale. Action to add on survey of Housing Approvals. Tightening of future funding agreements re timings and clawback will help to mitigate. Revised funding agreement drafted by Legal. Close links are maintained with BEIS
CDGD 18 | CDGD Programme slippage missing Mar 2021 deadline - LEP missing Growth Deal Objective and reputational damage impacting future funding | Quarterly grant spend profiling in place for all CDGD projects. Early identification of current pipeline projects to alternatively fund from grant slippage | Quarterly spend reporting to the Audit & Finance Group and the LEP Executive Board to highlight potential scheme/project slippage risks against the current CDGD Delivery Programme Funding from withdrawn schemes has been reallocated . Funding agreements for high risk schemes which are due to commence and complete in year 2020/21 include monitoring plans linked to financial penalties. An additional funding agreement has been contracted to mitigate against further slippage or failure.
CDGD 21 | Jobs (5000) and Houses (10000) CDGD target by Mar 2021 could be missed. Reputational damage impacting future funding. Delays due to Covid increase this risk. | An Outputs report/position statement and recommendations has been prepared for PAG 27/08/19, and is subsequently to be taken to Executive Board. (Review pipeline, open call). | Paper taken to Board on 19/09/2019 Board requested that Notice letters are to be sent to lagging schemes, giving deadlines for position statements/progress reports; these have been brought to the Board Oct/Nov 2019 Quarterly ouput reporting is taken to Audit & Finance Group, SPMG and Executive Board. Forecasts are revised annually in Q1 - a deep dive into forecasting will take place April 2020
CDGD 22 | 4 schemes (2 very large) in programme may not spend grant allocation by Mar'21 deadline. Impacts output and loss of grant | An Outputs report/position statement and recommendations has been prepared for PAG 27/08/19, and is subsequently to be taken to Executive Board on 19/09/19. (Review pipeline, open call). | - Churnet Works has now withdrawn (21/08/19). - CCAP - Notice letter sent 27/09/19. Response letter received from SoTCC, (Exec Board agenda for 17/10/19) provided reassurance that spend/delivery targets could be met. Spend is due to recommence in Q4 19/20 - CELR business case was approved by Exec Board subject to T&C's and Monitoring Plan including penalty milestones - these have been drafted . Funding agreement now signed - Etruria brought a report to Exec Board on 21/11/19. All elements of the business case have been submitted to DfT - awaiting outcome of business appraisal by DfT. - - Etruria Valley - All elements of the business case have been APPROVED by DfT. Funding agreement and monitoring plan is to be drawn up. The 2 very large schemes are now contracted or in contracting, but Covid makes delivery within timescale uncertain
CDGD 25 | COVID 19 Coronavirus - impact on programme delivery; impact on schemes' ability to spend LGF grant within deadline if work is delayed or halted. | Engage with BEIS - push for extension of timescales for spend Lobby ministers Engage with support groups such as LEP network | Questions and issues have been escalated to BEIS, who are collating these in order to inform a response
ESIF 5 | Plans to allocate remaining ESIF allocations for LEP areas through ERDF and ESF National Reserve Fund calls have now been put on hold in favour of re-orientating remaining funds to align with national priorities, as part of the EU's COVID-19 response package. For the UK this means that funds will target te three highest government priorities as part of their response to COVID-19, namely supporting the NHS, helping businesses and self employed and employment measures to help those in work retain their jobs. Whilst all of these measures are likely to benefit the SSLEP area, remaining priojects and programmes planned for the National Reserve Fund calls that don't feature in these three priorities are now unable to bid for ESIF Funding | Need to follow emerging guidance on re-orientation of ESIF funds and ensure government priorities benefit the SSLEP area | Continue to monitor and advise via ESIF Committee and SSLEP Executive Board

## CURRENT ISSUES
SSLEP CDGD Issues Log - 20/01/2021
No | Type | Severity | Date Id | Author | Area | Group Assigned to | Risk Owner | Deadline | Description | Impact | Mitigating action | Last Updated | Status
2 | issue CDGD | Severe | 2019-10-29 | SSLEP PAG | Delivery | Executive Board | SSLEP Chair | Immediate | The LEP is not likely to meet March 2021 outputs targets. The gap between output forecasts and output actuals is increasing, particularly regarding historical infrastructure schemes. Some schemes are very far from where they should be in terms of outputs targets. Forecasting is revised each year; reporting does not highlight the slippage that is built into forecasting year on year, it just shows performance against the revised (amended) figures, pushing higher targets further down the line. This issue will be further increased by Covid, although Covid has not caused the delays accrued in previous years. | Delays in producing outputs mean that schemes will not meet the LEP targets or will need to deliver outputs against high targets in the later part of the monitoring period. This could be potentially detrimental to future allocations of government funding to the SSLEP | SPMG reviewed outputs and forecasting again in August and took a paper to Audit & Finance Committee/ Board in September. A presentation was given to SPMG by Jon Vining, detailing the issues that lie behind the issue regarding the historic infrastructure schemes. Mapping of outputs forecasting from 2021-25 has taken place. | 2020-11-03 |  | Open
5 | CDGD | Severe | 29.10.20 | SPMG | Finance Reputation | Executive Board | SSLEP Chair | Immediate | Following flooding this summer, a review of flood risk/behaviour in Stoke town centre has caused the EA to redesign the solution for the Stoke Flood Alleviation scheme. This has delayed the scheme and the forecast LGF spend in Q2 did not occur. It is not certain what the new costs will be or if the £1.2m LGF grant will be spent before the March 2021 deadline. No plans or spend forecasts are available yet; dates are unknown. (It should be noted that the EA are directly managing the scheme - SoTCC only provides a vehicle for LGF the funding flow). | Any LGF funding that is not spent by March 2021 would be lost. | Verbal communication from EA in December, proposing to reduce level of funding by £700,000. The scheme would still be completed but remaining funding would come from an alternative source to bridge the gap. Outputs would remain the same. Confirmation in writing has been requested but not received yet. SoTCC are currently in dialogue with the EA regarding spending the 700,000 pounds on related elements of the same scheme if they are within scope. SPMG decision 11/01/21: Stoke to see if there are any schemes that will allow us to legitimately spend money within the Stoke flood scheme. If there are no legitimate schemes, the funding will be diverted to i54WE | 2021-01-11 |  | Open
6 | CDGD | Severe | 2020-11-12 | Programme manager | Finance Delivery | (Exec Board) SPMG | SPMG Chair | Immediate | There is an issue in determining the extent of mitigation required for LGF underspend/slippage due to lack of visibility of scheme progress. LGF grant was diverted from the City East Link Road scheme following the BEIS review in June 2020 as CELR could not forecast spend within deadline. A further underspend of around £678,000 is forecast, although this may change. Currently forecasting that this could be spent in Q1 of 2021/22. | The LEP has no visibility of progress of this scheme and no sight of the scale of any further slippage, making it difficult to plan mitigation or to know whether to put mitigation in place immediately. As the deadline approaches (March 2021), the window to divert funding to mitigating schemes reduces and any unspent funding could be lost to the LEP. | The CELR lead has now provided a progress report and a revised monitoring/spend plan. Some LGF is forecast to be spent slightly beyond the LGF deadline due to the impact of Covid and discovery of old mine workings on one of the two sections of the scheme. Discussions are taking place with SoTCC around the possible options of off-setting this against an other legitimate Stoke LGF scheme - a paper is to come to SPMG on 1st Feb. | 2021-01-11 |  | Open

## OPEN RISKS
| Title: | SSLEP CDGD - Risk Register | [20 empty] | SSLEP Use
| Updated: | 2021-01-20
Identification | [14 empty] | Respond and Monitor | [7 empty] | Updates
Programme | Risk ID | Date identified | Identified by | Risk area | Risk Statement | Impact | Risk category | Group Assigned to | Risk owner | Controls | Current/net impact score | Current/net likelihood score | Current/net risk level | Current/net value of risk | Risk actions (mitigations) | Action owner | Expected Completion date | Action progress | Target impact score | Target likelihood score | Target risk level | Target value of risk | Date updated or reviewed | Risk status
CDGD | CDGD 18 | 2018-05-15 | SSLEP PAG risk team | Financial | As a result of assigned schemes delivery timescales slipping, there is a risk that the CDGD planned investment will not be achieved by March 2021, Covid increases this risk. | The impact would be that the LEP fails to deliver its agreed Growth Deal objectives, leading to reputational impact and jeopardising future investment. | Economic | SPMG | SPMG Chair | Profile Finance Report tracker in place; 20/21 quarterly profile in place | C - Major | 1 - Rare | Low |  | Quarterly grant spend profiling in place for all CDGD projects. | Simon Ablewhite | 2021-03-31 | There is the potential for i54WE to soak up another £1.7m of underspend (originally more, but i54WE now has £3m GBF funding allocated) if further slippage occurs. In addition to i54WE, the S151 presented a paper to SPMG on 29/10/20, detailing further mitigation via other active LGF schemes that could quickly absord any underspend. The report was provided to Audit & Finance Committee to provide assurance that mitigation is in place. Further detail was provided by the S151. In January, SPMG agreed that SoTCC was to investigate options to off-set underspend from an SoTCC scheme (CELR) against other legitimate approved/active SoTCC LGF schemes that could spend the grant within timescale. | B - Moderate | 2 - Unlikely | Low |  | 2021-01-11 | Open
CDGD | CDGD 26 | 2020-08-26 | Jon Rouse | Programme delivery | There is a risk that the forecast benefits of the District Heat Network may not be fulfilled due to the low price of natural gas. | If DHN is not competitive on price, customers will not be attracted and the forecast volumes of customers will not be achieved. | Benefits realisation | Audit & Finance | Stoke City Council | City Deal agreement between SoTCC and BEIS | C - Major | 3 - Possible | Medium |  | Audit & Finance Committee have asked for more detail to understand the impact and scale of the risk, given that this is the SSLEP flagship scheme. | Andrew Briggs | 2020-10-31 | The DHN lead brought a presentation to Executive Board on 17/11/20. The scheme is progressing with the infrastructure stage. SoTCC are to commission a market report on fuel prices next year. The scheme will bring a further report to SSLEP Board in the next financial year. | C - Major | 3 - Possible | Medium |  | 2020-12-01 | Open
GBF | GBF1 | 2020-08-20 | Simon Ablewhite | Financial | There is a risk that the SSLEP programme of Getting Building Fund schemes may not achieve full grant spend by March 2022 deadline. | The impact of this could be potential withdrawal by government of unspent funding, resulting in loss of funding to Staffordshire and reputational damage to SSLEP. It could also impact on future government funding allocations to SSLEP. | Financial/ reputational | SPMG | SPMG Chair | Monitor spend and review spend forecasts regularly with scheme leads. Spend profile is included in the funding agrement | C - Major | 3 - Possible | Medium |  | Funding Agreements include claw-back arrangements. A reserve list of contingency schemes has been approved by SPMG (subject to business case appraisals); subject to government approval and SPMG approval, funding could be redirected to a contingency scheme if any scheme should fail to start or fail to progress. Quarterly reports will be taken to SPMG and to Exec Board. | SA/SP | 2022-03-31 | As part of the baseline report to BEIS, schemes have been asked to submit a quarterly spend profile. These are being included in the funding agreements. The baseline report to BEIS was submitted 26/11/20. As at January 2021: 7 schemes are contractually committed, 2 contracts are in draft and pending completion, 1 scheme is approved and will go into contracting shortly. Drakelow GBF will be passported to D2N2 on approval of the D2N2 business case. One scheme has withdrawn (£190k). Contingency schemes have been appraised and approved by SPMG, should funding become available, although chnages are subject to MHCLG change process. | B - Moderate | 3 - Possible | Medium |  | 2021-01-11 | Open
GBF | GBF2 | 2020-10-08 | Programme Manager | Financial | There is a risk that the SSLEP programme of Getting Building Fund schemes may not achieve forecast outputs | The impact of this could be reputational damage to SSLEP and could impact negatively on future funding allocations made available to the LEP by government.. | Reputation | SPMG | SPMG Chair | Outputs profile is included in the funding agreement | C - Major | 3 - Possible | Medium |  | Funding Agreements include claw-back arrangements. A reserve list of contingency schemes has been approved by SPMG (subject to business case appraisals); subject to government approval and SPMG approval, funding could be redirected to a contingency scheme if any scheme should fail to start or fail to progress. Quarterly reports will be taken to SPMG and to Exec Board. | SA/SP | 2022-03-31 | GBF programme is in very early stages. Business cases are being appraised by independent appraisers. Outputs targets are included in the funding agreement. | B - Moderate | 3 - Possible | Medium |  | 2020-11-03 | Open
GBF | GBF3 | 2020-12-01 | SPMG | Delivery | Shire Hall Business Hub scheme - there is a risk that the business model may not fully deliver, or may not maximise, the full potential of the solution and outputs. | The impact could be missed opportunities in supporting local businesses in an innovative and flexible way, and failing to fully meet workplace needs post-Covid. The full potential of the Business Hub may not be achieved. | Benefits realisation | Exec Board | Alun Rogers | Shire Hall Steering Group | B - Moderate | 3 - Possible | Medium |  | Maintain visibility of the ongoing business model of the service. AR is to seek an SSLEP Board member volunteer to represent the LEP on the Shire Hall Steering Group. | AR | 2020-12-17 | AR is to seek an SSLEP Board member volunteer to represent the LEP on the Shire Hall Steering Group. MP confirmed that he has received messages regarding dates for these meetings. | B - Moderate | 3 - Possible | Medium |  | 2021-01-11 | Open
GBF | GBF4 | 2020-12-01 | SPMG | Delivery | Drakelow Park is a complex scheme, shared by two LEPS. It has been allocated £5,050,000 GBF by SSLEP (21% of SSLEP's total GBF allocation). SSLEP GBF will be passported to D2N2 who will manage, monitor the scheme and report all outputs. However, no business case has been produced to date. There is a risk that the scheme may not be able to progress within the GBF spend window. | The impact could be reputational damage to SSLEP if the scheme fails to progress and subsequent delays impact on the ability of the SSLEP to reallocate the funding to contingency schemes within a timescale that allows these schemes to progress. As this is 1/5th of the total GBF allocation, the impact could be compounded if any other priority or contingency schemes fail to progress. | Reputation | SPMG | Chair of SPMG | GBF approval processes (government) GBF approval process (SPMG) | D - Critical | 3 - Possible | High |  | Developments are expected shortly. SPMG will review in January. | SPMG | 2021-01-11 | Links are being maintained with Drakelow Steering Group and D2N2. A report by Tom Goshawk, Head of Capital Programmes at D2N2, was brought to SPMG on 11/01/21, stating that D2N2 Officers and Investment Board are confident that the scheme will deliver on spend and outcomes and that they remain supportive of the investment to be made. | D - Critical | 3 - Possible | High |  | 2021-01-11 | Open

## Blank (hidden)
Title: | SSLEP Blank Risk Register | [18 empty] | SSLEP Use
Updated: | November 2018
Identification | [11 empty] | Respond and Monitor | [7 empty] | Updates
Risk ID | Date identified | Identified by | Risk area | Risk Statement | Risk category | Risk owner | Controls | Current/net impact score | Current/net likelihood score | Current/net risk level | Current/net value of risk | Risk actions (mitigations) | Action owner | Expected Completion date | Action progress | Target impact score | Target likelihood score | Target risk level | Target value of risk | Date updated | Risk status
1
2
3
4
5
6
7
8
9
13
14
15
16
17
18
19

## Project RAG rating (hidden)
PROJECT - overall RAG rating of scheme (updated quarterly to align with BEIS reporting) NOTE: the full impact of Covid and government response re extending spend/delivery deadlines are not yet known and not reflected here | Deliverables | Finances | Reputation | RAG Rating PREVIOUS quarter | RAG Rating Q4 19/20 | Change to overall risk level in Q3 | Comment added where RAG status has changed
Lichfield Park | 3 | 1 | 2 | AG | AG
Meaford | 3 | 1 | 4 | AG | A |  | No progress. To be raised at SPMG
Bericote Four Ashes | 2 | 1 | 1 | AG | AG
Stafford Western Access Route | 3 | 1 | 2 | AG | AG
Etruria Valley | 3 | 3 | 3 | AR | AR |  | Approved by DfT but still needs to be contracted and delivered in a very tight timeframe.
LSTP (SoTCC & SCC) | 1 | 1 | 2 | AG | A |  | Claiming grant quarterly but no progress report provided since March 2019.
Branston Locks | 3 | 1 | 3 | AG | A |  | Housing doing well but commercial side is not happening despite some interest
Advanced Manufacturing Skills Hub - South Staffordshire College |  |  |  | Closed | Closed
Advanced Manufacturing Skills Hub - Stafford College |  |  |  | Closed | Closed
Advanced Manufacturing Skills Hub - JCB Academy |  |  |  | Closed | Closed
Tamworth Enterprise Quarter | 1 | 1 | 1 | G | G
Leek Mill Heritage Quarter |  |  |  | Withdrawn | Withdrawn
Rugeley Town Centre | 2 | 1 | 1 | AG | AG
Friarsgate, Lichfield |  |  |  | Withdrawn | Withdrawn
Economic Regeneration Programme | 1 | 1 | 1 | G | G
ROF Featherstone | 1 | 1 | 1 | G | G
Chatterley Valley West Site Access | 1 | 1 | 1 | G | G
Redhill Business Park | 1 | 1 | 1 | G | G
Keele Innovation Centre No.5 (IC5) | 1 | 1 | 1 | G | G
I54 South Staffordshire Employment Site | 1 | 1 | 1 | G | G
Lichfield Southern Bypass Phase 3 | 1 | 1 | 1 | G | G
Bericote Four Ashes Phase 2 | 1 | 1 | 1 | G | G
City East Link Road (formerly Hanley - Bentilee Link) | 3 | 3 | 3 | A | A
Spode Works | 1 | 1 | 1 | G | G
ROF Featherstone - Strategic Employment Site |  |  |  | Withdrawn | Withdrawn
Keele Smart Innovation Hub | 1 | 1 | 1 | G | G
Skills Capital Equipment Fund | 1 | 1 | 1 | G | G
City Centre Access | 2 | 3 | 2 | AG | A |  | Spend was to have recommenced in Q4 but programme appears to be further delayed.
Churnet Works Small Business Units |  |  |  | Withdrawn | Withdrawn
SME Expansion Support Programme | 1 | 1 | 1 | G | G
Stoke-on-Trent Railway Station Power Upgrade | 5 | 1 | 1 | AG | A |  | These franchises have had programmes locked - they're checking if they are allowed to proceed with this
Victoria Ground (Phase 2) | 1 | 1 | 1 | G | G
Blythe Park Extension Infrastructure Project | 1 | 3 | 1 | AG | AG
Stafford Gateway Strategic Land Acquisition | 3 | 1 | 1 | AG | AG

## Risk Matrix
Risk Matrix |  |  | <----------------------------------- IMPACT ------------------------------------->
| A - Minor | B - Moderate | C - Major | D - Critical | E - Catastrophic
5 - Almost certain | Low | Medium | High | High | High
4 - Likely | Low | Medium | Medium | High | High
3 - Possible | Low | Medium | Medium | High | High
2 - Unlikely | Low | Low | Medium | Medium | High
1 - Rare | Low | Low | Low | Medium | Medium

## Summary analysis (hidden)
RISKS
| Red | Amber | Green | Total
Board | 1 | 3 | 2 | 6
Audit & Finance | 2 | 8 | 1 | 11
SPMG | 1 | 3 | 1 | 5
| 4 | 14 | 4 | 22
ISSUES | Severe | Moderate | Minor | Total
Board | 4 | 1 | 0 | 5
Audit & Finance | 0 | 0 | 0 | 0
SPMG | 0 | 0 | 0 | 0
GPF Panel | 0 | 1 | 0 | 1
| 4 | 2 | 0 | 6
RISKS
| Red | Amber | Green | Total
Strategic | 2 | 3 | 2 | 7
CDGD | 0 | 1 | 1 | 2
GPF | 0 | 1 | 1 | 2
Skills | 0 | 0 | 0 | 0
Funding Group | 0 | 1 | 0 | 1
ESIF | 1 | 5 | 0 | 6 | Total risks by group assigned | [6 empty] | RISKS
GBF | 1 | 3 | 0 | 4 |  | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 |  | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01
SSLEP | 4 | 14 | 4 | 22 | Board | 5 | 5 | 6 |  |  |  | Red | 6 | 3 | 4
[5 empty] | Audit & Finance | 12 | 11 | 11 |  |  |  | Amber | 15 | 14 | 14
[5 empty] | SPMG | 6 | 4 | 5 |  |  |  | Green | 3 | 3 | 4
ISSUES
| Red | Amber | Green | Total
Strategic | 1 | 1 | 0 | 2
CDGD | 3 | 0 | 0 | 3
GPF | 0 | 1 | 0 | 1
Skills | 0 | 0 | 0 | 0
Funding Group | 0 | 0 | 0 | 0
ESIF | 0 | 0 | 0 | 0
GBF | 0 | 0 | 0 | 0
Risks | Board | Audit & Finance | SPMG
Red | 1 | 2 | 1 | 4
Amber | 3 | 8 | 3 | 14
Green | 2 | 1 | 1 | 4
22
ISSUES
[13 empty] | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01
[12 empty] | Red | 2 | 3 | 4
[12 empty] | Amber | 2 | 2 | 2
Green

## Risk Analysis (hidden)
| Red | Amber | Green | Total
Strategic | 4 | 1 | 0 | 5 | [15 empty] | Red
CDGD | 0 | 14 | 1 | 15 | [15 empty] | Amber
GPF | 0 | 3 | 1 | 4 | [15 empty] | Green
Skills | 0 | 4 | 0 | 4
Funding Group | 0 | 4 | 2 | 6
ESIF | 1 | 3 | 0 | 4
SSLEP | 5 | 29 | 4 | 38
[6 empty] | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01
[5 empty] | Red | 6 | 6 | 6 | 5 | 5 | 7 | 7 | 9 | 9 | 8 | 8 | 8 | 10 | 11 | 9 | 10
[5 empty] | Amber | 19 | 22 | 25 | 24 | 24 | 22 | 22 | 23 | 23 | 23 | 23 | 23 | 26 | 27 | 30 | 29
[5 empty] | Green | 12 | 12 | 11 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 7 | 7 | 4 | 4