Report of **Audit & Finance Subgroup Chair** in relation to the meeting of **07 July 2021**

**For:** (I) Information (R) Ratification (D) Discussion and decision

**Key agenda items discussed:**

|  |
| --- |
| * Q1 21-22 LEP Finance Dashboard * Consolidated Risk Register update * Hatch commission – mapping of contracts * LEP VAT note * Reserves Policy * Items routed via T&F Group for information following Board decision to approve Phase 1 activities   + Business case: extension of staff contract   + Insight Commission |

**Notable changes, successes or risks**

|  |
| --- |
| Notable points to raise from the Finance dashboard   * £0.539m Unallocated GBF Grant pot has been reallocated to 4 contingency schemes + additional other LEP funding of £0.524m.   Risks   * On-going delays with 3 approved GPF loans currently awaiting Funding Agreements to be signed off. * Core Fund Grant letter has not yet been received from BEIS * 21-22 LEP Core Budget has yet to be finalised * Lack of visibility of SSLEP responsibilities and accountabilities, including governance, management roles and funding routes. A mapping exercise is being undertaken to provide visibility of contracts. The LEP Review will offer opportunity to build a strong foundation for the future.      * Risk mitigation plan being progressed for Drakelow Park, involving formal deallocation of funds from SSLEP and reallocation to D2N2 to improve efficiency * Careers & Enterprise Grant – awaiting business case. Funding deadline has been extended to August. * Reserves policy to be identified to help to manage expectation regarding funding requests. * Acknowledgement of budget implications for Board decision to proceed with Phase 1   + Extension of staff contract   + Insight commission |

**Decisions and/or Recommendations**

|  |
| --- |
| * Addition of the following risks to the Risk Register:   + RISK: Growth Hub Manager – change of key personnel due to new role last year.   Mitigation: SSLEP CEO will work with current Growth Hub Manager to draw up a JD and recruit to the role. In the meantime, the Growth Hub Manager has agreed to cover until replacement sourced.   * + RISK: Careers Enterprise Hub - risk of lack of future funding. A request for funding has been received on 10/06/21 with a deadline of 16/07/21 (now extended until August). Late notice of match funding required places service and staff at risk.   Mitigation: Working with Make It Stoke Staffs to identify alternative sources.   * + RISK: Risk of strategic changes in relation to existing contracts and services delivered by SSLEP. Risk of impact on governance arrangements, contracts and delivery.   Mitigation: Mapping of contracts to enable us to risk assess against available funding streams. Hatch have been commissioned to carry out a contracts mapping exercise. Results will be taken to Audit & Finance in September.   * + RISK: Core Fund. SSLEP has not yet received the annual Core Fund offer letter from BEIS. |

* + **Appendix 1:** 2021/22 Q1 LEP Finance Dashboard
  + **Appendix 2:** SSLEP Risk and Issue Log 07/07/2021

Full details of the meeting including agenda pack, presentations and minutes can be requested from [john.broad@staffordshire.gov.uk](mailto:john.broad@staffordshire.gov.uk)