## Summary
Programme Risks and Issues
Summary - August 2021

## CURRENT ISSUES
SSLEP programmes Issue Log - August 2021
No | Type | Severity | Date Id | Author | Area | Group Assigned to | Risk Owner | Deadline | Description | Impact | Mitigating action | Last Updated | Status
1 | issue Strategic | Severe | 10.12.2018 | SSLEP PAG | Strategic | Executive Board | LEP Chair | ? | LEP geography. | The delay in government confirming future geographies could impact on SSLEP funding from government going forwards. Funding could be withheld in the future. | A letter has been received from Ministers (Berry & Nahawi) requesting that LEPs make a further attempt at local resolution and report back by 27 February 2020. A meeting took place between SSLEP and GBSLEP & WLEP Chairs on 19 February 2020 and resulted in a further letter send advising that local resolution was not possible. Ministerial response is now likely to be aligned with the publication of the Devolution White Paper however removal of overlaps continues to be govt policy. (Note: during the recent GBF bid, BEIS referred some districts back to SSLEP from GBSLEP). | 2020-02-28 |  | Open
2 | issue CDGD | Severe | 2019-10-29 | SSLEP PAG | Delivery | Executive Board | SSLEP Chair | Immediate | The LEP is not likely to meet March 2021 outputs targets. The gap between output forecasts and output actuals is increasing, particularly regarding historical infrastructure schemes. Some schemes are very far from where they should be in terms of outputs targets. Forecasting is revised each year; reporting does not highlight the slippage that is built into forecasting year on year, it just shows performance against the revised (amended) figures, pushing higher targets further down the line. This issue will be further increased by Covid, although Covid has not caused the delays accrued in previous years. | Delays in producing outputs mean that schemes will not meet the LEP targets or will need to deliver outputs against high targets in the later part of the monitoring period. This could be potentially detrimental to future allocations of government funding to the SSLEP | SPMG reviewed outputs and forecasting again in August and took a paper to Audit & Finance Committee/ Board in September. A presentation was given to SPMG by Jon Vining, detailing the issues that lie behind the issue regarding the historic infrastructure schemes. Mapping of outputs forecasting from 2021-25 has taken place. BEIS is kept fully informed on progress. Following the Q4 20/21 quarterly report to BEIS, LGD will now be reported biennially to BEIS (but still reported quarterly to SPMG).. | 2021-06-03 |  | Open
3 | issue Strategic | Moderate | 15.06.2020 | Audit & Finance | Strategic | Executive Board | LEP Chair | Immediate | An inexperienced LEP Board as a singular Board | Impacting on ability of Board to act as a single group, in the best interests of the group i.e. being able to focus on "larger than local" issues. | Ensure all Board members are brought up to speed as soon as possible, via the Induction programme and via regular one to one's with chairman etc. | 2020-06-15 |  | Open
4 | issue GPF | Moderate | 19.08.2020 | GPF | Delivery | GPF Panel | GPF Manager | ? | A loan of £450K to date remains unpaid. Now with SCC legal to recover | Impacts on the ability to offer funding to other businesses | Funding Agreement is in place to mitigate loss via the terms of recovery. A paper was taken to Board on 18/02/21 and a way forward was proposed, being a repayment plan plus a charge on property. Further correspondence was sent to the beneficiary from SCC legal on 30.04.21, detailing proposed terms for the repayment of the loan, namely repayments from the Applicant/Guarantor of £20,000 per quarter including interest with security of a second charge over a relevant property or properties. There would also be a long stop date by which time the funding must have been repaid to ensure the Council would not call on the security (5 years 9 months from the date of the first repayment). Any agreement to be entered into would need to oblige the Applicant to repay the outstanding funding amount to the Council upon the sale of the premises or any other property whether or not the Council has a legal charge over the property. The applicant has responded to the proposal with a counter-proposal of £15,000 per quarter. SCC legal are drafting the necessary documentation to obtain approval from the GPF panel to action this proposal.. All interest charges are paid to date. | 2021-06-03 |  | Open

## RESOLVED ISSUES
No | Type | Severity | Date Id | Author | Area | Group Assigned to | Risk Owner | Deadline | Description | Impact | Mitigating action | Last Updated | Status
6 | CDGD | Low | 2020-11-12 | SPMG | Finance Delivery | SPMG | SPMG Chair | Immediate | There is an issue in determining the extent of mitigation required for LGF underspend/slippage due to lack of visibility of scheme progress. LGF grant was diverted from the City East Link Road scheme following the BEIS review in June 2020 as CELR could not forecast spend within deadline. A further underspend of around £678,000 is forecast, although this may change. Currently forecasting that this could be spent in Q1 of 2021/22. | The LEP has no visibility of progress of this scheme and no sight of the scale of any further slippage, making it difficult to plan mitigation or to know whether to put mitigation in place immediately. As the deadline approaches (March 2021), the window to divert funding to mitigating schemes reduces and any unspent funding could be lost to the LEP. | The CELR lead has now provided a progress report and a revised monitoring/spend plan. Some LGF is forecast to be spent slightly beyond the LGF deadline. Discussions are taking place with SoTCC around the possible options of off-setting this against an other legitimate Stoke LGF scheme. The S151 Officer brought a paper to SPMG on 01/02/21: S151 has discussed options with SoTCC Capital Finance team. His recommendation is to switch underspend from CELR to Etruria Valley Link Road (EVLR). EVLR has completed its LGF spend but is still an active scheme with various funding sources and could spend the additional LGF in Q4. SoTCC would then be able to switch funding back to CELR in the new financial year. Switching the LGF to EVLR means that all LGF grant will be spent on LGF schemes. SPMG APPROVED SA’s recommendation to switch underspend from CELR to EVLR. Legal documents will be drafted to reflect the agreed changes. | 2021-02-01 | CLOSED
5 | CDGD |  | 29.10.20 | SPMG | Finance Reputation | Executive Board | SSLEP Chair | Immediate | Following flooding this summer, a review of flood risk/behaviour in Stoke town centre has caused the EA to redesign the solution for the Stoke Flood Alleviation scheme. This has delayed the scheme and the forecast LGF spend in Q2 did not occur. It is not certain what the new costs will be or if the £1.2m LGF grant will be spent before the March 2021 deadline. No plans or spend forecasts are available yet; dates are unknown. (It should be noted that the EA are directly managing the scheme - SoTCC only provides a vehicle for LGF the funding flow). | Any LGF funding that is not spent by March 2021 would be lost. | EA is proposing to reduce level of funding by £700,000. The scheme would still be completed but remaining funding would come from an alternative source to bridge the gap. Outputs would remain the same. Report from S151 is to go to SPMG on 04/05/21. A letter from Phil Cresswell SoTCC was received 15/03/221. SPMG to be asked to consider earmarking £200,000 of switched capital funding to fund de-silting work in the new financial year. The de-silting work was not part of the original scheme but is linked (co-dependent outputs) and information provided will be appraised and considered by SPMG subject to any available funding. The issue related to the original scheme is now closed as the unspent LGF funding has been retracted. | 2021-06-03 | Closed

## OPEN RISKS
| Title: | SSLEP Programmes - Risk Register | [20 empty] | SSLEP Use
August-2021
Identification | [14 empty] | Respond and Monitor | [7 empty] | Updates
Programme | Risk ID | Date identified | Identified by | Risk area | Risk Statement | Impact | Risk category | Group Assigned to | Risk owner | Controls | Current/net impact score | Current/net likelihood score | Current/net risk level | Current/net value of risk | Risk actions (mitigations) | Action owner | Expected Completion date | Action progress | Target impact score | Target likelihood score | Target risk level | Target value of risk | Date updated or reviewed | Risk status
Strategic | Strategic 7 | 2019-12-19 | LEP Executive Board | Strategic | Covid - Businesses are emerging from national lockdown(s) / new regional-tier restrictions, and the associated impact on business trading/survival and temporary/permanent job losses are beginning to be understood Impacts may include: | - LIS will have to reprofile implementation plans around recovery, renewal and longer term growth (i.e. short, medium, long term) - There may an operational risk if LEP resources are over-stretched (e.g. demand on Growth Hub support) - there may be an impact on future LEP funding if funds are diverted to support furlough or other government Covid mitigations. | Reputation | Exec Board | LEP Chair | The Chair, Board Members and Partnerships Manager are engaging in local regional and national discussions on future policy and delivery mechanisms. | D - Critical | 4 - Likely | High |  | LEP Covid-19 Task Force meet on a weekly basis. LEP Secretariat also support Staffordshire Prepared / Civil Contingency Groups (e.g. Recovery Co-ordinating Group). Appropriate timely responses in the absence of clarity re impact and timing. | Executive Board |  | Data and intelligence is being gathered by the full range of LEP partners in order to ensure a detailed understanding of economic impacts is available in considering required actions. Awareness of the impact and potential mitigations forms part of the integrated implementation plan and supported sub-groups. Ongoing | D - Critical | 3 - Possible | High |  | 2021-06-03 | Open
Strategic | Strategic 10 | 15.06.2020 | Audit & Finance | Strategic | Local Recovery and Devolution White Paper c/o UK Government (MHCLG sponsoring dept.) has the potential to shape the 'levelling up' policy agenda for the remaining four years of this central government administration. May led to institutional reform of the LEP and/or its membership. Now expected to be published in early Summer 2021. | If a short notice call of limited scope arises there is a reputational risk re the LEP's ability to move quickly enough and inclusively enough. | Reputation | SPMG | SPMG Chair | Government policy | C - Major | 4 - Likely | Medium |  | 1. Build credibility - demonstrate delivery; show that the LEP is a valid investment proposal. 2. Make the case : engage with the government / align communications & marketing 3. Build good partner relations | Executive Board |  | Partner networks are monitoring this and the LEP is seeking early insight. The White Paper is now expected in Winter 2021 (delayed from Summer/Autumn 2020), and should set out a menu of options and process. |  |  |  |  | 2021-06-03 | Open
Strategic | Strategic 11 | 15.06.2020 | Audit & Finance | Strategic | There is a risk that the SSLEP will not meet National Assurance Framework diversity requirements by 2023 associated with being a public funded board. | The impact would be that failure to fulfil public board requirements would trigger BEIS improvement plan and associated reputational impact. | Compliance | Exec Board | LEP Chair | Governance processes | C - Major | 1 - Rare | Low |  | LEP Secretariat have a Management Information System to track performance/actions required and includes straightforward actions to achieve compliance/embrace good practise. Recruitment for two new Board members is underway. | Executive Board |  | The requirement is now embedded in LEP Secretariat to support LEP Chair/Board as 'Business as Usual'. Internal Audit, Mid Year Performance Review and Annual Reviews track performance. |  |  |  |  | 2020-12-03 | Open
Strategic | Strategic 12 | 15.06.2020 | Audit & Finance | Strategic | There is a risk that LIS subgroups may not perform in line with their Terms of Reference. | The impact could be that an LIS Implementation Plan, which is likely to be required to access competitive/discretionary government funding, may not be produced. | Reputation | Exec Board | LEP Chair | Strategy/tender | B - Moderate | 3 - Possible | Medium |  | Board Members are providing leadership to the Sub Groups. SPMG undergoing policy work to provide more of a process around open calls for projects that require public intervention and associated priority/assessment maturity model. | Executive Board |  | Sub Groups are operational and continually evolving through 'learn/build as we go'. SPMG scope of work via Hatch will be subject to a commissioning process. |  |  |  |  | 2020-12-03 | Open
Strategic | Strategic 13 | 13.08.2020 | SSLEP CEO | Programme Delivery | With requirements from BEIS re governance requirements (Delivery Plan, AGM etc), there is a risk that the necessary admin tasks for the LEP Secretariat and the LEP sub-group leadership may be greater than the resources available. | The impact of this could be that some governance requirements may not be met, negatively impacting on the LEP's reputation and performance indicators. | Reputation | Exec Board | LEP Chair | Annual budget reviews | C - Major | 3 - Possible | Medium |  | Resourcing proposal will be brought to Board in June 2021 | LEP CEO |  | Proposal including revised structure and budget to be presented to Board in June 2021 |  |  |  |  | 2021-06-03 | Open
Strategic | Strategic 14 | 2018-05-15 | SSLEP Covid-19 Task Force / SPMG | Programme delivery | There is a risk of impact from economic and political trends which are beyond the control of the SSLEP. EU transition, global pandemic, stability of central government, general downturn in the economy could all impact negatively (or positively) on the schemes within the programme. | Programmes could slow or stall as a result of any of these external factors, which would have the affect of the programme not meeting targets | Economic | Audit and Finance | Audit & Finance Chair | Monthly programme reporting in place for all projects; top risks identified | D - Critical | 4 - Likely | High |  | Keep abreast of delivery partner operational issues and SPMG taking action as appropriate through conventional grant award conditions, incentives and penalties. | Mark Parkinson | 2021-03-31 | Regular reviews are undertaken at programme level and potential impacts of this risk monitored by each programme. | C - Major | 3 - Possible | Medium |  | 2020-12-03 | Open
Strategic | Strategic 15 | 2021-06-03 | SSLEP CEO |  | Risk of business continuity for LEP and associated Growth Hub given LEP Review process |  | Financial/ reputation | Exec Board | LEP Chair | Government process | D - Critical | 4 - Likely | High |  | Regular engagement with officials and working groups to help to shape future structures. High quality delivery to secure confidence in current role. |  |  | Letter of comfort for delivery 21/22. Engagement and influence into LEP Review process | D - Critical | 4 - Likely | High |  | 2021-06-03 | Open
Strategic | Strategic 16 | 2021-06-03 | SSLEP CEO | Programme delivery | There is a risk that the LEP review will significantly alter the direction of the LEP. |  | Reputation | Exec Board | LEP Chair | LEP strategy | C - Major | 4 - Likely | Medium |  | Review LEP Strategy. |  |  | Board engagement to be sought. | C - Major | 4 - Likely | Medium |  | 2021-06-03 | Open
Strategic | Strategic 17 | 2021-06-03 | SSLEP CEO | Strategic/ Delivery | Risk of failure to meet grant conditions for the Growth Hub which requires direct leadership and Governance from the LEP and failure to understand and mitigate associated risks relating to Growth Hub finance/operations/performance |  | Reputation/ Compliance | Exec Board | LEP Chair | Governance policy and process/structural change to ensure direct line management | C - Major | 3 - Possible | Medium |  | Governance/scrutiny via SPMG; formal approval of business plan and budget . Future organisation governance structure to be reviewed at LEP Executive Board/ |  |  | Direct operational reporting commenced via regular meetings with CEO. Outline proposal of activity for 21/22 and Budget (S1/S3) shared with Board. Regular progress reports required to SPMG | C - Major | 3 - Possible | Medium |  | 2021-06-03 | Open
Strategic | Strategic 18 | 2021-07-07 | SSLEP CEO | Programme Delivery | Growth Hub Manager – change of key personnel due to new role last year. | There is a risk that the Growth Hub could be left without a manager | Delivery/ reputation | Exec Board | LEP Chair | Governance structure - this post now reports direct to LEP CEO. Recruitment processes. | C - Major | 4 - Likely | Medium |  | SSLEP CEO will work with current Growth Hub Manager to draw up a JD and recruit to the role. In meantime, the Growth Hub Manager has agreed to cover until replacement sourced. | AB | 2021-10-31 |  | C - Major | 4 - Likely | Medium |  | 2021-07-07 | Open
Strategic | Strategic 19 | 2021-07-07 | SSLEP CEO | Finance | Careers Enterprise Hub - risk of lack of future funding. A request for funding has been received on 10/06/21 with a deadline of 16th July | Late notice of match funding required places service and staff at risk. | Delivery/ reputation | SPMG | SPMGChair | SPMG funding processes | C - Major | 3 - Possible | Medium |  | Working with Make It Stoke Staffs to identify alternative sources. Careers Enterprise Company have agreed to postpone deadline date until August. | AB | 2021-07-31 | SPMG asked the Careers Enterprise Hub to provide a business case if they wished to bid for LEP funding, but no business case has been received. SCC and SoTCC have agreed to underwrite the match funding for the current academic year, so the LEP CEO has signed and progressed the CEC grant offer letter. The Careers Hub could still subsequently submit a business case to the LEP, although they have been advised that there is no guarantee of any LEP funding. | C - Major | 3 - Possible | Medium |  | 2021-07-07 | Open
Strategic | Strategic 20 | 2021-07-07 | SSLEP CEO | Strategic | Risk of strategic changes in relation to existing contracts and services delivered by SSLEP | Risk of impact on governance arrangements, contracts and delivery | Reputation/ Governance | Exec Board | LEP Chair | SSLEP strategy and governance | D - Critical | 4 - Likely | High |  | Map the contracts to enable us to risk assess against available funding streams | AB |  | Hatch have been commissioned to carry out a contracts mapping exercise. Results will be taken to Audit & Finance in September. | C - Major | 4 - Likely | Medium |  | 2021-07-07 | Open
Strategic | Strategic 21 | 2021-07-07 | SSLEP CEO | Finance | SSLEP has not yet received the annual Core Fund offer letter from BEIS | This could potentially impact on the core budget | Delivery | Audit & Finance | Audit & Finance Chair | LEP Review | C - Major | 3 - Possible | Medium |  | LEP CEO and Chair pressing BEIS for a decision, directly and via LEP Network. We have sufficient reserves to manage cashflow. | AB/AR |  | SSLEP has now received an offer letter for funding for 6 months, so funding is in place to end of September 2021 | C - Major | 3 - Possible | Medium |  | 2021-07-07 | Open
NEW Strategic | Strategic 22 | 2021-09-01 | Audit & Finance | Governance | Lack of consistency regarding data sharing and retention procedures, meaning that there is a risk that tracking and links across subgroups may not be as visible and traceable as they should be. Subgroups are managed by different people so inherited templates and filing policies etc are not consistent. | Information may be unclear, inconsistent or omitted instead of following a clear and transparent path between subgroups and Board. | Delivery/ reputation | Audit & Finance | Audit & Finance Chair | Internal protocols. Consistent templates | B - Moderate | 3 - Possible | Medium |  | Audit & Finance Committee have requested that draft templates (for agendas, minutes etc) are drawn up and shared with subgroup Chairs so that one standard version can be used. Shared filing protocols and permissions are to be reviewed. | MA/AB | 2021-10-31 |  | B - Moderate | 3 - Possible | Medium |  | 2021-09-01 | Open
GPF | GPF 2 | 2018-11-09 | GPF | Financial | Potential for default or delayed repayment of GPF loans. AS GPF is to be self-sustaining. | This would impact on capacity to provide future loans | Legal | Audit & Finance | LA Accountable Body & GPF Steering Group | GPF Steering Group monthly review | C - Major | 3 - Possible | Medium |  | Loan repayment schedule included in GPF Funding Agreement together with explicit conditions stating the terms of the loan. Regular monitoring and close liaison with business applicant to identify any issues affecting the timely repayment of the loan. All GPF contracted schemes will be closely monitored to identify any potential default situations. | GPF |  | 2 business applicants have defaulted on their loan to date and the terms and consequences, including additional interest charged on the outstanding balance, were executed for both of the 2 projects of default. The first of the 2 applicants who defaulted has repaid the loan in full along with interest of £5,916 for the 7m default period; progress on the second is detailed under GPF Issue 4 (see "Current Issues" sheet) | B - Moderate | 1 - Rare | Low |  | 2020-11-03 | Open
GPF | GPF 1 | 2018-11-09 | GPF | Programme delivery | GPF calls fail to attract eligible applications from businesses. There are concerns that Covid may impact. | Loans are not being allocated to support local businesses. Future risk to investment. Reputational risk for the SSLEP | Economic | Audit & Finance | LA Accountable Body & GPF Steering Group | GPF Steering Group monthly review | B - Moderate | 2 - Unlikely | Low |  | Continuous bidding call and publicise GPF via a wide range of media, events and partnership activity. | GPF |  | January A&F Group consider this risk to be "In Control" as applications are oversubscribed. The next project call has taken place in September: Round 15: 3 projects have progressed to Stage 2 and went back to panel in December. Funding agreements are being prepared; total GPF requests of £345,000 approved. | B - Moderate | 2 - Unlikely | Low |  | 2020-12-01 | Open
NEW GPF | GPF5 | 2021-08-12 | GPF Programme Manager | Financial | An LGF scheme in receipt of both LGF grant and GPF loan is delayed and in breach of the S278 agreement. There is arisk that, if the issues are not resolved quickly by SCC Highways, the scheme may be further delayed or fail to progress. Further delays could reduce the length of time before the loan repayment needs to be made (May 2023). (Linked to CDGD risk 27) | Timely repayment may be at risk, impacting on the GPF loan cycle. | Financial | SPMG | Chair of SPMG | LGF contract and GPF contract | B - Moderate | 3 - Possible | Medium |  | SSLEP Programme Manager is keeping in close contract with SCC Highways and SCC Legal to monitor progress | LGF/GPF Prog Mngrs |  | A meeting is to be held on 18/08/2021 between: SCC Highways leads, the Amey project manager, the SCC S278 and Land Transfer solicitors, scheme sponsors and their solicitor. An update report will be brought to SPMG 24/08/21 and to Audit & Finance on 01/09/21 if this has not been resolved prior to the meeting on 18th Aug. | B - Moderate | 3 - Possible | Medium |  | 2021-08-12 | Open
FG | FG 9 | 2019-07-16 | LEP Funding Group | Financial | There is a risk that insufficient funding is reserved from budget for future redundancies and VAT liabilities (post Company structure) | The impact would be that SSLEP would be unable to meet its statutory obligations which would have a financial and reputational impact | Financial/ reputational | Audit & Finance | LEP Funding Group | LEP Funding Group scheduled to meet monthly to review | C - Major | 3 - Possible | Medium |  | Review redundancy annually. Keep running total of VAT from 1/4/2019. 2021/22 budget commitments have been set/approved inclusive of VAT. | LEP CEO | Ongoing | To be monitored and discussed at the next funding meeting. Reserved from core budget: £100k for 2019/20 VAT and £65k for 20/21. January 2021:The 20/21 VAT liability has been increased to £90k. The 20/21 VAT liability was increased to £100k. From 2021/22 the budget commitments have been set as inclusive of VAT. Redundancy pot of £45k + £10k top up to be added in 20/21; underspend from core fund may further increase this reserve. | B - Moderate | 3 - Possible | Medium |  | 2021-06-18 | Open
ESIF | ESIF 6 | 4/14/20 | Nigel Senior | Financial | COVID-19 related impact delay implementation of contracted activities, particularly where face to face delivery is prevalent, including Business support and Employment/Skills programmes across SSLEP area | The impact is that the LEP could run the risk of being in breach of funding agreements by not spending to set targets and not delivering the contracted outputs | Economic | Audit & Finance | Nigel Senior | Updates through ESIF Committee | B - Moderate | 3 - Possible | Medium |  | Need to advise projects to use the MHCLG Project Change Request Process to get any delivery issues addressed so as funds are not lost to specific projects through non delivery or non compliance | N Senior / M Connell | Ongoing | The EU has announced flexibilities for existing contracted ESIF projects and programmes as part of its COVID-19 response packages, to ensure that these activities have sufficient time to deliver and spend ESIF funding . Whilst the ultimate financial completion date remains unchanged delivery timescales could given extensions to compensate for any impacts associated with COVID-19. This is particularly relevant to business support and grant programmes as well as employment and skills support schemes | B - Moderate | 3 - Possible | Medium |  | 2021-02-01 | Open
ESIF | ESIF 7 | 2020-04-14 | Mark Connell | Financial | ERDF programmes end at the latest June 23 and the ‘replacement’ UKSPF has been delayed which is likely to be extended as the Government deal with the Covid 19 pandemic. To ensure continued support an overlap of the two programmes was being progressed, however there has to be concern that this may no longer be the case | The impact would be that much needed investment programmes could be halted within SSLEP. | Economic | Audit & Finance | Mark Connell | Updates from CLG | C - Major | 3 - Possible | Medium |  | The LEP to continue to lobby government for UKSPF monies | M Connell | Ongoing | Continue to liaise with MHCLG on Government announcements with regard to replacement funding | C - Major | 3 - Possible | Medium |  | 2021-02-01 | Open
ESIF | ESIF 8 | 2020-04-14 | Mark Connell | Impact | There is a possibility that the activity required may not be delivered in the current climate, impacting on the suite of projects delivering Business support activities targeted at growth. | The impact would be that activity required will not be delivered in the current environment - there may be job losses rather than growth | Economic | Audit & Finance | Mark Connell | Working with live ERDF / ESF projects | B - Moderate | 4 - Likely | Medium |  | We need to try to introduce flexibilities into the existing programmes and projects and encourage projects to recalibrate so as delivery is better aligned to business survival and reducing job losses, rather than growth, in the current environment. | M Connell | Ongoing | Working with Live projects | B - Moderate | 4 - Likely | Medium |  | 2021-02-01 | Open
ESIF | ESIF 9 | 2020-08-13 | Julie Obada/ Tony Baines | Impact | The County wide redundancy Task Force is utilising the JEP brokerage service to assist individuals get back into employment. The capacity of this service could be called into question once the furlough scheme comes to an end in October. | Impact is that the capacity of this service could be over-stretched once the furlough scheme comes to an end. | Economic | Audit & Finance | J Obada | Updates to LEP Task Force | B - Moderate | 3 - Possible | Medium |  | This is an issue that the Redundancy Task Group is aware of and continue to monitor, however no clear additional resource identified to date | ESF TA Team | Ongoing | Monitored through the Redundancy Group and its partner network |  |  |  |  | 2021-02-01 | Open
ESIF | ESIF 10 | 2020-08-13 | Julie Obada/ Tony Baines | Financial | Delivery of the current ESF Programme has been impacted due to Covid and whilst existing clients have been retained these has been a significant fall in new clients. | This could impact on the programmes delivery as it moves forward. Similarly the fall in vacancies will impact on the ability of programme to get individuals back into employment over the short term | Economic | Audit & Finance | J Obada | Updates to LEP Task Force | B - Moderate | 3 - Possible | Medium |  | ESF will continue to work with DWP to reshape the delivery profile and expenditure profile | ESF TA Team | Ongoing | Monitored via the ESF Officer Group |  |  |  |  | 2021-02-01 | Open
CDGD | CDGD 26 | 2020-08-26 | Jon Rouse | Programme delivery | There is a risk that the forecast benefits of the District Heat Network may not be fulfilled due to the low price of natural gas. | If DHN is not competitive on price, customers will not be attracted and the forecast volumes of customers will not be achieved. | Benefits realisation | Audit & Finance | Stoke City Council | City Deal agreement between SoTCC and BEIS | C - Major | 3 - Possible | Medium |  | Audit & Finance Committee have asked for more detail to understand the impact and scale of the risk, given that this is the SSLEP flagship scheme. | Andrew Briggs | 2020-10-31 | The DHN lead brought a presentation to Executive Board on 17/11/20. The scheme is progressing with the infrastructure stage. SoTCC are to commission a market report on fuel prices next year. The scheme will bring a further report to SSLEP Board in the next financial year. | C - Major | 3 - Possible | Medium |  | 2020-12-01 | Open
NEW CDGD | CDGD27 | 2021-07-06 | SCC Highways | Programme delivery/ Finance | There is a risk that one LGF scheme may be seriously delayed or may fail to progress due to problems including legal land transfer and disengagement of design engineers | If the problems are not resolved, the scheme may not progress or outputs may be delayed. | Finance/ reputation | Audit & Finance | Chair of Audit & Finance | SCC Highways legal processes. SSLEP legal contracts (include clawback clauses) | C - Major | 3 - Possible | Medium |  | SCC Highways and the scheme sponsor are working to resolve the problems. |  |  | SCC Highways and Amey are working with the scheme sponsor to seek resolution. SPMG are backed by Audit & Finance Committee in continuing to take a supportive role, although mitigations are being considered in the event that resolution is not possible. | C - Major | 3 - Possible | Medium |  | 2021-08-12 | Open
GBF | GBF1 | 2020-08-20 | Simon Ablewhite | Financial | There is a risk that the SSLEP programme of Getting Building Fund schemes may not achieve full grant spend by March 2022 deadline. | The impact of this could be potential withdrawal by government of unspent funding, resulting in loss of funding to Staffordshire and reputational damage to SSLEP. It could also impact on future government funding allocations to SSLEP. | Financial/ reputational | SPMG | SPMG Chair | Monitor spend and review spend forecasts regularly with scheme leads. Spend profile is included in the funding agreement | C - Major | 3 - Possible | Medium |  | Funding Agreements include claw-back arrangements. A reserve list of contingency schemes has been approved by SPMG (subject to business case appraisals); subject to government approval and SPMG approval, funding could be redirected to a contingency scheme if any scheme should fail to start or fail to progress. Quarterly reports will be taken to SPMG and to Exec Board. | SA/SP | 2022-03-31 | As part of the baseline report to BEIS, schemes have been asked to submit a quarterly spend profile. These are being included in the funding agreements. The baseline report to BEIS was submitted 26/11/20. As at 5th June 2021: 9 schemes are contractually committed. Drakelow GBF will be passported to D2N2 on approval of the D2N2 business case; the detail and control around this process is to be researched. One scheme has withdrawn (£190k). One scheme has been re-scoped, with a reduction in GBF ask of £350k. As more LEP funding has become available via capital switch funding, all Contingency schemes have been re-appraised and re-prioritised and 4 have been approved by SPMG, submitted to MHCLG RFC process and subsequently approved. The re-scoped scheme and 3 of the 4 contingency schemes are now in the contracting stage; one is already contracted and in progress. | B - Moderate | 3 - Possible | Medium |  | 2021-08-12 | Open
GBF | GBF2 | 2020-10-08 | Programme Manager | Financial | There is a risk that the SSLEP programme of Getting Building Fund schemes may not achieve forecast outputs | The impact of this could be reputational damage to SSLEP and could impact negatively on future funding allocations made available to the LEP by government.. | Reputation | SPMG | SPMG Chair | Outputs profile is included in the funding agreement | C - Major | 3 - Possible | Medium |  | Funding Agreements include claw-back arrangements. A reserve list of contingency schemes has been approved by SPMG (subject to business case appraisals); subject to government approval and SPMG approval, funding could be redirected to a contingency scheme if any scheme should fail to start or fail to progress. Quarterly reports will be taken to SPMG and to Exec Board. | SA/SP | 2022-03-31 | GBF programme is in very early stages. Outputs targets and timelines for delivery of these are included in the funding agreements, most of which have now been complete. The funding agreements contain clawback clauses. Spend and outputs are monitored and reported to BEIS, Board and SPMG | B - Moderate | 3 - Possible | Medium |  | 2021-06-03 | Open
GBF | GBF3 | 2020-12-01 | SPMG | Delivery | Shire Hall Business Hub scheme - there is a risk that the business model may not fully deliver, or may not maximise, the full potential of the solution and outputs. | The impact could be missed opportunities in supporting local businesses in an innovative and flexible way, and failing to fully meet workplace needs post-Covid. The full potential of the Business Hub may not be achieved. | Benefits realisation | Exec Board | Alun Rogers | Shire Hall Steering Group | B - Moderate | 3 - Possible | Medium |  | Maintain visibility of the ongoing business model of the service. AR is to seek an SSLEP Board member volunteer to represent the LEP on the Shire Hall Steering Group. | AR | 2020-12-17 | AR is to seek an SSLEP Board member volunteer to represent the LEP on the Shire Hall Steering Group. MP confirmed that he has received messages regarding dates for these meetings. AR will join the Design Group for the scheme. | A - Minor | 3 - Possible | Low |  | 2021-03-01 | Open
GBF | GBF4 | 2020-12-01 | SPMG | Delivery | Drakelow Park is a complex scheme, shared by two LEPS. It has been allocated £5,050,000 GBF by SSLEP (21% of SSLEP's total GBF allocation). SSLEP GBF will be passported to D2N2 who will manage, monitor the scheme and report all outputs. However, no business case has been produced to date. There is a risk that the scheme may not be able to progress within the GBF spend window. | The impact could be reputational damage to SSLEP if the scheme fails to progress and subsequent delays impact on the ability of the SSLEP to reallocate the funding to contingency schemes within a timescale that allows these schemes to progress. As this is 1/5th of the total GBF allocation, the impact could be compounded if any other priority or contingency schemes fail to progress. | Reputation | SPMG | Chair of SPMG | GBF approval processes (government) GBF approval process (SPMG) | D - Critical | 2 - Unlikely | Medium |  | Developments are expected shortly. SPMG are reviewing monthly. | SPMG | 2021-01-11 | A meeting took place on 29/06/21 between the SSLEP and D2N2 CEOs, S151s, Programme managers and BEIS Area Leads for both areas. It was agreed that to de-risk the scheme for SSLEP and to enable efficiencies and better control of the project for D2N2, a proposal would be put forward to de-allocate the £5m GBF from SSLEP and re-allocate it to D2N2, subject to legal assurances being in place between SSLEP and D2N2. A paper was taken to SSLEP SPMG and then to Executive Board; the submission of a change request to MHCLG to request de-allocation/re-allocation of GBF was approved and the Change Request was submitted on 26/07/21. (MHCLG have subsequently approved the request - a legal assurance agreement between SSLEP and D2N2 is pending). | D - Critical | 2 - Unlikely | Medium |  | 2021-08-12 | Open
GBF | Skills 8 | 2021-01-26 | SPMG | Delivery | SEF 3 - Digital Skills Academy - There is a risk that the project will not deliver its spend and/or outputs targets. | The impact could be an underspend in the GBF LEP allocation and the creation of fewer jobs to dampen economic growth. | Financial/ economic | SPMG | Chair of SPMG | monthly project review in place until spend targets are met, followed by quarterly reviews. Project reviewed at monthly S&E management meetings | B - Moderate | 3 - Possible | Medium |  | Funding Agreements include claw-back arrangements. Agree any remedial actions with the provider following review | David Poole | 2022-09-30 | South Staffordshire College’s Digital Skills Academy project claimed £539,860 against profile of £539,973 an underspend of £113. £493,314 in-kind match recorded to date.. | B - Moderate | 3 - Possible | Medium |  | 2021-08-12 | Open
GBF | Skills 9 | 2021-01-26 | SPMG | Delivery | SEF 3 - Creative & Digital Industries Project - There is a risk that the project will not deliver its spend and/or outputs targets. | The impact could be an underspend in the GBF LEP allocation and the creation of fewer jobs to dampen economic growth. | Financial/ economic | SPMG | Chair of SPMG | monthly project review in place until spend targets are met, followed by quarterly reviews. Project reviewed at monthly S&E management meetings | B - Moderate | 3 - Possible | Medium |  | Funding Agreements include claw-back arrangements. Agree any remedial actions with the provider following review | David Poole | 2022-09-30 | Stoke-on-Trent College’s Creative and Digital Industries (CDI) project due to commence in May 21. Grant spend in Q4 for the CDI project was £7,283. Forecast spend in Q1 £19,920, Q2 £222,797.(less management fee) | B - Moderate | 3 - Possible | Medium |  | 2021-08-12 | Open
GBF | Skills 10 | 2021-01-26 | SPMG | Delivery | SEF 3 - Construction Industries Digital Technologies - There is a risk that the project will not deliver its spend and/or outputs targets. | The impact could be an underspend in the GBF LEP allocation and the creation of fewer jobs to dampen economic growth. | Financial/ economic | SPMG | Chair of SPMG | monthly project review in place until spend targets are met, followed by quarterly reviews. Project reviewed at monthly S&E management meetings | B - Moderate | 3 - Possible | Medium |  | Funding Agreements include claw-back arrangements. Agree any remedial actions with the provider following review | David Poole | 2022-09-30 | Stoke-on-Trent College’s Construction Industry Digital Technologies (CIDT) due to commence in May 21. Forecast spend Q1 is £50,493, Q2 £69,507.(less management fee) | B - Moderate | 3 - Possible | Medium |  | 2021-08-12 | Open
GBF | GBF 5 | 2021-05-17 | Audit & Finance | Finance | The usual requirement for draw down of grant is that grant and match are drawn down proportionately during the life of the scheme, to demonstrate sponsor commitment. However, GBF schemes are being encouraged to front-load spend of GBF to ensure that it is spent before the spend deadline of March 2022. There is a risk that if a project stalls or fails to complete, it is entirely GBF funding that is at risk, as zero or negligible match funding may have been spent. | The impact of this is that any financial risk or loss arising from failure of a scheme to progress or complete would be higher for GBF grant and lower for match funded contribution as GBF is front-loaded. | Financial | SPMG | Chair of SPMG | Funding agreements include claw-back arrangements and reporting obligations. | B - Moderate | 3 - Possible | Medium |  | Close monitoring and tracking of project progress. Quarterly tracking of financial progress. | SA/SP | 2021-03-31 | The de-allocation of Drakelow removes a substantial risk from SSLEP and gives D2N2 far greater control and flexibility. A process will be put in place to ensure that match spend is evidenced in the same way that grant spend must be evidenced (provision of invoices etc). | B - Moderate | 3 - Possible | Medium |  | 2021-08-12 | Open
GBF | GBF6 | 2021-05-24 | Programme manager | Finance | Keele University IC7 have suffered slight delays to the programme due to a protracted procurement process (impacted by Covid and Brexit). Q1 claim will be £600,000 less than original forecast, with this amount being pushed back to Q3 and Q4, meaning that nearly 70% of the total GBF is now forecast to be spent in the last two quarters of the GBF spend window, increasing the risk of not achieving full spend. | Any GBF grant not drawn down within the GBF spend window will be at risk of retraction, which could impact on the scheme and on the reputation of the LEP. | Financial/ Reputational | SPMG | Chair of SPMG | Reporting and monitoring processes (both LEP's and Keele's processes ensure visibility) | B - Moderate | 3 - Possible | Medium |  | Close monitoring and tracking of project progress. Quarterly tracking of financial progress. | SA/SP | 2022-03-31 | Keele University raised this in advance of usual reporting deadlines and provided a refreshed spend profile and reassurance that they are confident that we will be able to claw back the initial underclaim during the claim period (final claim due to be submitted in March 2022). SPMG accepted the revised spend profile but requested that the project be rated as Amber and additional monitoring to take place. Keele University have been notified. They slightly exceeded their revised Q1 spend forecast. | B - Moderate | 3 - Possible | Medium |  | 2021-06-02 | Open
NEW GBF | GBF7 | 2021-08-12 | Programme manager | Delivery | As the contingency schemes have only very lately been approved, there is a risk that implementing the schemes and achieving GBF spend by the deadline of March 2022 may prove too challenging. Schemes that had originally planned to deliver during a period of 12 to 18 months now have only 7 months. There have been delays in providing HoTs and in responses to draft contracts. | The impact of this could be partially-completed schemes that have failed to spend all their GBF allocation by the end of March 2022. | Finance/Delivery | SPMG | Chair of SPMG | Reporting and monitoring processes. Contracts. | C - Major | 3 - Possible | Medium |  | Close monitoring and tracking of progress towards contracting and project start dates and spend progress. | SA/SP | 2022-03-31 | Three of the four contracts are sitting with scheme sponsors, awaiting completion. The fourth scheme has submitted HoTs on 01/09/21. (In the event of any future capital funding allocations, lessons learned will be noted and deadlines will be included in the grant offer letters for submission of HoTs, completion of contracts etc to avoid lengthy delays) | B - Moderate | 3 - Possible | Medium |  | 2021-08-17 | Open
NEW GBF | GBF8 | 2021-09-01 | SPMG | Delivery | There is a risk that escalating costs and shortages of supplies due to Covid and Brexit could cause delays and project costs to increase to a significant level above original budget. | Schemes may find if diffiicult to fully complete if costs significantly exceed budget or shortages of materials cause extensive delays. | Finance | SPMG | Chair of SPMG | Reporting and monitoring | C - Major | 3 - Possible | Medium |  | Monitoring and tracking of project progress/financial progress, especially in relation to supplier costs. | SA/SP | 2022-03-31 | Quarterly project progress reports and frequent interim conversations with scheme leads. | C - Major | 3 - Possible | Medium |  | 2021-09-01 | Open

## CLOSED RISKS
| Title: | SSLEP Risk Register | [20 empty] | SSLEP Use
| Identification | [13 empty] | Respond and Monitor | [7 empty] | Updates
Programme | Risk ID | Date identified | Identified by | Risk area | Risk Statement | Impact | Risk category | Group Assigned to | Risk owner | Controls | Current/net impact score | Current/net likelihood score | Current/net risk level | Current/net value of risk | Risk actions (mitigations) | Action owner | Expected Completion date | Action progress | Target impact score | Target likelihood score | Target risk level | Target value of risk | Date updated | Risk status
| Strategic 1 | 2018-12-10 | SSLEP PAG risk team | LEP governance | The LEP Review requires all LEPs to review their governance arrangements and move to incorporated body status by 1 April 2019. Financial penalties may be incurred by LEPs which do not meet this deadline. E.g. prevention of access to new funding. |  | Economic |  | Board mandated governance sub group | Board mandated sub group (agreed 18 Oct 2018) comprising: LEP Chair, Audit & Finance Committee Chair & match-funding partners (LEP Accountable Body & City Council). |  |  |  |  | Secretariat working with LEP Network to commission legal advice on incorporation and draft template on potential articles of association. Sub Group created to lead process Regular reports to Executive Board | Interim Partnership Manager | 2019-03-31 | LEP Network-commissioned legal advice received. Sub group established to determine and enact requirements. Company structure & articles agreed by Board and first 8 directors signed up 7 March 2019 | A - Minor | 1 - Rare | Low |  | 2019-03-12 | Closed
Strategic | Strategic 2 | 2018-12-10 | SSLEP PAG risk team | The LEP review required all LEPs to review their functioning economic geographies, removing overlaps and confusion over accountability and responsibility on leadership & priority-setting. LEPs submitted details of their proposed future geographies by end of September 2018. The delay in government confirming future geographies is impacting upon confirmation of £300k Core Funding for 2018/19 & 2019/20. This funding is allocated against delivering the LEP Review, including move to incorporated status & increasing capacity in the team in order to be 'fit' for future investment. | Political |  | Governance | Exec Board | LEP Chair | Executive Board provided geographies statement to deadline and, through the Chair and partner organisations, has continued to engage with partner LEPs and with government as requested. |  |  |  |  | Chair to maintain engagement with government on progress, in notifying govt of company formation which aligns with current LEP geography i.e. county boundaries and (4 April) in agreeing to revisit opportunity for local resolution with GBSLEP. Executive Board to discuss once geographies determined. | Chair/Interim Partnership Manager | 2018-12-31 | BEIS has reported that Minister will now determine geographies. 03/04/19 Minister asked LEPs to revisit opportunity to reach agreement locally & meet with him in May to review. The most recent date that Acting Chair has liaised with govt was by letter to BEIS & MHCLG in October 2019. Govt has requested a further position statement on local resolution by 12 Dec 2019. All District Council partners agreed to become Board Directors/Alternates in June 2019, although, as of 4 Dec 2019 Cannock Chase DC has written to former Ministers (Berry & Nahawi) stating a preference to be included in GBSLEP only. A further letter has been received from Ministers (Berry & Nahawi) requesting that LEPs make a further attempt at local resolution and report back by 27 February 2020. A meeting took place between SSLEP and GBSLEP & WLEP Chairs on 19 February 2020 and resulted in a further letter send advising that local resolution was not possible. Ministerial response is now likely to be aligned with the publication of the Devolution White Paper however removal of overlaps continues to be govt policy. MOVE TO ISSUES LOG
Strategic | Strategic 3 | 2018-12-10 | SSLEP PAG risk team | LEP Partnership Manager is retired at end of December 2018 and 3 staff on temporary contracts which finish between May & July 2019. Outcome of LEP Review is still emerging, leading partners to delay a decision to recruit for new LEP Director. Potential gap creates difficulties in delivering in a timely manner on LEP Review and wider LEP work programme. | Economic |  | LEP governance | Exec Board | Executive Board | interim Partnership Manager put in place 3 December 2018 enabling handover. Governance review, including move to incorporated body and a comprehensive review of future secretariat requirements has been undertaken. |  |  |  |  | Interim Partnership Manager put in place 3 December 2018 enabling handover. Governance review, including move to incorporated body and review of secretariat requirements has been undertaken. JD for recruitment of Chief Executive Officer has been agreed by the new LEP Chair. | LEP Chair/Interim Partnership Manager | 2019-03-31 | Option to retain Interim Partnership Manager until end of March 2020 has been put in place by SCC. Work to review resources and future secretariat requirements was completed. Future team was agreed by Board on 18 July 2019 however the lack of partner support to resource the required team presents the most significant risk to the partnership. Partnership Manager is realigning existing resources to support new team requirements where possible & seeking new funding partner arrangements. New Independent Technical Appraisers, a new Programme Manager, the LEP Strategy & Research Officer, Business Engagement Officer (part funded by the Chambers of Commerce partner) and Project Officer are now in place. The Interim Partnership Manager is now progressing the PR and marketing support. CLOSE RISK - appointment of CEO is covered by Risk 8, other team members have been recruited.
Strategic | Strategic 4 | 10/12/.2018 | SSLEP PAG risk team | LEP governance | Partnership decisions are not made in a timely manner causing delays in the ability of the LEP to: respond to threats to project delivery timetables, creating slippage on programme delivery profiles; and act upon opportunities to increase resources to the partnership. |  | Economic | Executive Board |  | A small secretariat and a set of business-led sub-groups are in place, which have clear roles and responsibilities and which operate in accordance with an agreed scheme of delegation, reporting to the Executive Board. |  |  |  |  | The agreed scheme of delegation operates within a clear reporting framework, ensuring decision-making is transparent and accountable. | All Sub Group Chairs | ongoing | A revised Scheme of Delegation was approved at the 18 July Board meeting. Operational Sub-Group review has been completed, with Chairs appointed and revised ToRs for all groups including Audit & Finance Group and Strategic Programme Management Group agreed by Board. In line with the governance deep dive outcomes, PAG has been discontinued and the SPMG role was strengthened. This risk has been mitigated and it is proposed that this risk is CLOSED |  |  |  |  | 2020-03-10 | Closed
Strategic | Strategic 5 | 2018-12-10 | SSLEP PAG risk team | LEP governance | Loss of Executive Board knowledge due to several private sector board members potentially due to rotate in July 2019 |  | Political | Executive Board |  | Executive Board Terms of reference provides an opportunity to reduce a significant turnover of members by enabling members to seek re-nomination to the Board for a second 3 year term. |  |  |  |  | The LEP Review will require four further private sector board members to be added to the board in order to achieve the required private-public balance. The timing of this will further assist in 'staggering' the rotation dates of board members. | Interim Partnership Manager | 2019-06-30 | New Board Member Skills and Experience discussed at 18 July 2019 Board. Advert for new Board Members was issued in September 2019 with a good return. Four new Board Members are now in place . and the recruitment of the new Chair is complete. as this was an internal appointment, one further private sector board Director's place remains under active recruitment and will be filled as soon as possible. . The restructured Board has a broad skills set. New sub group arrangements included 'doubling up' arrangements (through chair and vice chair board appointments) to significantly strengthen resilience going forward. This risk is considered to be fully mitigated and 19 March LEP Board proposed closure. |  |  |  |  | 2020-03-19 | Closed
Strategic | Strategic 6 | 2019-04-11 | Audit & Finance Group | LEP strategy | Delay in receipt of additional £300k Core Funding for 2018/19 & 2019/20 (see Risk ID 2) means that LEP is undertaking work at risk in order to develop the Local Industrial Strategy (LIS) by Government's timetable of December 2019. Any delay in LIS production could impact upon ability to access forthcoming funding incl. UK Shared Prosperity Funds. If the additional Core funds do not arrive in a timely fashion, LEP will need to find funding and resources from else where. |  | Economic | Executive Board |  | See Risk ID2 |  |  |  |  | See Risk ID2 resolution lies in the hands of government/SoS. | LEP Chair/Interim Partnership Manager | Unknown | See Risk ID2 Response to all LEPs required Partnerships to provide position statement on local resolution of geographies issue by 12 December 2019 and now a further position statement by 28 February 2020. Local resolution at this stage would only release £100k. Local Resolution is not possible in SSLEP's case so all funding is likely to be lost. New govt (post election) will determine outcome and any further penalties for non-compliance. LEP Core budget has been protected for use against the LIS (which is essential to drawing down of future funds) which has led to further delay in the staff recruitment due to lack of funds. This funding is no longer available to the LEP. The LEP Board of 19 March 2020 proposed closure of this risk. |  |  |  |  | 2020-03-19 | Closed
Strategic | Strategic 8 | 10.03.2020 | LEP Executive Board | Strategic | Recruitment of CEO – agreements are in place to retain interim CEO until external advertisement for CEO recruitment process is complete. Interim CEO has indicated that they are prepared to stay on a permanent basis subject to recruitment process / or that there will be sufficient time for an effective handover for a new external appointment. | Impact would be potential loss of leadership and/or increased time for new CEO to become effective | Resources | Exec Board | LEP Chair | Close links with SCC HR re JE process. Recruitment process. |  |  |  |  | CEO post has been through Job Evaluation; it will now follow the recruitment process. | Executive Board |  | New CEO, Anne Boyd, has been appointed and is in place from 1st April 2021 |  |  |  |  | 2021-04-01 | Closed
Strategic | Strategic 9 | 12.03.2020 | Audit & Finance Committee | COVID 19 Coronavirus - impact on resources and programme delivery | Delivery Economy |  | SSLEP delivery | Exec Board | Executive Board | Government advice |  |  |  |  | Note Government advice re mitigations. Government process to mitigate against impact on the economy. Internally: apply remote working practices and other government advice to ensure continued working of SSLEP secretariat | Executive Board |  | SSLEP Secretariat has a business continuity plan in place and this is working well so far. The Programme Manager is assessing the impact upon current programme delivery ensuring that 20/21 spend profiles are as accurate as possible and keeping in touch with BEIS on key issues arising. CLOSE RISK - risk is being managed as part of BAU |  |  |  |  | 2020-03-19
GPF | GPF 3 | 2019-04-04 | GPF | Programme delivery | GPF pipeline over-subscribed |  | Economic | Audit & Finance | LA Accountable Body & GPF Steering Group | GPF Steering Group monthly review |  |  |  |  | Utilise GPF panel to consider projects in competitive bidding process as necessary | GPF |  | Likely to be funds decommitted from a previously awarded project. GP fund allocation is utilising other LEP funds for short-term bankrolling. As LGF grant comes to an end, GPF funding will now be limited to funds in the GPF pot, so the amount of funding is dictated. CLOSE Risk |  |  |  |  | 2020-08-19 | Closed
GPF | GPF 4 | 2019-10-01 | GPF | Programme delivery | Liquidation of Pochin as builders appointed for Hilton Garden hotel development part funded via GPF grant. New builders appointed, development as yet incomplete. Additional delay as a result of COVID-19 disruption. | Delay or failure to complete the build would have reputational impact on SSLEP and the loan may not be repaid, reducing the loan funding pot available to future schemes. | Legal / Economic | Audit & Finance | LA Accountable Body & GPF Steering Group | Legal ensuring mitigation measures in place |  |  |  |  | Legal maintaining dialogue with Stoke City Council and their legal representation. | GPF |  | Legal ensuring mitigation measures in place. Letter re Revised Funding Conditions taken to Executive Board 17/10/19. Revised target practical completion date early September 2020 from original profile date of 07/08/2020. 03/11/20 - the Hotel is complete and opened in October with 30 jobs created. CLOSE RISK |  |  |  |  | 2020-08-19 | Closed
CDGD | CDGD 6 | 2016-04-19 | SSLEP PAG risk team | Wider economy | As a result of wider economic trends e.g. economic downturn, there is a possibility of developers being less likely to undertake speculative developments which could have the effect of Programme not meeting its objectives THIS RISK HAS BEEN MERGED WITH RISK 13 TO COVER ALL ECONOMICAL AND POLITICAL CLIMATES WHICH COULD IMPACT THE PROGRAMME BUT OVER WHICH LEP HAS NO CONTROL |  | Economic |  | CDGD PAG | Monthly programme reporting in place for all projects; top risks identified |  |  |  |  | Monthly highlight review at CDGD PAG | All project leads | 2021-03-31 | Active Projects Overview presented at monthly CDGD PAG Recently speculative builds have been completed at Bericote Four Ashes and Meaford. Lichfield Park construction commenced 11 Feb 2019) - PR event held on 18th Feb. Practical Completion is due Q3 2019. Tightening of future funding agreements re timings and clawback will help to mitigate. Revised funding agreement drafted by Legal - to be applied to the 6 new schemes. |  |  |  |  | 2019-09-04 | Closed
CDGD | CDGD 18 | 2018-05-15 | SSLEP PAG risk team | Financial | As a result of assigned schemes delivery timescales slipping, there is a risk that the CDGD planned investment will not be achieved by March 2021, Covid increases this risk. | The impact would be that the LEP fails to deliver its agreed Growth Deal objectives, leading to reputational impact and jeopardising future investment. | Economic | SPMG | SPMG Chair | Profile Finance Report tracker in place; 20/21 quarterly profile in place |  |  |  |  | Quarterly grant spend profiling in place for all CDGD projects. | Simon Ablewhite | 2021-03-31 | There is the potential for i54WE to soak up another £1.7m of underspend (originally more, but i54WE now has £3m GBF funding allocated) if further slippage occurs. In addition to i54WE, the S151 presented a paper to SPMG on 29/10/20, detailing further mitigation via other active LGF schemes that could quickly absorb any underspend. The report was provided to Audit & Finance Committee to provide assurance that mitigation is in place. Further detail was provided by the S151. In January and February 2 key Issues were resolved (Risk 6 CELR and Risk 5 Stoke Flood Alleviation), reducing this risk further. End of Q4 - final LGF contract was signed (S278 agreement meant that funding transfer was immediate). S151 applied freedoms and flexibilities to capital switch remaining underspend/retracted LGF, meaning that LGF is fully spent by March 2021 deadline. |  |  |  |  | 2021-03-31 | Closed
CDGD | CDGD 23 | 2019-08-31 | Finance | Reputation/ regulatory | 3 x Finance audits are taking place in key LEP streams |  | Regulatory |  | Finance leads | Working practices | [7 empty] | Audits have been completed, no issues: LGF and Growth Hub: audited as substantial assurance; Core Funding/Implementation Review: audited as adequate assurance. CLOSE RISK | [5 empty] | Closed
Skills | Skills 1 | 2018-05-24 | ESEG | Advanced Manufacturing Mechanical & Electrical Centres | The provider may not achieve its targets |  | LGF capital re. the Skills Equipment Fund round 1 |  | NSCG | monthly project review in place to March 19 followed by quarterly reviews, project reviewed at monthly S&E management meetings |  |  |  |  | agree any remedial actions with the provider following review | David Poole | 2019-12-31 | The college has achieved its KPIs. Apprenticeship growth 139 (target 132), new learners assisted 87 (target 82) |  |  |  |  | 11.Feb.2020 | Closed
Skills | Skills 2 | 2018-06-12 | ESEG | Embedding Technical Capabilities Project | The provider may not achieve its targets |  | LGF capital re. the Skills Equipment Fund round 1 |  | Staffordshire University | monthly project review in place to March 19 followed by quarterly reviews, project reviewed at monthly S&E management meetings |  |  |  |  | agree any remedial actions with the provider following review | David Poole | 2019-12-31 | The university has significantly exceeded its KPIs. Apprenticeship growth 751 (target 387), new learners assisted 0 (target 0) |  |  |  |  | 2020-02-11 | Closed
Skills | Skills 3 | 2018-06-28 | ESEG | Technical & Curriculum Development Project | The provider may not achieve its targets |  | LGF capital re. the Skills Equipment Fund round 1 |  | Stoke-on-Trent College | monthly project review in place to March 19 followed by quarterly reviews, project reviewed at monthly S&E management meetings |  |  |  |  | agree any remedial actions with the provider following review | David Poole | 2019-12-31 | The college has achieved its KPIs. Apprenticeship growth 155 (target 75), new learners assisted 779 (target 155) |  |  |  |  | 2020-02-11 | Closed
Skills | Skills 4 | 2018-08-15 | ESEG | Delivery of outputs | Manufacturing Excellence Centre The provider may not achieve its targets |  | LGF capital re. the Skills Equipment Fund round 1 | SPMG | Perkins Engines Stafford | monthly project review in place to March 19 followed by quarterly reviews, project reviewed at monthly S&E management meetings |  |  |  |  | agree any remedial actions with the provider following review | David Poole | 2019-12-31 | Perkins has fallen short of its KPIs. Apprenticeship growth 22 (target growth 32), new learners assisted 8 (target 200). Note. New learners not counted towards govt. targets. The project will continue to be monitored until targets are achieved. Risk of a drop in learner numbers following COVID-19 situation. SEF 1 as a whole has exceeded its targets and SEF 1 and SEF 2 are reported to BEIS as one project. Perkins outputs will be managed as an issue within the SEF programme but the risk will be removed from LEP reports. Any subsequent outputs to be delivered by SEF 1 will be included in SEF 2 figures. Both rounds are reported as one figure to BEIS. |  |  |  |  | 2019-12-04 | Closed
Skills | Skills 5 | 2018-12-13 | ESEG | Delivery of outputs | The Cannock Engineering Academy There is a risk that Covid may impact the output level of apprenticeships due to furlough, redundancy etc. | KPI targets may not be met which could result in a shortfall in outputs. | Reputation | SPMG | South Staffordshire College | monthly project review in place to March 19 followed by quarterly reviews, project reviewed at monthly S&E management meetings |  |  |  |  | Agree any remedial actions with the provider following review. | David Poole | 2020-09-30 | KPI measurement Sept 20. Monitor periodic reports to gain insight into the impact. A mitigating factor is that SEF round 1 and Round 2 are both reported as one scheme to BEIS. As Round 1 greatly exceeded its targets, this will help to mitigate any shortfall in Round 2. November: The project has exceeded its KPI targets for Sept 20 - Apprenticeship growth target 60 actual 61, new learners target 91 actual 247. CLOSE RISK |  |  |  |  | 2020-11-03 | Closed
Skills | Skills 6 | 2018-11-13 | ESEG | Delivery of outputs | The Hybrid Construction Technology Project There is a risk that Covid may impact the output level of apprenticeships due to furlough, redundancy etc. | KPI targets may not be met which could result in a shortfall in outputs. | Reputation | SPMG | NSCG | monthly project review in place to March 19 followed by quarterly reviews, project reviewed at monthly S&E management meetings |  |  |  |  | Agree any remedial actions with the provider following review | David Poole | 2020-09-30 | KPI measurement Sept 20. Monitor periodic reports to gain insight into the impact. A mitigating factor is that SEF round 1 and Round 2 are both reported as one scheme to BEIS. As Round 1 greatly exceeded its targets, this will help to mitigate any shortfall in Round 2. November: The project has exceeded its KPI targets for Sept 20 - Apprenticeship growth target 173 actual 194, new learners target 135 actual 205. CLOSE RISK | B - Moderate | 3 - Possible |  |  | 2020-11-03 | Closed
Skills | Skills 7 | 2018-12-04 | ESEG | Delivery of outputs | The Academy of Technology & Digital Skills There is a risk that Covid may impact the output level of apprenticeships due to furlough, redundancy etc. | KPI targets may not be met which could result in a shortfall in outputs. | Reputation | SPMG | Stoke-on-Trent College | monthly project review in place to March 19 followed by quarterly reviews, project reviewed at monthly S&E management meetings |  |  |  |  | Agree any remedial actions with the provider following review | David Poole | 2020-09-30 | KPI measurement Sept 20. Monitor periodic reports to gain insight into the impact. A mitigating factor is that SEF round 1 and Round 2 are both reported as one scheme to BEIS. As Round 1 greatly exceeded its targets, this will help to mitigate any shortfall in Round 2. November: The project has mixed performance against its KPI targets for Sept 20 - Apprenticeship growth target 52 actual 44, new learners target 104 actual 1076. CLOSE RISK | B - Moderate | 3 - Possible |  |  | 2020-11-03 | Closed
FG | FG 1 | 2018-06-12 | LEP Funding Group | Financial | Failure to spend the allocated 2018/19 budget before the year end. |  | Economic |  | LEP Funding Group | LEP Funding Group scheduled to meet monthly to review all activities |  |  |  |  | Some projects require CF such as Mgt and Admin to cover LEP staff payment, and Careers Co that runs by school calendar not the financial year. | Chris McCann | Complete | Reviewed at monthly Funding Group January A&F Group consider this risk to be "In Control", allocation will not be spent, however, funding can be rolled over, without risk. No longer risk as now clawback on funding. |  |  |  |  | 2019-03-13 | Closed
FG | FG 2 | 2018-06-12 | LEP Funding Group | Financial | The risk of allocating funding to projects that are not in line with LEP priorities. |  | Economic | Audit & Finance | LEP Funding Group | LEP Funding Group scheduled to meet monthly to review all activities |  |  |  |  | Operate a scheme of delegation and developed the LIS. | LEP CEO | Ongoing | Reviewed at monthly Funding Group. Scheme of Delegation was signed at the LEP Executive 18/7/19 |  |  |  |  | 2020-03-18 | Open
FG | FG 3 | 2018-06-12 | LEP Funding Group | Financial | The risk of allocating £25,000 to the Careers Co for 2018/19 and they will not spend the allocation having carried forward £11,415.31 from 2017/18. |  | Economic | Audit & Finance | LEP Funding Group | LEP Funding Group scheduled to meet monthly to review all activities |  |  |  |  | The Careers Co carry over relates to original commencement of claims over the academic year straggling our financial year. | Jacqui Casey | Ongoing | £11,413 has now been utilised + £6,000 of new allocation |  |  |  |  | 2019-11-13 | Closed
FG | FG 4 | 2018-06-12 | LEP Funding Group | Financial | Concerns that the Core funds are funding 2 year projects without the certainty that we have future funding. |  | Economic | Audit & Finance | LEP Funding Group | LEP Funding Group scheduled to meet monthly to review all activities |  |  |  |  | Reviewed what funding goes against in line with LIS delivery. Worked over course of year for funding post 2020/21. | John Broad | Ongoing | Reviewed at monthly Funding Group |  |  |  |  | 2020-03-18 | Open
FG | FG 5 | 12//6/2018 | LEP Funding Group | Governance | Ensure governance is in place and applicants confirm via funding request form. |  | Legal | Audit & Finance | LEP Funding Group | LEP Funding Group scheduled to meet monthly to review all activities |  |  |  |  | Form updated. Checks to be carried out by Jacqui Casey/Sharon Palphreyman/Sam Hicks and report back to Funding Group | LEP CEO | Ongoing | Amended form in use |  |  |  |  | 2020-03-18 | Open
FG | FG 6 | 2018-06-12 | LEP Funding Group | Governance | Making allocations prior to business case approvals e.g. Industrial Strategy, ME DIT Challenge Fund. |  | Legal | Audit & Finance | LEP Funding Group | LEP Funding Group scheduled to meet monthly to review all activities |  |  |  |  | Prompt submission of forms To be brought to immediate attention of the Funding Group. Scheme of Delegation includes an annual process for all project development activity. | LEP CEO | Ongoing | Scheme of Delegation was signed on 18/7/2019 |  |  |  |  | 2020-03-18 | Open
FG | FG 7 | 2018-08-21 | LEP Funding Group | Governance | Uncertainty of LEP Review and ability to allocate funds going forward. |  | Political |  | LEP Funding Group | LEP Funding Group scheduled to meet monthly to review all activities |  |  |  |  | To get further guidance from HM Government. | Jacqui Casey | 2019-03-31 | Awaiting outcome of LEP Review geography Position to be reviewed at April Funding Group |  |  |  |  | 2019-04-11 | Closed
FG | FG 8 | 2019-02-06 | LEP Funding Group | Governance | Lack of cash limiting ability to fund pipeline projects emerging from the LIS. | Reputational risk of non-delivery may impact on size of future funding allocations. | Financial/ reputational | Audit & Finance | LEP Funding Group | LEP Funding Group scheduled to meet monthly to review |  |  |  |  | Comprehensively reviewed our governance. | LEP CEO | Ongoing | To be monitored, discussed and the level of risk reviewed at the next funding meeting. CLOSED - The budget Jacqui set aside was for the development of the LIS itself (for example, if we needed any consultancy work etc.) not for any projects emerging out of it. As I understand it, the projects themselves wouldn’t be funded by core budget, but by any funding schemes that were allocated to the LEP. |  |  |  |  | 2020-09-28 | Closed
FG | FG 13 | 2019-11-13 | LEP Funding Group | Financial | LEP Review & Implementation Grant not being fully received. JC commented it is already detailed as Risk No 6 on the Strategic Risk Register |  | Economic |  |  | LEP Funding Group scheduled to meet monthly to review all activities |  |  |  |  | Managed within the Strategic Risk Register (see comment under Risk Statement) | Jacqui Casey | Ongoing | Managed within the Strategic Risk Register. CLOSED This funding is no longer available to the LEP. The LEP Board of 19 March 2020 proposed closure of Strategic Risk 6. |  |  |  |  | 2020-03-18 | Closed
ESIF | ESIF 1 | 2019-01-31 | Nigel Senior | Financial | There is a risk of not reaching full commitment of ERDF by the Spring ERDF call. Currently we have about £17.9m still to commit and whilst we know where most of this could go bids still have to be submitted by partners and progressed through the ERDF gateway assessment. Any residual allocation left after this call will be returned to DCLG for a nation-wide call and lost to addressing local priorities. |  | Economic |  | Nigel Senior | Regular review at ESIF sub-committee |  |  |  |  | Given the emergence of key projects at Keele, i54 and Spode the bids have to be ready for the last call expected in May/June 2019 | Nigel Senior | 2019-06-30 | Outline bids received for Keele, i54 and Spode. Risk closed (it has, in part, materialised) |  |  |  |  | 2019-10-01 | Closed
ESIF | ESIF 2 | 2019-01-31 | Nigel Senior | Financial | There is a risk of not reaching full commitment of remaining ESF allocation due to the LEP not being invited forward for a second phase of the DWP Opt in co-financing programme. |  | Economic |  | Nigel Senior | Regular review at ESIF sub-committee |  |  |  |  | Approximately £21.2 m depends on extensions being agreed with ESFA & Big Lottery Opt In programmes As there is no second phase of DWP more resource can be put into Big Lottery and ESFA along with a range of local open call projects | Nigel Senior | 2019-06-30 | Outside of the Opt Ins, the SSLEP ESIF Committee has been asked to inform DWP about priorities for a final (Summer 2019) Open Call for bids. Close risk - we are progressing new calls for ESF |  |  |  |  | 2020-04-14 | Closed
ESIF | ESIF 3 | 2019-04-04 | Nigel Senior | Financial | There is a risk regarding funding profile of projects and the programme as a whole as partners encounter challenges in delivering their projects and have to make adjustments. |  | Economic |  | Nigel Senior | Regular review at ESIF sub-committee |  |  |  |  | Monitor. The mid programme stage spend target at December 2018 has been achieved. | Nigel Senior |  | Continue to monitor. Close risk - this has been taken over by Covid-19 |  |  |  |  | 2020-04-14 | Closed
ESIF | ESIF 4 | 2019-12-06 | Mark Connell | Financial | The ERDF Programme despite a strong final local call for projects has been unable to allocate its full £90M allocation and £7M will be returned to a National Reserve Pot. It is important that the LEP continues to identify its priorities/projects which could be supported by ERDF for which a National Call is planned around April/May 2020. |  | Economic |  | Mark Connell | Updates through ESIF Committee and TA to action |  |  |  |  | Need to ensure that committed monies are defrayed and that any new funding opportunities are maximised. | Mark Connell | 2020-05-01 | Technical Assistance Team to aid any project development to take advantage of future funding opportunities. This risk only applies pre covid as the National call isn't going to happen - risk closed. |  |  |  |  | 2020-04-14 | Closed
ESIF | ESIF 5 | 2020-04-14 | Nigel senior | Financial | Plans to allocate remaining ESIF allocations for LEP areas through ERDF and ESF National Reserve Fund calls have now been put on hold in favour of re-orientating remaining funds to align with national priorities. There is a spend deadline attached to these of March 2021. | The impact is that the spend deadline may not be met and funding may be lost. | Economic | Audit & Finance | Nigel Senior | Updates through ESIF Committee and TA to action |  |  |  |  | Need to follow emerging guidance on re-orientation of ESIF funds and ensure government priorities benefit the SSLEP area. The delivery primarily through the Growth Hub has to gear up quickly to ensure that these funds are defrayed within the LEP Geography by the said date | TA Team | Ongoing | Continue to monitor using ERDF process and advise via ESIF Committee and SSLEP Executive Board 03/02/21 - MC advised that this risk can now be closed |  |  |  |  | 2020-11-02 | Closed
CDGD | CDGD 2 | 2016-04-19 | SSLEP PAG risk team | Programme delivery | As a result of failure of the vital few projects to deliver, which are concentrated within very few organisations / applicants, there is a possibility of significant impact on the deliverability of programme outcomes, which would have the effect of the overall programme being unable to attain the stated benefits agreed by Government within the time frame, spend / underspend. Covid-19 increases the risks of non-delivery. |  | Reputation/ Financial | SPMG | SPMG Chair | Frequent in depth reviews / attendance at project boards carried out on all key programmes |  |  |  |  | Programme of regular reviews of all key projects in place. Reporting back to SPMG | LEP CEO | 2021-03-31 | Risk Accepted Regular reviews / project board dates schedule in place and in progress Outcomes dashboard produced to highlight potential areas of concern. |  |  |  |  | 2020-07-14 | In Control
CDGD | CDGD 22 | 2019-08-20 | SSLEP PAG risk team | Programme/ Reputational | There is a risk that 4 schemes (2 of which are very large) in the current programme may fail to progress. This could severely impact on the LEP's ability to spend the LGF grant and to attain the required outputs. |  |  |  | CDGD PAG | [5 empty] | Keep PAG and Exec Board aware of slippage, delays and risk of underspend. Work closely with project leads to keep sight of progress, issues and risks. | SA/SP | 2019-11-30 | - Churnet Works has now withdrawn (21/08/19). - CCAP -following the LGF review May 2020, LGF funding has been redirected to i54WE. Alternative funding sources will be allocated to this scheme. - CELR business case was approved by Exec Board subject to T&C's and Monitoring Plan including penalty milestones - these have been contracted. Funding agreement now signed - Etruria Valley - All elements of the business case have been APPROVED by DfT. Funding agreement has been drafted and signed. Although Covid is still a risk, these schemes are now contracted and will be monitored in the usual way. CLOSE RISK |  |  |  |  | 2020-07-14 | Closed
CDGD | CDGD 25 | 2020-03-20 | SSLEP | Finance/ Delivery | Covid-19 - Live schemes: impact on programme delivery; impact on schemes' ability to spend LGF grant within deadline if work is delayed or halted. Pending schemes: sponsors are nervous of signing up to milestones and spend profiles which will in most cases be impacted by Covid-19 | [9 empty] | Engage with BEIS - push for extension of timescales for spend Lobby ministers Engage with support groups such as LEP network | JC/SP/ LEP Chair |  | All except 2 smaller schemes are now contracted. Spend forecasts for 2020/21 have been provided by all schemes and approved by BEIS as part of a review. Partial funding has been redirected from CELR and remaining funding from CCAP, this has been redirected to i54WE. Alternative funding sources (eg business rates uplift from i54 and CVEZ) will be redirected to CELR and CCAP. Progress of schemes will be monitored and any slippages reported to SPMG. RISK CLOSED |  |  |  |  | 2020-07-14 | Closed
CDGD | CDGD 1 | 2016-04-19 | SSLEP PAG risk team | Resourcing | As a result of insufficient or inappropriate resources being assigned to projects, there is a possibility delivery may be delayed, which would have the effect of uncertainty, slippage and inability to attain stated benefits |  | Political |  | CDGD PAG | Monthly programme reporting in place for all projects; top risks identified |  |  |  |  | Monthly highlight review at CDGD PAG | All project leads | 2021-03-31 | Active Projects Overview presented at monthly CDGD PAG Resourcing issues not raised as being a current issue. Any future slippage will be reported to SPMG. RISK CLOSED |  |  |  |  | 2020-07-14 | Closed
CDGD | CDGD 4 | 2016-04-19 | SSLEP PAG risk team | Contracts | As a result of failure to contract projects to deliver and / or slippage of funding approvals, there is a possibility of failing to deliver projects and outputs within the agreed time frame or budget |  | Legal |  | CDGD PAG | Funding tracker in place to highlight status / progress or all agreements |  |  |  |  | Regular review with Legal lead in place | Programme Manager | 2021-03-31 | All except 2 smaller schemes have now been contracted (total of outstanding contracts is now just£1.35m). All LGF funding has been allocated. An additional scheme has been contracted which can soak up any further slippage of funding. RISK CLOSED |  |  |  |  | 2020-07-14 | Closed
CDGD | CDGD 5 | 2016-04-19 | SSLEP PAG risk team | Programme Allocation | As a result of Programme allocation only up to 100%, there is a possibility of no over programming to allow for slippage / project changes, which would have the effect of Programme being unable to recover from slippages / failure of individual project deliverables |  | Political |  | CDGD PAG | Reviewed monthly at CDGD PAG |  |  |  |  | Review to identify all additional projects that can be brought forward in progress GD3 bid included basket of schemes Open call to refresh pipeline held December 2017 Further open call held September 2018 | Jacqui Casey | 2021-03-31 | Feb 2020 - an additional scheme has been contracted (i54 Western Extension) which would be able to mop up, up to £10m of slippage RISK CLOSED |  |  |  |  | 2020-07-14 | Closed
CDGD | CDGD 7 | 2016-04-19 | SSLEP PAG risk team | Project mix | As a result of not having the right mix of focused projects, there is a possibility of the Programme not being able to deliver the agreed outputs, which could have the effect of the Programme missing its energy, housing, jobs, skills targets |  | Economic |  | CDGD PAG | All GD3 submissions assessed against Strategic fit; Value for money; Deliverability criteria |  |  |  |  | GD3 schemes agreed; additional basket of alternative schemes also identified | Jacqui Casey | 2021-03-31 | All funding has now been allocated - only 2 small contracts left to complete and if either or both fail, i54WE has capacity to mop up an slipped funding. RISK CLOSED |  |  |  |  | 2020-07-14 | Closed
CDGD | CDGD 8 | 2016-04-19 | SSLEP PAG risk team | Relationship Management | As a result of a significant proportion of the Programme being reliant upon private sector developers, without a robust relationship management there is a possibility that developers do not perform according to contract, which would have the effect of the Programme missing its energy, housing, jobs, skills targets |  | Social |  | CDGD PAG | Monthly programme reporting in place for all projects; top risks identified |  |  |  |  | Monthly highlight review at CDGD PAG | All project leads | 2021-03-31 | Risk Accepted Hatch Regeneris have been recruited to appraise business cases and also to review process and literature pertaining to the funding allocation process. Tighter clawback arrangements in the funding agreement and the inclusion of spend and milestone monitoring plans in the funding agreements. Regular monitoring of scheme delivery and outputs via comms between Programme manager and scheme leads.. Concerns or issues would be escalated to SPMG. RISK CLOSED |  |  |  |  | 2020-07-14 | Closed
CDGD | CDGD 9 | 2016-04-19 | SSLEP PAG risk team | Programme Governance | As a result of no robust appraisal of business cases or lack of expertise to challenge projects and oversee delivery, there is a possibility of the Programme underperforming, which would have the effect of overspends / underspends / under achievement of outputs |  | Social |  | CDGD PAG | All business case submissions are assessed against: - SSLEP Full Business Case Assessment template - "green book guidance checklist for assessing business cases" |  |  |  |  | All business cases to be reviewed prior to presentation at CDGD PAG | Jacqui Casey | 2021-03-31 | Meetings arranged with all business case leads ahead of submission to CDGD PAG SSLEP Full Business case Assessment template introduced January 2017 All business cases independently assessed before presentation to CDGD PAG Lessons learned analysis being introduced Take into account an applicant's previous or current delivery of CDGD funded schemes. Lessons Learned to be recorded as part of programme management/project closure RISK CLOSED |  |  |  |  | 2020-07-14 | Closed
CDGD | CDGD 15 | 2018-05-15 | SSLEP PAG risk team | LGF Funding | As a result of a number of projects not progressing to original timescale, there is a possibility that the 19/20 and 20/21 LGF funding profile will be significantly underspent, which would have the affect of future LGF funding being cut back |  | Economic |  | CDGD PAG | 2018/19 Profile Finance Report tracker in place; quarterly profile in place |  |  |  |  | Quarterly profiling in place for all CDGD projects. Early identification of current pipeline projects to alternatively fund from grant slippage | Simon Ablewhite | 2019-04-30 | An additional scheme, i54 WE, has been contracted Feb 2020, to mitigate against any significant delay or failure. A full review of spend forecast for 20/21 was undertaken in response to a BEIS review of LGF allocation. Funding has been removed from 2 schemes (it will be replaced with alternative funding eg business rates uplift) and redirected to i54WE. There is the potential for i54WE to soak up another £4m approx if further slippage occurs. BEIS is satisfied with the Review. RISK CLOSED |  |  |  |  | 2020-07-14 | Closed
CDGD 16 | CDGD 16 | 2018-05-15 | SSLEP PAG risk team | Contracts | As a result of no deadlines and/or weak clawback clauses in the funding agreement, there is a possibility that failing schemes cannot be withdrawn in a timely manner, which would have the affect of blocking potential investment in other 'ready to go' schemes that can could deliver same or enhanced outputs |  | Legal |  | CDGD PAG | Monthly programme reporting in place for all projects; top risks identified |  |  |  |  | Standard funding agreement template in place, agreed with Legal team Programme consultant reviewing effectiveness of template | Dave Nicholls | 2019-03-31 | All GD1,GD2 and majority of GD3 funding agreements already in place A review of existing template has been carried out by programme consultant. The funding agreement has now been redrafted by Legal, to tighten clawback and delivery timescales. This will be applied to the 4 new schemes from the Open Call and the 2 schemes that have been approved for reallocation of ROF Featherstone funding.. An additional scheme has been contracted to mitigate underspend or failure of schemes. Funding agreement for the delayed CELR, scheme includes a spend/milestone monitoring plan, linked to financial penalties for slippage. All funding allocated and final 2 schemes are in draft contract stage. RISK CLOSED |  |  |  |  | 2020-07-14 | Closed
CDGD | CDGD 17 | 2018-05-15 | SSLEP PAG risk team | Communication | As a result of lack of visibility / understanding of availability of LEP funding sources, there is a possibility that weaker schemes will be considered for inclusion in the CDGD programme, at the expense of unknown stronger candidates, which would have the affect of the LEP failing to maximise its forecast outputs |  | Political |  | CDGD PAG | SSLEP website details assurance framework. Open call comms distributed widely via email, website and social media |  |  |  |  | Ensure effective, timely and widely distributed communications in place for pipeline submission requests | Jacqui Casey | 2021-03-31 | Growth deal funding open call communications to be distributed widely Annual assurance framework review completed Sept 2019 Open Call process has been revised (March 2020) and will be updated in the Assurance Framework. RISK CLOSED |  |  |  |  | 2020-07-14 | Closed
10 | 10 | 2016-04-19 | SSLEP PAG risk team | Performance Measurement | As a result of inadequate systems in place to capture, monitor & report programme performance, there is a possibility of being unable to accurately measure progress and stated benefits, which would have the effect of inaccurate reporting |  | Technological |  | CDGD PAG | Standard template in place for monthly project reporting |  |  |  |  | Monthly project highlight reporting | Dave Nicholls | 2018-05-15 | Monthly reporting summarised for CDGD PAG; full reports available on request Outputs monitored monthly; request to Gestamp to ensure Bericote jobs outputs - data now received No longer a key risk to the programme |  |  |  |  | 2020-07-14 | Closed
11 | 11 | 2016-05-24 | SSLEP PAG risk team | LGF Funding | There is a risk that the 16/17 LGF funding profile will be significantly underspent. As a result of a number of projects not progressing to original timescale there is a possibility of future LGF funding being cut back if current years profile is not met |  | Economic |  | CDGD PAG | 2016/17 Profile Finance Report tracker in place; quarterly profile in place |  |  |  |  | Quarterly profiling introduced for all projects. Review to identify areas that can be brought forward in progress (see also Risk ID 5) | Simon Ablewhite | 2017-05-08 | Monthly reporting to CDGD PAG Project Slippage schemes identified and included within 16/17 LGF programme Overall 16/17 outcome = £0.245m (0.7%) slippage Given GD3 funding profile from Gov't; potential 17/18 could have similar risk |  |  |  |  | 2020-07-14 | Closed
12 | 12 | 2017-05-22 | SSLEP PAG risk team | LGF Funding | There is a risk that the 17/18 LGF funding profile will be significantly underspent. As a result of a number of projects not progressing to original timescale and GD3 profile from DCLG larger than expected for 17/18, there is a possibility of future LGF funding being cut back if current years profile is not met |  | Economic |  | CDGD PAG | 2017/18 Profile Finance Report tracker in place; quarterly profile in place |  |  |  |  | Quarterly profiling in place for all projects. Early identification of pipeline projects London Mill, Leek schemes & Rugeley Town Centre Ph 2, identified as projects that will not progress | Simon Ablewhite | 2018-04-30 | Initial report and outlook to June CDGD PAG Executive Group (Oct 17) agreed to run an open call for initiatives to refresh pipeline and identify suitable alternative schemed; recommendations to be presented to Exec Group February 2018 Exec Group approved SME Expansion Support business case, February 2018; to be utilised to ensure 17/18 spend profile met |  |  |  |  | 2020-07-14 | Closed
CDGD | CDGD 19 | 2018-07-25 | SSLEP PAG risk team | Programme Governance | As a result of the current national review of LEPs, there is a possibility of uncertainty around the future of the CDGD programme in general, which would have an impact on governance, programme investment and outputs |  | Political |  | CDGD PAG | Regular reviews at regional & national level SSLEP Executive Board responsible for determining local submission |  |  |  |  | LEP network; national and regional | Jacqui Casey | 2019-03-31 | Regular dialogue at regional & national level RISK CLOSED |  |  |  |  | 2020-07-14 | Closed
CDGD | CDGD 20 | 2019-08-20 | SSLEP PAG risk team | LGF funding | Very low LGF spend in Q1 2019/20. There is a risk that uncertainty around the spend profile of some schemes (e.g. City Centre Access Programme) will result in poor visibility of spend profile and an accrual of unspent funds. |  | Reputational |  | CDGD PAG | Quarterly finance review of all scheme spend. Monthly reporting to PAG. |  |  |  |  | Deadlines to be applied to schemes that are not progressing. | SA/SP | 2019-11-30 | An additional scheme, i54 WE, has been contracted Feb 2020, to mitigate against any significant delay or failure. A full review of spend forecast for 20/21 was undertaken in response to a BEIS review of LGF allocation. Funding has been removed from 2 schemes (it will be replaced with alternative funding eg business rates uplift) and redirected to i54WE. There is the potential for i54WE to soak up another £4m approx if further slippage occurs. BEIS is satisfied with the Review. RISK CLOSED |  |  |  |  | 2020-07-14 | Closed
CDGD | CDGD 24 | 2019-12-12 | SSLEP Executive Board | Finance/ Delivery | A new independent technical appraiser has been procured and contracted on a lower contract value than the previous appraiser. As we don't have sight of future demand there is a risk that volume of work may exceed the contract value, increasing costs |  |  |  |  | Call-off Contract - we pay for services as we use them, no retainer fee. |  |  |  |  | Monitor usage of the contract | SPMG | 2022-08-01 | Monitoring contract in line with Procurement rules. Ringfence additional resources to mitigate any additional costs in case further work needs to be procured.. Costs will be addressed as and when required. RISK CLOSED |  |  |  |  | 2020-07-14 | Closed
CDGD | CDGD 3 | 2016-04-19 | SSLEP PAG risk team | Communication | As a result of lack of or poor communications between delivery teams, partners and CDGD Board, both internally & externally, there is a possibility of bypassing established governance framework and loss of focus on deliverables, which would have the effect of overspend / underspend of expenditure, lack of clear management and lack of accountable governance |  | Political |  | CDGD PAG | Monthly programme reporting in place for all projects; top risks identified |  |  |  |  | Monthly highlight review at CDGD PAG. CDGD PAG restructured to focus on assurance and strategic areas | All project leads | 2021-03-31 | Risk Accepted Areas of concern escalated to Strategic Board as necessary Channels of communication working well, Strategic Board focus being reassessed Regular reporting in place. Scheme of delegation manages escalation of any issues. RISK CLOSED |  |  |  |  | 2020-07-14 | Closed
CDGD | CDGD 14 | 2018-05-15 | SSLEP PAG risk team | Performance Measurement | As a result of over optimism of benefits achievement, there is a possibility of the CDGD programme over estimating the forecast benefits, which would have the affect of the programme missing agreed LEP targets |  | Economic |  | CDGD PAG | Quarterly review of all scheme outputs, coincide with national LGF reporting |  |  |  |  | Individual scheme review of outputs with all project leads. Report back to CDGD PAG | Dave Nicholls | 2021-03-31 | Monthly highlight reporting in place. Quarterly review of all outputs in place; regular feedback from scheme leads. Output forecasts are reviewed annually in Q1 with schemes sponsors. RISK CLOSED - this is an issue - see Issue 2 |  |  |  |  | 2020-07-14 | Closed
CDGD | CDGD 21 | 2019-08-20 | SSLEP PAG risk team | Programme delivery | Based on current outputs estimates, there is a risk that the SSLEP may not achieve its output targets of 5000 jobs and 1000 houses by March 2021. As failure to deliver outputs in previous years is rolled forward, the forecasts for future years are becoming less achievable. Delays due to Covid increase this risk. | This could result in reputational damage and could impact on future funding allocation from central government. | Reputation | SPMG | SPMG Chair | Review forecasts regularly (in line with Outputs Monitoring best practice guidance) with scheme leads. |  |  |  |  | Quarterly reports are taken to SPMG and to Exec Board. | SA/SP | 2019-11-30 | Quarterly output reporting is taken to Audit & Finance Group, SPMG and Executive Board. Forecasts are revised annually in Q1. The Outputs report taken to Board in May 2020 showed how forecasts have slipped year on year, leaving some key schemes with a potentially unachievable delivery target. Recommendations to be taken to SPMG/Board. CLOSE RISK - THIS HAS NOW BECOME AN ISSUE |  |  |  |  | 2020-07-14 | Open

## Risk Matrix
Risk Matrix |  |  | <----------------------------------- IMPACT ------------------------------------->
| A - Minor | B - Moderate | C - Major | D - Critical | E - Catastrophic
5 - Almost certain | Low | Medium | High | High | High
4 - Likely | Low | Medium | Medium | High | High
3 - Possible | Low | Medium | Medium | High | High
2 - Unlikely | Low | Low | Medium | Medium | High
1 - Rare | Low | Low | Low | Medium | Medium

## Summary analysis (hidden)
RISKS
| Red | Amber | Green | Total
Board | 3 | 6 | 1 | 10
Audit & Finance | 1 | 10 | 1 | 12
SPMG | 0 | 12 | 0 | 12
| 4 | 28 | 2 | 34
ISSUES | Severe | Moderate | Minor | Total
Board | 2 | 1 | 0 | 3
Audit & Finance | 0 | 0 | 0 | 0
SPMG | 0 | 0 | 0 | 0
GPF Panel | 0 | 1 | 0 | 1
| 2 | 2 | 0 | 4
RISKS
| Red | Amber | Green | Total
Strategic | 4 | 8 | 1 | 13
CDGD | 0 | 2 | 0 | 2
GPF | 0 | 2 | 1 | 3
Funding Group | 0 | 1 | 0 | 1
ESIF | 0 | 5 | 0 | 5
GBF | 0 | 10 | 0 | 10 | RISKS
SSLEP | 4 | 28 | 2 | 34 |  | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | Jul/Aug -21
[5 empty] | Red | 6 | 3 | 4 | 3 | 3 | 3 | 4 | 6 | 4
[5 empty] | Amber | 15 | 14 | 14 | 14 | 17 | 17 | 21 | 24 | 28
[5 empty] | Green | 3 | 3 | 4 | 4 | 4 | 2 | 2 | 2 | 2
ISSUES
| Red | Amber | Green | Total
Strategic | 1 | 1 | 0 | 2
CDGD | 1 | 0 | 0 | 1
GPF | 0 | 1 | 0 | 1
Funding Group | 0 | 0 | 0 | 0
ESIF | 0 | 0 | 0 | 0
GBF | 0 | 0 | 0 | 0
| 2 | 2 | 0 | 4
Risks | Board | Audit & Finance | SPMG
Red | 3 | 1 | 0 | 4
Amber | 6 | 10 | 12 | 28
Green | 1 | 1 | 0 | 2
34
ISSUES
[6 empty] | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | Jul/Aug -21
[5 empty] | Red | 2 | 3 | 4 | 2 | 2 | 2 | 2 | 2 | 2
[5 empty] | Amber | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
[5 empty] | Green | 0 | 0 | 0 | 2 | 2 | 1 | 0 | 0 | 0