## GBF Projects - progress
Getting Building Fund - Q4 2020/21
Getting Building Fund Q2 2021/22 |  | District | Total GBF spend to date | Total GBF spend forecast by end March 2022 | GBF- current UNDERSPEND (completed schemes) | STATUS | Progress/Commentary | Overall RAG rating/ Summary
Drakelow Park | A strategic development in South Derbyshire that will accommodate 2,000 houses and 30ha of employment land. The scheme has transport implications for East Staffordshire and the project is a new road bridge that will facilitate the development. This scheme is also being supporting by the D2N2 LEP. | South Derbyshire/ East Staffordshire | 0 | 0 |  | De-allocated | A meeting took place on 29/06/21 between the SSLEP and D2N2 CEOs, S151s, Programme managers and BEIS Area Leads for both areas. It was agreed that to de-risk the scheme for SSLEP and to enable efficiencies and better control of the project for D2N2, a proposal would be put forward to de-allocate the £5m GBF from SSLEP and re-allocate it to D2N2, subject to legal assurances being in place between SSLEP and D2N2. A paper was taken to SSLEP SPMG and then to Executive Board; the submission of a change request to MHCLG was subsequently approved. A legal assurance agreement between SSLEP and D2N2 is pending. | Reduced from Red to Amber - deallocation now approved by MHCLG
Health Innovation Centre, Blackheath Lane | This project provides both physical and sector-leading digital capabilities to accelerate the much-demanded transformation of the health workforce to. This new capability incorporates advanced digital simulation and immersion suites enabling healthcare professionals to explore and develop new techniques whilst collaborating with on-campus students. This facility will enable the teaching of advanced techniques and the required digital skills to support the future needs of our health sector. Project is currently paused due to COVID19, we are seeking the opportunity to reinstate. | Stafford (Staffordshire University) | 2889500 | 2889500 |  | In progress | The project is at week 52 out of revised 61 weeks. The new completion date will now be moved to the last week of November 2021 subject to delivery and progress on-site. The progress on-site is taking shape with internal walls erected and 1st fix fully completed. All cladding and masonry are now fully complete. All cement boarding, insulation, decorative masonry, external doors, windows, and atrium glazing are now fully completed. The building iwas watertight as of 30th August 2021. A business case for the development of the staffing infrastructure for the Centre for Health Innovation is being developed to ensure the delivery of the university and LEP KPI’s. A suite of short courses and CPD are being developed along with masters level courses that will play to the key strengths of CHI as well as meet several of the KPI targets. A promotional brochure is in development outlining how the CHI can be utilised by the wider health and business economy as well as a web presence. | All GBF spent. Progressing well
i54 Western Extension | The phase 2 extension to i54 is currently being built and physical plot preparation works are due to complete during 2021. Funding for the project is provided by SSLEP and BCLEP and with prudential borrowing by Staffordshire County Council and City of Wolverhampton Council who together with South Staffordshire Council form a highly successful joint venture partnership. Accelerated project funding allows the maximum financial flexibility for the joint venture funding local authorities in managing their capital programme budgets going forward at a time of significant financial challenges. | South Staffordshire | 3000000 | 3000000 |  | In progress | GBF fully spent. Outputs will be reported through LGF returns to BEIS. | All GBF spent. Progressing well.
Innovation Centre Seven | Innovation Centre Seven (IC7) comprising 4,820sqm of BREEAM excellent innovation space at the Keele Growth Corridor University Enterprise Zone. Planning permission is approved and £14.2m of the £22.4m cost secured with a gap of £8.1m. MHCLG investment would accelerate the project and de-risk its delivery enabling: (i) the OJEU main works procurement to commence in July 20 with an appointment by December 2020 and construction by financial year 2021/22; (ii) delivery of a number of LEP priorities and initiatives including the LIS and network Staffordshire and; (iii) a minimum £17m GVA per annum economic impact. | Newcastle-under-Lyme (Keele University) | 1521157 | 6100000 |  | In progress | The Innovation Centre Seven project is progressing well following appointment of Bowmer and Kirkland (B&K) as the main works contractor with onsite activities commencing April 2021. There have however been slight programme delays due to: (i) Tenderers for the main works contract asking for a two week extension to their tender preparation timescale due to the impact of the latest lockdown and the construction cost is also higher than originally envisaged (for which a mitigation strategy is in place). (ii) Inclement weather (accounting for a three day delay). (iii) The movement of badgers into the site exclusions zone and the discovery of a third sett which has necessitated re-sequencing of the car park works resulting in a minor level of under investment against the £1.5m predicted for Quarter Two. (iv) There is also an emergent risk of a delay to completion of the steel frame which is currently being discussed with the contractor. These programme delays will not impact detrimentally on full GBF investment in 2021/22 financial year. IC7 delivery team recruitment and selection commenced. Significant dialogue with potential tenants. | Progressing well. Some spend slippage in Q1 and Q2 but mitigation is in place.
Creative Lab (formerly:New Enterprise Collaboratory) | Stoke-on-Trent & Staffordshire LEP has 38 new start-ups per 10,000 people, below national averages. Staffordshire University proposes a New Enterprise Accelerator to build on the successful BeInpsired (revenue) project which provides start-up advice and mentoring support. The new project will add a dedicated Enterprise & Innovation collaboratory enabling access to specialist equipment where start-up’s will share the 'co-working' environment within the wider university's Enterprise Zone, an evolving enterprise & innovation eco-system. The university will award a small capital grants to start-ups in priority sectors as identified in the Local Industrial Strategy where collaboratory does not satisfy bespoke start up needs. | Stoke on Trent (Staffordshire University) | 379743 | 500000 |  | Complete | The construction, networking and digital infrastructure for this space is now complete. All equipment and furniture have been procured and the majority is now installed except for a couple of items which are delayed in transit. Signage for the space has been added. The Creative Lab is fully operational with its first event being hosted on 14/09/21. | Slight spend slippage but scheme completed on time
Powering Up Enterprise | The City Council have a scalable portfolio of underused commercial assets which with capital investment will be refurbished and repurposed for start ups, enterprise and innovation activities. The package of premises includes Swann House, Swift House, CoRE, Longton Town Hall, Clayworks, Spode (No5) which all require a range of capital investment to reshape and remodel along with installation of gigabit digital infrastructure. The resulting space, located across the City, will meet an existing demand for space. The blend of space will facilitate innovation, business start ups and even companies looking to temporarily downsize as a result of the pandemic. | Stoke-on-Trent | 0 | 2450000 |  | Starting on site from October onwards | Re-scoped scheme; MHCLG Change Request approved 15/06/2021. Contract is now completed. Construction starts at the various sites from October onwards. | Contract signed 30/09/21 Awaiting tender returns
SEF C - Digital Skills Academy (South Staffs College) | The Digital Skills Academy will provide digital hubs at Cannock & Tamworth to provide access to high quality skills training supported by state of the art physical and digitally simulated environments in order to develop the skills needed by local and regional employers, the same skills needs as identified earlier to which we have mapped provision. | South Staffordshire | 550262 | 550262 | 113 | Completed | GBF fully spent. £493,314 in-kind match recorded to date - it is expected that more will be reported in Q3 return.. Project launched 20.9.21, Cannock, 24.9.21 Tamworth. SSLEP and BEIS engaged. Forecast outputs are for KPIs at September 2022. KPIs for learners are reported after one full academic year. KPIs will also be monitored and reported at 5 academic years. New learners forecast is for learners achieving a full qualification. | Completed, outputs pending
SEF F - Creative and Digital Industries project phase 2 (Stoke on Trent College) | The scheme incorporates completion of remodelling and refurbishment of the New Library Building to create collaborative learning space for development of digital skills including coding and software engineering for Digital Arts and Engineering learners at advanced and higher levels enabling them to progress to Higher Education or local jobs. The scheme supports skills growth for existing and new business start-ups emerging from labour market restructuring in North Staffs and City of Stoke-on-Trent. Students will work in a modern, semi open-plan space, interacting with learners from other disciplines reflective of the work environment. The project also supports remote working and learning. | Stoke-on-Trent | 249523 | 249523 | 477 | Completed | Scheme completed. GBF and match spend complete. Awaiting details of project launch. 170m2 of learning floorspace delivered. Forecast outputs are for KPIs at September 2022. KPIs for learners are reported after one full academic year. KPIs will also be monitored and reported at 5 academic years. New learners forecast is for learners achieving a full qualification. | Completed, outputs pending
SEF H - Construction Industry Digital Technologies (CIDT) (Stoke on Trent College) | Digital technology will be a cornerstone of construction sector reform to productivity, efficiency and quality of delivery. The College will expand use of AR/ VR hubs at both sites to incorporate building information management hardware and software. Learners will be work ready to support supply of sites and commercial premises. In particular and in addition to current skills requirements, there will be emphasis on low carbon technology to future proof students’ skills and ensure significant improvements in economic productivity for the city and for the region. Learners from deprived communities local to college will benefit in particular from the scheme. | Stoke-on-Trent | 119757 | 119757 | 243 | Completed | Scheme completed. GBF and match spend complete. Awaiting details of project launch. Forecast outputs are for KPIs at September 2022. KPIs for learners are reported after one full academic year. KPIs will also be monitored and reported at 5 academic years. New learners forecast is for learners achieving a full qualification. | Completed, outputs pending
Shire Hall regeneration project | Re--purpose the Grade II* Listed Shire Hall to become a vibrant icon known across the region as an engine for entrepreneurialism and business start-up. The rear portion of the building (the old library), will be converted to become a WeWork style business incubator with small office suites and a large airy atrium. It will capitalise on the unique historic building to create a space that young entrepreneurs are attracted to. We are in discussions with Staffordshire University about working in partnership to create a pathway for graduates to utilise the space and we have our own Enterprise Centre team who are ready to manage the space. | Stafford | 92266 | 1600000 |  | In progress | Change of Use planning permission was granted on 8th July; listed building consent has been granted by the Secretary of State on 15/07/21. The main contractor went into liquidation just as the works were due to commence in September. Putting a new contractor in place could cause significant delay to the scheme. The scheme provided a briefing note to SPMG on 18/10/21. An alternate contractor who is on the SCC Framework and has extensive experience of heritage projects is to be put in place, subject to the tender meeting the project specifications and cost parameters. Reprofiling indicates that the scheme is still confident of being able to draw down the £1.6m Getting Building Fund contribution in full by the end of March 2022, with the balance of match funding from SCC being fully expended by the end of June 2022 | Progressing. Some slippage but mitigation in place.
Staffordshire Local Sustainable Transport Package | 3.6km walking/cycling infrastructure in Tamworth, Biddulph, Burton, Uttoxeter, Burntwood and Eccleshall facilitating a Green recovery and continuing the rediscovery of active travel seen in the COVID-19 pandemic. Builds on delivery of previous LEP supported Local Sustainable Transport packages, enabling another phase of improvements. Cycle/pedestrian routes will be created to a width that maintains social distancing on National Cycle Network and within town centres, supporting Masterplan and community priorities. Tamworth improvements are on a key corridor where cycling collisions have been recorded. Further benefits include health and mental well-being, access to jobs, social inclusivity and a sustainable alternative to public transport. | County-wide: Tamworth, Biddulph, Burton, Uttoxeter, Burntwood and Eccleshall) | 251789 | 651000 |  | In progress | Contractually committed and in progress. The programme is on track for delivery. The Uttoxeter, Eccleshall and Tamworth schemes are complete and detailed design and consultation is progressing on the Burton upon Trent, Biddulph and Burntwood schemes. Outputs: 1.1Km of cycling/pedestrain enhancements have been reported in Q4. | Progressing well
SEF G - JCB Automation and Robotics Suite | The scheme will create an Automation & Robotics Suite to include a Control and Automation Suite, a cad & visualisation suite and an independent study area. The suite will enable the expansion of curriculum in both the mechanical and electronic sector from level 1 to level 3. The facility will provide a bureau of specialist knowledge and equipment and will allow smaller employers access to emerging technologies and advice. | East Staffs | 86260 | 87093 |  | In progress | 1 of 4 contingency schemes to be progressed with funding reallocated from the withdrawn GBF scheme and surplus GBF from the rescoped Powering Up Enterprise scheme. (MHCLG Change Request approved 15/06/2021). SSLEP funding is a mixture of GBF (as shown, left) and other SSLEP funds (LGF switch funds). Scheme is progressing well, GBF is fully spent and 30% of forecasted match has already been spent | All GBF spent. Progressing well
Church Street Gaming Hub | The Church Street Gaming Hub is a collaboration between Stoke-on-Trent City Council, VX Fiber and Staffordshire University in part of the Spode site. With a strong focus on the more innovative area of game streaming platforms the hub will provide educational and training support for video game development and programming across the community, offering digital skill opportunities for those upskilling, for school leavers and NEETS, as well as opportunities for graduate internships. Encouraging engagement with the central hub through a community hub system, the Innovation Hub will provide opportunities for all areas of the community. As well as an educational and training function the hub will provide an ideal environment as an incubator for business start-ups. | Stoke on Trent | 0 | 97042 |  | In progress | 2 of 4 contingency schemes to be progressed with funding reallocated from the withdrawn GBF scheme and surplus GBF from the rescoped Powering Up Enterprise scheme. (MHCLG Change Request approved 15/06/2021). SSLEP funding is a mixture of GBF (as shown, left) and other SSLEP funds (LGF switch funds) Contract completed on 30/09/21. Works are due to start October 2021. | Contract signed 30/09/21. Pending start
Cornhill Small Business Units | Delivery of Small business units in rural market town to meet demand for micro-business start-up and grow on space for business. | Staffordshire Moorlands | 0 | 291128 |  | Pending contract | 3 of 4 contingency schemes to be progressed with funding reallocated from the withdrawn GBF scheme and surplus GBF from the rescoped Powering Up Enterprise scheme. (MHCLG Change Request approved 15/06/2021). SSLEP funding is a mixture of GBF (as shown, left) and other SSLEP funds (LGF switch funds) STATUS: chasing Heads of Terms so that contract can be drafted. There is some uncertainty re ability of the scheme to deliver within the funding spend timescale. | Awaiting contract
Cleveland Future Skills Hub | Capital investment is sought for Phase 1 of the submission made in Summer 2020. The investment will provide refurbished facilities enabling more flexible education areas – providing greater capacity and improved resilience for the delivery of training courses. (e.g. in Covid-secure teaching arrangements). It will also enable PM Training to deliver the digital elements of their original submission – including digital and creative skills (e.g. Cyber Security, Digital Support, Software development, IS Solutions). | Stoke on Trent | 0 | 64695 |  | Starts 22/11/21 | 4 of 4 contingency schemes to be progressed with funding reallocated from the withdrawn GBF scheme and surplus GBF from the rescoped Powering Up Enterprise scheme. (MHCLG Change Request approved 15/06/2021). SSLEP funding is a mixture of GBF (as shown, left) and other SSLEP funds (LGF switch funds) STATUS: contract completed 12/11/21. Scheme is forecast to complete by end March 2021. | Contract signed 12/11/21 Pending start
|  |  | 9140257 | 18650000 | 833
|  |  | GBF spent to date | Total GBF allocated | Total underspend
GBF - contractual position |  |  |  | %
GBF schemes contractually committed: | 13 schemes contracted | Value | 18358872 | 98.44%
Pending contract | 1 scheme - contract pending | Value | 291128 | 1.561%
|  | Total | 18650000

## By District
Scheme | District | GBF grant | Area total | District | Allocation | %
Drakelow Park (SSLEP as co-investor) | South Derbyshire/ East Staffordshire | 5050000 | East Staffs £5,136,260 | East Staffs | 5136260 | 21.67%
SEF G - JCB Automation and Robotics Suite | East Staffs | 86260 |  | South Staffs | 3550375 | 14.98%
i54 Western Extension | South Staffordshire | 3000000 | South Staffs £3,550,375 | Stafford | 4489500 | 18.94%
SEF C - Digital Skills Academy (South Staffs College) | South Staffordshire | 550375 |  | Stoke on Trent | 3481737 | 14.69%
Health Innovation Centre, Blackheath Lane | Stafford (Staffordshire University) | 2889500 | Stafford £4,489,500 | Newcastle-u-Lyme | 6100000 | 25.74%
Shire Hall regeneration project | Stafford | 1600000 |  | Staffs Moorlands | 291128 | 1.228%
Creative Lab (New Enterprise Collaboratory) | Stoke on Trent (Staffordshire University) | 500000 | Stoke-on-Trent £3,481,737 | County-wide | 651000 | 2.747%
Powering Up Enterprise | Stoke-on-Trent | 2450000 |  |  | 23700000 | 100%
SEF F - Creative and Digital Industries project phase 2. (Stoke on Trent College) | Stoke-on-Trent | 250000 |  |  |  |  | Includes Drakelow
SEF H - Construction Industry Digital Technologies (CIDT) (Stoke on Trent College) | Stoke-on-Trent | 120000
Church Street Gaming Hub | Stoke on Trent | 97042
Cleveland Future Skills Hub | Stoke on Trent | 64695
Innovation Centre Seven | Newcastle-under-Lyme (Keele University) | 6100000 | Newcastle-u-Lyme £6,100,000
Cornhill Small Business Units | Staffordshire Moorlands | 291128 | Staffs Moorlands £291,128
Staffordshire Local Sustainable Transport Package | County-wide: Tamworth, Biddulph, Burton, Uttoxeter, Burntwood and Eccleshall) | 651000 | County-wide £651,000

## GBF and Match - Totals
Match funding
Schemes are being encouraged to spend GBF grant prior to drawing down sources of match funding, to mitigate against delays in spend during the very limited timescale of the GBF programme.
GBF grant spend and Match funding spend to date
Match funding reported to date Q1 2020/21 | Total scheme budget | SSLEP GBF grant per scheme | Total GBF spend reported to date | % of GBF allocation spent to date | Total match funding forecast | of which is LA forecast | of which is Other Public forecast | of which is Private match forecast | % of overall budget that is private match forecast | Total Match funding reported to date
Drakelow Park (D2N2 to claim outputs) | 0 | 0 |  | 0% | 0 | 0 | 0 | 0 | 0% | 0
The Centre for Health Innovation | 5779000 | 2889500 | 2889500 | 100% | 2889500 | 0 | 0 | 2889500 | 50% | 341668
i54 Western Extension (reported through LGF) | 27262000 | 3000000 | 3000000 | 100% | 24262000 | 10487000 | 13775000 | 0 | 0% | 0
Keele Innovation Centre 7 | 14400000 | 6100000 | 1521157 | 24.94% | 8300000 | 0 | 8180000 | 120000 | 0.8333% | 2210000
Creative Lab (New Enterprise Collaboratory) | 721600 | 500000 | 379743 | 75.95% | 221600 | 0 | 0 | 221600 | 30.71% | 0
Powering Up Enterprise | 3666295 | 2450000 | 0 | 0% | 1216295 | 571295 | 0 | 645000 | 17.59% | 0
SEF C - Digital Skills Academy (South Staffs College) | 1213662 | 550262 | 550262 | 100% | 663400 | 0 | 0 | 663400 | 54.66% | 493314
SEF F - Creative and Digital Industries project phase 2 (Stoke on Trent College) | 349523 | 249523 | 249523 | 100% | 100000 | 0 | 100000 | 0 | 0% | 98717
SEF H - Construction Industry Digital Technologies (CIDT) (Stoke on Trent College) | 164757 | 119757 | 119757 | 100% | 45000 | 0 | 45000 | 0 | 0% | 44058
Shire Hall regeneration project | 2000000 | 1600000 | 92266 | 5.767% | 400000 | 400000 | 0 | 0 | 0% | 0
Staffordshire Local Sustainable Transport Package | 859000 | 651000 | 251789 | 38.68% | 208000 | 35000 |  | 173000 | 20.14% | 166576
SEF G - JCB Automation and Robotics Suite | 272710 | 87093 | 86260 | 99.04% | 185617 |  | 85617 | 100000 | 36.67% | 56873
Church Street Gaming Hub | 450000 | 97042 | 0 | 0% | 352958 | 260000 | 92958 | 0 | 0% | 0
Cornhill Small Business Units | 1309846 | 291128 | 0 | 0% | 1018718 | 734846 | 283872 | 0 | 0% | 0
Cleveland Future Skills Hub | 251000 | 64695 | 0 | 0% | 186305 | 0 | 60805 | 125500 | 50% | 0
| Total schemes: budget | GBF allocation: | GBF actual spend to date: | % of GBF spent to date | Total match funding forecast | 12488141 | 22623252 | 4938000 | 12.33% | Total Match funding achieved to date
| 58699393 | 18650000 | 9140257 | 49.01% | 40049393 | LA match forecast | Other public forecast | Private match spend forecast | % of match forecast that is private match | 3411206
|  | Total GBF remaining | % of forecast GBF spend achieved to date |  | % of forecast match in total budget |  | * of which £523,252 is Other SSLEP funding |  |  | % of forecast match achieved to date
|  | 50.99% | 49.01% |  | 68.23% |  |  |  |  | 8.517%
Amended in Q2 MHCLG reporting but not in the SPMG reports.
GBF underspend £833 moved from the SEF C,F,H schemes to SEFG and the SSLEP other funding for SEF G reduced by £833
Note on D12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Underspend reallocated to SEF G
Note on J12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: In kind match
Note on D13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Underspend reallocated to SEF G
Note on D14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Underspend reallocated to SEF G
Note on D17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Underspend from the other SEF schemes was reallocated to this scheme - increasing the GBF allocation by £833 and reducing the SSLEP "Other" funding from reserves by £833.
Note on I17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Underspend from the other SEF schemes was reallocated to this scheme - increasing the GBF allocation by £833 and reducing the SSLEP "Other" funding from reserves by £833.
Note on J21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes £663,400 "in kind" match

## GBF and Match - by Quarter
Total match funding forecast: | 40049393 | LA forecast | 12488141 | Other Public forecast | 22623252 | Private forecast | 4938000
| Total Match funding reported to date | of which is LA |  | of which is Other Public |  | of which is Private |  | of which is 3rd sector |  | Q2 Match |  | GBF spend in Q2
Drakelow Park (D2N2 to claim outputs) | 0 | #DIV/0! | [8 empty] | GBF to be de-allocated | 0
The Centre for Health Innovation | 341668 | 0 |  | 0% |  | 100% | 341668 |  |  | 341668 | Private | 465986
i54 Western Extension (reported through LGF) | 0 | [9 empty] | Reported via LGF return | 0
Keele Innovation Centre 7 | 2210000 | 0 |  | 100% | 2210000 | 0% |  |  |  | 2210000 | Other public (EU) | 1158582
Creative Lab (New Enterprise Collaboratory) | 0 | #DIV/0! |  | #DIV/0! |  | #DIV/0! | [5 empty] | 289763
Powering Up Enterprise | 0 | #DIV/0! |  | #DIV/0! |  | #DIV/0! | [5 empty] | 0
SEF C - Digital Skills Academy (South Staffs College) | 493314 | 0 |  | 0% |  | 100% | 493314 |  |  |  | In-kind | 0
SEF F - Creative and Digital Industries project phase 2 (Stoke on Trent College) | 98717 | 0 |  | 100% | 98717 | 0% |  |  |  | 87047 | College | 218383
SEF H - Construction Industry Digital Technologies (CIDT) (Stoke on Trent College) | 44058 | 0 |  | 100% | 44058 | 0% |  |  |  | 29296 | College | 78124
Shire Hall regeneration project | 0 | #DIV/0! |  | #DIV/0! |  | #DIV/0! | [5 empty] | 92266
Staffordshire Local Sustainable Transport Package | 166576 | 0 |  | 0% |  | 100% | 166576 |  |  |  |  | 27573
SEF G - JCB Automation and Robotics Suite | 56873 | 0 |  | 9.006% | 5122 | 90.99% | 51751 |  |  | 56873 | £5,122 Other Public (LEP) + £51,751 JCB private match | 86260
Church Street Gaming Hub | 0 | #DIV/0! |  | #DIV/0! |  | #DIV/0! | [5 empty] | 0
Cornhill Small Business Units | 0 | #DIV/0! |  | #DIV/0! |  | #DIV/0! | [5 empty] | 0
Cleveland Future Skills Hub | 0 | #DIV/0! |  | #DIV/0! |  | #DIV/0! | [5 empty] | 0
| Total Match funding achieved to date |  | LA match reported |  | Public match reported |  | Private match reported |  | 3rd sector match reported | Match funding reported in Q2 |  | GBF spend reported in Q2
| 3411206 |  | 0 |  | 2357897 |  | 1053309 |  | 0 | 2724884 |  | 2416937
% of forecast match achieved to date
8.517%
[11 empty] | Total match forecast | 40049393
[11 empty] | Total match achieved to end of Q2 | 3411206
[9 empty] | LA match | Other public match | Private match
[8 empty] | Forecast | 12488141 | 22623252 | 4938000
[8 empty] | Achieved | 0 | 2357897 | 1053309
Note on F9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Public sector match funding of £1.3m provided in 2020/21 and £0.91m to date in Quarter Two 2021/22 (£0.18m Qtr1 and £0.73m Qtr 2).
Note on H12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: "In-kind"

## GBF Outputs
Getting Building Fund - Outputs
GBF Forecast Project Outputs (Baseline) | FORECAST OUTPUTS
Q1 21/22
GBF schemes - Forecast Outputs (includes those to be reported in the BEIS return + future years) | Jobs created | Construction jobs | Jobs safeguarded | Sqm Commercial floorspace | Sqm R&D Floorspace | Businesses assisted | Km walking/ cycleways | Sqm Learning/ Training space | New learners assisted | Sqm public realm created or improved
Drakelow Park (D2N2 to claim outputs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
The Centre for Health Innovation | 115 | 0 | 0 | 0 | 0 | 0 | 0 | 1230 | 500 | 0
i54 Western Extension | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Keele Innovation Centre 7 | 174 | 53 | 34 | 2696 | 0 | 0 | 0 | 0 | 0 | 0
Creative Lab (New Enterprise Collaboratory) | 44 | 0 | 0 | 147 | 30 | 22 | 0 | 0 | 0 | 0
Powering Up Enterprise (RE-SCOPED) | 339 | 37 | 0 | 3097 | 0 | 70 | 0 | 0 | 0 | 0
SEF C - Digital Skills Academy (South Staffs College) | 57 | 0 | 0 | 0 | 0 | 43 | 0 | 600 | 32 | 0
SEF F - Creative and Digital Industries project phase 2 (Stoke on Trent College) | 30 | 0 | 5 | 0 | 0 | 5 | 0 | 170 | 66 | 0
SEF H - Construction Industry Digital Technologies (CIDT) (Stoke on Trent College) | 60 | 0 | 1 | 0 | 0 | 5 | 0 | 0 | 50 | 0
Shire Hall regeneration project | 60 | 14 | 0 | 12000 | 0 | 21 | 0 | 0 | 0 | 0
Staffordshire Local Sustainable Transport Package | 0 | 0 | 0 | 0 | 0 | 0 | 3.6 | 0 | 0 | 0
SEF G - JCB Automation and Robotics Suite | 31 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 36 | 0
Church Street Gaming Hub | 5 | 0 | 0 | 290 | 0 | 0 | 0 | 0 | 20 | 0
Cornhill Small Business Units | 23 | 0 | 0 | 715 | 0 | 7 | 0 | 0 | 0 | 23
Cleveland Future Skills Hub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1184 | 45 | 0
Totals | 938 | 104 | 40 | 18945 | 30 | 203 | 3.6 | 3184 | 749 | 23
Note: MHCLG return form only reports outputs up to March 2026 - additional outputs are included above (see comments in specific cells)
GBF Project Outputs - Summary of Actuals achieved | OUTPUTS - ACHIEVED by end of Q4 20/21 | [9 empty] | % of outputs achieved against overall forecast | % of total forecast achieved to end of Q4 20/21
GBF schemes - Forecast Outputs | Jobs created | Construction jobs | Jobs safeguarded | Sqm Commercial floorspace | Sqm R&D Floorspace | Businesses assisted | Km walking/ cycleways | Sqm Learning/ Training space | New learners assisted | Sqm public realm created or improved |  | Jobs created | Construction jobs | Jobs safeguarded | Sqm Commercial floorspace | Sqm R&D Floorspace | Businesses assisted | Km walking/ cycleways | Sqm Learning/ Training space | New learners assisted | Sqm public realm created or improved
Drakelow Park (D2N2 to claim outputs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Drakelow Park (D2N2 to claim outputs)
The Centre for Health Innovation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | The Centre for Health Innovation | 0% | [6 empty] | 0% | 0%
i54 Western Extension | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | i54 Western Extension
Keele Innovation Centre 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Keele Innovation Centre 7 | 0% | 0% | 0% | 0%
Creative Lab (New Enterprise Collaboratory) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Creative Lab (New Enterprise Collaboratory) | 0% |  |  | 0% | 0% | 0%
Powering Up Enterprise (RE-SCOPED) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Powering Up Enterprise (RE-SCOPED) | 0% | 0% |  | 0% |  | 0%
SEF C - Digital Skills Academy (South Staffs College) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | SEF C - Digital Skills Academy (South Staffs College) | 0% |  |  |  |  | 0% |  | 0% | 0%
SEF F - Creative and Digital Industries project phase 2 (Stoke on Trent College) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | SEF F - Creative and Digital Industries project phase 2 (Stoke on Trent College) | 0% |  | 0% |  |  | 0% |  | 0% | 0%
SEF H - Construction Industry Digital Technologies (CIDT) (Stoke on Trent College) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | SEF H - Construction Industry Digital Technologies (CIDT) (Stoke on Trent College) | 0% |  | 0% |  |  | 0% |  |  | 0%
Shire Hall regeneration project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Shire Hall regeneration project | 0% | 0% |  | 0% |  | 0%
Staffordshire Local Sustainable Transport Package | 0 | 0 | 0 | 0 | 0 | 0 | 1.1 | 0 | 0 |  | Staffordshire Local Sustainable Transport Package | [6 empty] | 30.56%
SEF G - JCB Automation and Robotics Suite | [10 empty] | SEF G - JCB Automation and Robotics Suite | 0% |  |  |  |  | 0% |  |  | 0%
Church Street Gaming Hub | [10 empty] | Church Street Gaming Hub | 0% |  |  | 0% |  |  |  |  | 0%
Cornhill Small Business Units | [10 empty] | Cornhill Small Business Units | 0% |  |  | 0% |  | 0% |  |  |  | 0%
Cleveland Future Skills Hub | [10 empty] | Cleveland Future Skills Hub | [7 empty] | 0% | 0%
Totals | 0 | 0 | 0 | 0 | 0 | 0 | 1.1 | 0 | 0 | 0 | Totals | 0% | 0% | 0% | 0% | 0% | 0% | 30.56% | 0% | 0% | 0%
GBF Project Outputs - Summary of Actuals achieved | OUTPUTS - ACHIEVED by end of Q1 21/22 | [9 empty] | GBF Project Outputs - Summary of Actuals achieved | OUTPUTS - TOTAL ACHIEVED by end of Q1 21/22 Q4 + Q1 (formulae already entered below) | [9 empty] | % of outputs achieved against overall forecast | % of total forecast achieved to end of Q1 21/22
GBF schemes - Forecast Outputs | Jobs created | Construction jobs | Jobs safeguarded | Sqm Commercial floorspace | Sqm R&D Floorspace | Businesses assisted | Km walking/ cycleways | Sqm Learning/ Training space | New learners assisted | Sqm public realm created or improved | GBF schemes - Forecast Outputs | Jobs created | Construction jobs | Jobs safeguarded | Sqm Commercial floorspace | Sqm R&D Floorspace | Businesses assisted | Km walking/ cycleways | Sqm Learning/ Training space | New learners assisted | Sqm public realm created or improved |  | Jobs created | Construction jobs | Jobs safeguarded | Sqm Commercial floorspace | Sqm R&D Floorspace | Businesses assisted | Km walking/ cycleways | Sqm Learning/ Training space | New learners assisted | Sqm public realm created or improved
Drakelow Park (D2N2 to claim outputs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Drakelow Park (D2N2 to claim outputs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Drakelow Park (D2N2 to claim outputs)
The Centre for Health Innovation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The Centre for Health Innovation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The Centre for Health Innovation | 0% | [6 empty] | 0% | 0%
i54 Western Extension | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | i54 Western Extension | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | i54 Western Extension
Keele Innovation Centre 7 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Keele Innovation Centre 7 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Keele Innovation Centre 7 | 0% | 32.08% | 0% | 0%
Creative Lab (New Enterprise Collaboratory) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Creative Lab (New Enterprise Collaboratory) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Creative Lab (New Enterprise Collaboratory) | 0% |  |  | 0% | 0% | 0%
Powering Up Enterprise (RE-SCOPED) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Powering Up Enterprise (RE-SCOPED) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Powering Up Enterprise (RE-SCOPED) | 0% | 0% |  | 0% |  | 0%
SEF C - Digital Skills Academy (South Staffs College) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SEF C - Digital Skills Academy (South Staffs College) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SEF C - Digital Skills Academy (South Staffs College) | 0% |  |  |  |  | 0% |  | 0% | 0%
SEF F - Creative and Digital Industries project phase 2 (Stoke on Trent College) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SEF F - Creative and Digital Industries project phase 2 (Stoke on Trent College) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SEF F - Creative and Digital Industries project phase 2 (Stoke on Trent College) | 0% |  | 0% |  |  | 0% |  | 0% | 0%
SEF H - Construction Industry Digital Technologies (CIDT) (Stoke on Trent College) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SEF H - Construction Industry Digital Technologies (CIDT) (Stoke on Trent College) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SEF H - Construction Industry Digital Technologies (CIDT) (Stoke on Trent College) | 0% |  | 0% |  |  | 0% |  |  | 0%
Shire Hall regeneration project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Shire Hall regeneration project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Shire Hall regeneration project | 0% | 0% |  | 0% |  | 0%
Staffordshire Local Sustainable Transport Package | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Staffordshire Local Sustainable Transport Package | 0 | 0 | 0 | 0 | 0 | 0 | 1.1 | 0 | 0 | 0 | Staffordshire Local Sustainable Transport Package | [6 empty] | 30.56%
SEF G - JCB Automation and Robotics Suite | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SEF G - JCB Automation and Robotics Suite | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SEF G - JCB Automation and Robotics Suite | 0% |  |  |  |  | 0% |  |  | 0%
Church Street Gaming Hub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Church Street Gaming Hub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Church Street Gaming Hub | 0% |  |  | 0% |  |  |  |  | 0%
Cornhill Small Business Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cornhill Small Business Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cornhill Small Business Units | 0% |  |  | 0% |  | 0% |  |  |  | 0%
Cleveland Future Skills Hub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cleveland Future Skills Hub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cleveland Future Skills Hub | [7 empty] | 0% | 0%
Totals | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Totals | 0 | 17 | 0 | 0 | 0 | 0 | 1.1 | 0 | 0 |  | Totals | 0% | 16.35% | 0% | 0% | 0% | 0% | 30.56% | 0% | 0% | 0%
GBF Project Outputs - Summary of Actuals achieved | OUTPUTS - ACHIEVED in Q2 21/22 | [9 empty] | GBF Project Outputs - Summary of Actuals achieved | OUTPUTS - TOTAL ACHIEVED by end of Q2 21/22 Q4 + Q1 + Q2 (formulae already entered below) | [9 empty] | % of outputs achieved against overall forecast | % of total forecast achieved to end of Q2 21/22
GBF schemes - Forecast Outputs | Jobs created | Construction jobs | Jobs safeguarded | Sqm Commercial floorspace | Sqm R&D Floorspace | Businesses assisted | Km walking/ cycleways | Sqm Learning/ Training space | New learners assisted | Sqm public realm created or improved | GBF schemes - Forecast Outputs | Jobs created | Construction jobs | Jobs safeguarded | Sqm Commercial floorspace | Sqm R&D Floorspace | Businesses assisted | Km walking/ cycleways | Sqm Learning/ Training space | New learners assisted | Sqm public realm created or improved |  | Jobs created | Construction jobs | Jobs safeguarded | Sqm Commercial floorspace | Sqm R&D Floorspace | Businesses assisted | Km walking/ cycleways | Sqm Learning/ Training space | New learners assisted | Sqm public realm created or improved
Drakelow Park (D2N2 to claim outputs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Drakelow Park (D2N2 to claim outputs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Drakelow Park (D2N2 to claim outputs)
The Centre for Health Innovation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The Centre for Health Innovation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The Centre for Health Innovation | 0% | [6 empty] | 0% | 0%
i54 Western Extension | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | i54 Western Extension | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | i54 Western Extension
Keele Innovation Centre 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Keele Innovation Centre 7 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Keele Innovation Centre 7 | 0% | 32.08% | 0% | 0%
Creative Lab (New Enterprise Collaboratory) | 0 | 0 | 0 | 147 | 0 | 0 | 0 | 0 | 0 | 0 | Creative Lab (New Enterprise Collaboratory) | 0 | 0 | 0 | 147 | 0 | 0 | 0 | 0 | 0 | 0 | Creative Lab (New Enterprise Collaboratory) | 0% |  |  | 100% | 0% | 0%
Powering Up Enterprise (RE-SCOPED) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Powering Up Enterprise (RE-SCOPED) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Powering Up Enterprise (RE-SCOPED) | 0% | 0% |  | 0% |  | 0%
SEF C - Digital Skills Academy (South Staffs College) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | SEF C - Digital Skills Academy (South Staffs College) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | SEF C - Digital Skills Academy (South Staffs College) | 0% |  |  |  |  | 0% |  | 100% | 0%
SEF F - Creative and Digital Industries project phase 2 (Stoke on Trent College) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170 | 0 | 0 | SEF F - Creative and Digital Industries project phase 2 (Stoke on Trent College) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170 | 0 | 0 | SEF F - Creative and Digital Industries project phase 2 (Stoke on Trent College) | 0% |  | 0% |  |  | 0% |  | 100% | 0%
SEF H - Construction Industry Digital Technologies (CIDT) (Stoke on Trent College) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SEF H - Construction Industry Digital Technologies (CIDT) (Stoke on Trent College) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SEF H - Construction Industry Digital Technologies (CIDT) (Stoke on Trent College) | 0% |  | 0% |  |  | 0% |  |  | 0%
Shire Hall regeneration project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Shire Hall regeneration project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Shire Hall regeneration project | 0% | 0% |  | 0% |  | 0%
Staffordshire Local Sustainable Transport Package | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Staffordshire Local Sustainable Transport Package | 0 | 0 | 0 | 0 | 0 | 0 | 1.1 | 0 | 0 | 0 | Staffordshire Local Sustainable Transport Package | [6 empty] | 30.56%
SEF G - JCB Automation and Robotics Suite | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SEF G - JCB Automation and Robotics Suite | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SEF G - JCB Automation and Robotics Suite | 0% |  |  |  |  | 0% |  |  | 0%
Church Street Gaming Hub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Church Street Gaming Hub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Church Street Gaming Hub | 0% |  |  | 0% |  |  |  |  | 0%
Cornhill Small Business Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cornhill Small Business Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cornhill Small Business Units | 0% |  |  | 0% |  | 0% |  |  |  | 0%
Cleveland Future Skills Hub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cleveland Future Skills Hub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cleveland Future Skills Hub | [7 empty] | 0% | 0%
Totals | 0 | 0 | 0 | 147 | 0 | 0 | 0 | 770 | 0 |  | Totals | 0 | 17 | 0 | 147 | 0 | 0 | 1.1 | 770 | 0 |  | Totals | 0% | 16.35% | 0% | 0.7759% | 0% | 0% | 30.56% | 24.18% | 0% | 0%
Note on C22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 100 are forecast for future years
Note on H22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5 are forecast for future years
Note on I22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Delta return rounds it to 4
Note on K22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 350 are reported for future years - mainly Centre for Health Innovation

## Forecast
OUTPUTS - FORECAST TIMELINE
GBF Forecast Project Outputs (Baseline)
GBF schemes - Forecast Outputs | 20/21 | 21/22 | 22/23 | 23/24 | 24/25 | 2025+
Drakelow Park (D2N2 to claim outputs)
The Centre for Health Innovation
i54 Western Extension
Keele Innovation Centre 7
Creative Lab (New Enterprise Collaboratory)
Powering Up Enterprise
SEF C - Digital Skills Academy (South Staffs College)
SEF F - Creative and Digital Industries project phase 2 (Stoke on Trent College)
SEF H - Construction Industry Digital Technologies (CIDT) (Stoke on Trent College)
Shire Hall regeneration project
Staffordshire Local Sustainable Transport Package
SEF G - JCB Automation and Robotics Suite
Church Street Gaming Hub
Cornhill Small Business Units
Cleveland Future Skills Hub
GBF - Outputs forecast by year
Outputs to be delivered | By year
| 2020/21 | 2021/22 | 2022/23 | 2023/24 | 2024/25 | Forecast for future years 2025 + | Total
Jobs created | 0 | 168 | 377 | 273 | 20 | 100 | 938
Construction jobs |  | 104 | 0 | 0 | 0 |  | 104
Jobs safeguarded | 0 | 6 | 14 | 20 | 0 |  | 40
Sqm Commercial floorspace | 0 | 16249 | 2696 | 0 | 0 |  | 18945
Sqm R&D Floorspace | 0 | 30 | 0 | 0 | 0 |  | 30
Businesses assisted | 0 | 56 | 104 | 33 | 5 | 5 | 203
Km walking/ cycleways | 1.1 | 2.5 | 0 | 0 | 0 |  | 3.6
Sqm Learning/ Training space | 0 | 3184 | 0 | 0 | 0 |  | 3184
New learners assisted | 0 | 148 | 151 | 50 | 50 | 350 | 749
Sqm public realm created or improved | 0 | 23 | 0 | 0 | 0 |  | 23
115 jobs over 10 years
500 learners trained over 10 years
1,230 sq m
Training space
Outputs will be monitored by and claimed by D2N2
Outputs will be captured through SSLEP LGF reporting
2,696 sqm comm'cial floorspace
53 construction jobs
44 jobs created
174 jobs created
34 safeguarded
147 sqm comm'cial floorspace
22 businesses assisted
600 collaboratory users
37 construction jobs
3,097 sqm comm'cial floorspace
70 businesses asst'd
339 jobs created
57 jobs created
43 businesses asst'd
30 jobs created
5 safeguarded
5 businesses asst'd
60 jobs created
1 safeguarded
5 businesses asst'd
60 jobs created
14 construction jobs
12,000 sqm comm'cial floorspace
5 businesses asst'd
3.6k walk/cycleways
31 jobs created
36 learners assisted
30 businesses assisted
1,184 sqm comm'cial
floorspace improved
20 x apprenticeships
25 traineeships starts
10 work experience placements
715 sqm new comm'cial
floorspace
23 jobs created
7 businesses assisted
290 sqm new comm'cial
floorspace
5 jobs created
20 new learners (not FTE)

## GBF Outputs OLD (hidden)
GBF - Forecast Outputs
GBF schemes | Jobs created | Construction jobs | Jobs safeguarded | Sqm Commercial floorspace | Sqm R&D Floorspace | Businesses assisted | Km walking/ cycleways | Sqm Learning/ Training space | New learners assisted
Drakelow Park | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Health Innovation Centre | 115 | 0 | 0 | 0 | 0 | 0 | 0 | 1230 | 500
i54 Western Extension | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Keele Innovation Centre 7 | 174 | 53 | 34 | 2696 | 0 | 0 | 0 | 0 | 0
New Enterprise Collaboratory | 44 | 0 | 0 | 147 | 30 | 22 | 0 | 0 | 0
Powering Up Enterprise | 420 | 30 | 0 | 8745 | 0 | 130 | 0 | 0 | 0
SEF C - Digital Skills Academy (South Staffs College) | 57 | 0 | 0 | 0 | 0 | 43 | 0 | 600 | 32
SEF F - Creative and Digital Industries project phase 2 (Stoke on Trent College) | 30 | 0 | 5 | 0 | 0 | 5 | 0 | 170 | 66
SEF H - Construction Industry Digital Technologies (CIDT) (Stoke on Trent College) | 60 | 0 | 1 | 0 | 0 | 5 | 0 | 0 | 50
Shire Hall regeneration project | 60 | 14 | 0 | 12000 | 0 | 21 | 0 | 0 | 0
Staffordshire Local Sustainable Transport Package | 0 | 0 | 0 | 0 | 0 | 0 | 3.6 | 0 | 0
Unallocated (£190k) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Totals | 960 | 97 | 40 | 23588 | 30 | 226 | 3.6 | 2000 | 648