## Strategic Risks
DRAFT SSLEP RISK REGISTER - Strategic |  |  |  |  | Item 9, App i
Risk Number | Category | Risk Detail | Impact | Likeli-hood | Mitigation | Overall Risk | Risk Owner | Date Identified | Date Reviewed
Strategic 24 | Strategic | Emerging policy/strategy contradicts direction of travel adopted | Medium | Low | Regular engagement with Government to maintain insight into emerging policy. Flexible, collaborative approach ensure agility and provides ability to adapt | Low
|  | Loss of strategic collaboration | Low | High | Co-design from concept to execution at all levels (Political/Operational) ensures collaboration throughout. | Low
|  | Limited influence of ‘Voice of Business’ to affect change | Low | High | Formal/informal commitment/declaration/pledge to listen to business voices will provide credibility. Case study/Mar-comms support to promote examples of private-sector influencing policy | Low
|  | Current legal structure costs (VAT implications) | High | High | Review of Governance/organisational structure and Assurance Framework to identify opportunities to achieve efficiency.
|  | (Near) future economic shocks could derail plans | Medium | High | Shared insight/intel and collaborative decision-making will ensure that resources are deployed and focused appropriately. | Medium
|  | Future funding | High | High | Careful deployment of existing resources, including reserves, as defined by Reserves Policy. Active Promotion of added-value achieved through new model and regular engagement with Government to assess risk/advocate for ongoing investment. Collective accountability for new vehicle will determine resource and scope of works. | Medium
|  | Loss of key personnel at Board resulting in Governance/quoracy issues | Medium | Medium | New Governance arrangements to be agreed including recruitment to any new evolved LEP/Business Partnership Board. | Medium
Strategic 29 | Operational | Loss of key personnel at operational level resulting in loss of momentum. | Medium | Medium | Review of Fixed-term posts in relation to new remit and structure and suring-up accordingly. | Medium
Strategic 27 & 28 |  | Managing demand on available resources. | Medium | High | Focused staff work programmes linked directly to Delivery Plan for all staff and strong communication/management of expectation amongst partners. | Low
|  | Inertia amongst partners/business and team | Medium | High | Active management of Delivery Plan progress and highly-accountable workforce reporting progress in to board. Momentum of meetings, actions and communications to demonstrate and celebrate progress. | Low
Strategic 22, ESIF 11 (Legacy Risks) | Governance | Lack of consistency regarding programme reporting leading to inaccurate or delayed information and governance limitations; specifically ERDF, ESF and ESIF | High | Medium | Regular communication and building relationships with Project Leads. | Medium |  | 2021-09-01
Strategic 25, 26 (Legacy Risk) | Financial | Reductions in 22/23 core budgets for services that the LEP is accountable for SSELP core team, Growth Hub, Careers Enterprise Hub etc. Likely to impact on service provision | High | High | Working with partners to redesign services. | High |  | 2022-02-02

## Programme Risks
DRAFT SSLEP RISK REGISTER - Programme
Risk Number | Category | Risk Detail | Impact | Likeli-hood | Mitigation | Overall Risk | Risk Owner | Date Identified | Date Reviewed
GBF 3, Skills 8,9,10 &11 (Legacy Risk) | Delivery | There is a risk that the SSLEP programme of Getting Building Fund schemes may not achieve forecast outputs or match funding. | Medium | Medium | Regular Project Review meetings with Project Managers to build relationships and capture information early. Funding Agreements include claw-back arrangements. | Low |  | 2020-10-01
NEW LGF | Delivery | There is a risk that the SSLEP programme of Local Growth Deal schemes may not achieve forecast outputs, match or leverage funding. | Medium | Medium | Regular Project Review meetings with Project Managers to build relationships and capture information early. Funding Agreements include claw-back arrangements. | Medium |  | 2019-04-01
GBF 11 (Legacy Risk) | Delivery | There is a risk the Drakelow project may be seriously delayed or fail to progress. | Medium | Low | Directed by a Delegated Authority Members Sub Group. Requirement for D2N2 to provide regular reportying updates. Signed Agreement for the transfer of GBF grant to DCC included claw-back arrangements. | Low |  | 2022-05-01
CDGD 27 & GPF 5 (Legacy Risk) | Delivery | There is a risk that the Blythe scheme may be seriously delayed or fail to progress. | Medium | Low | Directed by a Delegated Authority Members Sub Group. Regular Project Review meetings with Project Manager and connected parters in SCC Highways, SMDC to build relationships and capture information early. | Medium |  | 2021-07-01
CDGD 26 (Legacy Risk) | Delivery | DHN - Awating up date from Project Lead
GPF 2 (Legacy Risk) | Delivery | There is a risk that GPF loans may default or receive delayed repayments. | Medium | Medium | Loan repayment schedule included in GPF Funding Agreement together with explicit conditions stating the terms of the loan. Regular monitoring and close liaison with business applicant to identify any issues affecting the timely repayment of the loan. All GPF contracted schemes will be closely monitored to identify any potential default situations. | Low |  | 2018-11-01
NEW ERDF | Delivery | There is a risk of being unable to contract and spend the remaining DIT Internationalisation Fund budget | High | Medium | Action is underway to mitigate loss of funds and ensure full deployment. | Medium |  | 2022-06-01